## Read Me
GCSD Culinary Pathway ¦ Production Control Document
Master Execution Matrix
Title | Master Execution Matrix — GCSD Culinary Pathway Documentation and Website Project
Audience | Kevin McCann (Pathway Lead); production team
Purpose | Show, at a glance, every work package's deliverables, dependencies, current status, unresolved decisions, files produced, and QC status.
Owner | Lead Editor / Pathway Lead
Version | 6.2
Date | 2026-07-14
Approval / Planning Status | Planning document; not adopted district policy
Access Classification | RESTRICTED — production control document
Governing Source | Master Document Register v1.0, "Recommended Production Work Packages" table; Kevin McCann's 2026-07-12 quality-control corrections
Review Date | Update after every completed work package or Kevin McCann decision
Superseded Document | v6.1 superseded 2026-07-14 and archived as pathway-documents/_archive/GCSD_CulinaryPathway_Master-Execution-Matrix_v6.1_2026-07-14-ARCHIVED.xlsx. v6.2 adds verified GOV-01–GOV-07 produced-file evidence and updates GOV-09 to v1.1 without changing authorization, ownership, dependency, implementation, or owner visual-QA status.
Headline status
• REQUIRED CORRECTION PASS (Kevin McCann, 2026-07-12) — COMPLETE. Every item is resolved: (1) source-file immutability re-verified, no violation; (2) Work Package 3 now has the actual revised, versioned Culinary 1/2 and Advanced Culinary course documents — independently verified by the lead editor, not just self-reported — and is promoted to "Production complete — awaiting owner visual QA review"; (3) Kitchen Management's proposed (not active) status now stated prominently on CUR-03, all 4 KM-* documents, GOV-10 PA-05, three curriculum trackers (~101 cells), and the website; (4) the Cottage Client Agreement and all financial/operational records reconfirmed restricted, planning-draft, not for distribution, not linked publicly; (5) site-wide navigation unified across all 15 staged pages — one canonical 13-item nav, zero broken links, correct active-page state everywhere; (6) the stale Gateway 5 CUR-03 note corrected.
• Work Package 1 (Governance and Control) and Work Package 2A (Website Architecture) remain "production complete — awaiting owner visual QA review," unchanged by this pass.
• Work Package 4 (The Cottage and Kitchen Management) remains "production complete — awaiting owner visual QA review" — all Kitchen Management documents patched to v1.1 with the corrected proposed-status language as part of this pass.
Work Package 2B Phase 1 and Work Package 2B Phase 2A (Cottage and Kitchen Management detail pages, plus current conditional External WBL and Employer Partners pages replacing archived structure drafts) are both "production complete - awaiting owner visual QA review." No restricted Work Package 4 record is exposed on any public page - verified by scanning rendered text outside HTML comments.
• Work Package 6 (Employer, Mentor, Training Station, and Conditional External WBL System) is "production complete — awaiting owner visual QA review" — 18 files, consolidated down from 35 raw Register items. Every file independently verified to carry the exact boxed conditional statement (not just self-reported). 5 new legal-policy dependencies discovered and logged (LP-12 through LP-16) with source/verification-date/unresolved-dependency/responsible-reviewer fields — none invented.
• Work Package 2B Phase 2B (finalizing the Employer and Community Partners and External WBL public pages using Work Package 6's now-established framework) and the remaining Participant Resource Center pages are the next logical website step — not yet started, not commissioned this pass.
• Work Package 5 remains on hold, per standing instruction.
• See the "Execution Matrix" and "OPS Item Assignment" tabs for the full breakdown and the "Files Produced" tab for exact file paths. See the project-wide Production Control Log for the running change log, unresolved-decision log, and legal/policy verification flags — including the correction-pass entries and the new LP-11 (Cottage Client Agreement) item.

## Execution Matrix
GCSD Culinary Pathway Master Execution Matrix - v6.2 - 2026-07-14 - RESTRICTED - Planning document; not adopted district policy
Work Package | Register Categories | Deliverable Count | Owner / Assigned Role | Key Deliverables (sample) | Dependency / Gate | Current Status | Unresolved Decisions | QC Status
Work Package 1: Governance and Control | A (GOV-01–GOV-12) | 12 | Pathway Lead | Canon, Operating Principles, Register (existing); Glossary, Document Control Procedure, Authorization Register, Review Calendar, Companion Document Map (produced this pass) | P0 — must finish first; gates every other package. | Production complete — awaiting owner visual QA review | None outstanding for this package. Status holds at "awaiting visual review" until Kevin McCann inspects the Word documents and spreadsheets. | Passed internal QC (Section below); pending Kevin McCann visual review before distribution.
Work Package 2A: Website Architecture (pre-terminology-lock) | K (WEB-01, 13, 19, 22, 24); M (ARC-01–10 informed the audit); GOV-13 (relocated from provisional WEB-25) | 21 in scope (9 files produced) | Web Lead | Website Content Map and Migration Specification; page template standards (now GOV-13, a governance document); status-label system (points to GOV-10); document download index structure; content ownership and update schedule; Home page, Contact/Help/Concerns, Privacy and Records Notice, and Accessibility Statement produced as staged HTML (not deployed) | Depended on Work Package 1 (complete). Ran parallel to Work Package 3. Not deployed or published — staged in pathway-documents/work-package-2-website/. | Production complete — awaiting owner visual QA review | RESOLVED (UD-06, 2026-07-12): the Page Template Set is now GOV-13 (Website Page Template and Content Standards), relocated to pathway-documents/work-package-1-governance/ as a governance/publication-control document, not a public website page. | Passed internal QC (files open cleanly; live site confirmed untouched; no premature Gateway/credential claims on the Home page). Pending Kevin McCann visual review.
Work Package 2B Phase 1: Website Page Copy (terminology-locked, non-Cottage/KM) | K (WEB-03, 04, 05, 09, 11, 12, 23-partial) | 7 | Web Lead | Pathway at a Glance; Six Gateways and Culinary Passport (Gateway 6 boxed conditional); Courses and Learning Environments (full detail on Culinary 1/2/Advanced Culinary, brief deferred mentions of Cottage/KM/SkillsUSA/WBL); Students and Families overview; Credentials and Recognition; Results and Accountability; partial FAQ | Depended on Work Package 3 establishing authoritative instructional/assessment language — satisfied. Ran parallel to Work Package 4. | Production complete — awaiting owner visual QA review | All 7 pages set to "Internal Review" approval status (not yet "Approved for Planning Use" like the WP2A pages) since the Pathway Lead/Web Lead have not yet reviewed them. Credentials page: GOV-10 only has an explicit status row for ServSafe (PA-10) — other credentials have no individual GOV-10 row; recommend Kevin McCann confirm whether GOV-10 needs new rows for these. RESOLVED: the site-wide navigation inconsistency flagged here has been fixed — see the Website Navigation Unification note below. | Passed internal QC (all pages open cleanly, single H1, metadata block present, conditional-draft language verified present on WEB-04/05, SkillsUSA exploratory language verified, Cottage/KM sections confirmed brief and deferred, now updated to link to WEB-06/07). Pending Kevin McCann visual review.
Work Package 2B Phase 2A: Website Page Copy (Cottage, Kitchen Management, WBL/Employer structure) | K (WEB-06, 07 full; WEB-08, 10 current conditional pages) | 4 | Web Lead | The Cottage (full detail: educational purpose, client-centered learning, Gateway 4, Learning Before Labor, inquiry process - no internal records exposed); Leadership and Kitchen Management (full detail: leadership development, Gateway 5, Travel Rights, career readiness - proposed status stated repeatedly); External WBL page (current conditional public-safe page; not authorized for implementation); Employer and Community Partners page (current conditional public-safe page; no partnerships currently established) | Depended on Work Package 4 (Cottage/Kitchen Management operations, complete). Ran parallel to the WP3 course-document completion. | Production complete — awaiting owner visual QA review | None outstanding. Verified: no restricted Work Package 4 document (Client Agreement, Event Planning Packet, Closeout/Financial Record, Event Register) named or linked in visible content — confirmed by scanning rendered text outside HTML comments. Kitchen Management's proposed status stated at every section heading on WEB-07, not just once. | Passed internal QC (structural validation; restricted-content leakage scan clean; status language cross-checked against GOV-10 PA-05/06/08/09/14). Pending Kevin McCann visual review.
Website Navigation Unification (cross-package correction) | K (all 15 staged pages) | 15 | Lead Editor | One canonical 13-item primary navigation (matching the target public structure exactly) applied identically across all 15 staged pages, correct aria-current active-page state per page, unified footer Program/Connect columns, External WBL and Employer Partners nav entries visibly marked "in development" rather than presented as finished sections | Performed after Work Package 2B Phase 2A so every target page (or its placeholder) existed to link to. Required a full backup of staging-pages/ before the bulk edit. | Production complete — awaiting owner visual QA review | None outstanding. | Verified: exactly 1 distinct nav label-set across all 15 pages (previously 3 different sets); 0 broken links (every href resolves to an existing staged file); correct aria-current state on all 13 primary-nav pages; restricted-content leakage re-scanned clean after the bulk edit; all 15 pages retain exactly 1 H1 and a visible metadata block.
Work Package 3: Curriculum, Passport, and Gateways | B (CUR-01, 02, 05–08, all produced); C (CMP-01,02,03-07,08,14, consolidated) | 20 in scope (12 files + 1 manifest produced) | Pathway Team / Culinary Teachers | Actual revised, versioned Culinary 1/2 course document (real 35-week/9-unit content, not a memo) and Advanced Culinary course document (real 7-unit content); Course Alignment Memo (retained as the analysis record); reconciled Skills Map v1.2; Course-to-Gateway Evidence Crosswalk v1.1; Credential and Recognition Crosswalk; Assessment and Evidence Inventory v1.1; revised Employability Profile; Culinary Passport workbook; Gateway 1-5 rubrics v1.1 (stale CUR-03 note corrected); Gateway 6 rubric (CONDITIONAL PLANNING DRAFT); Evidence Naming and Storage Guide | Depended on Work Package 1 (complete); ran parallel to Work Package 2B Phase 2A. Required before full pathway implementation. | Production complete — awaiting owner visual QA review | CORRECTED and now COMPLETE (Kevin McCann's 2026-07-12 correction pass): the actual revised course documents now exist (CUR-01, 305 substantive paragraphs/5 tables; CUR-02, 172 paragraphs/9 tables) — independently verified, not just self-reported. Both original sources confirmed untouched (mtime 2026-07-07, unchanged). A genuine conflict was found and flagged, not silently resolved: the Skills Map's Culinary-1-vs-Culinary-2 week split (implying a Week ~12/13 boundary) does not match the source outline's actual continuous 35-week structure — open for course-team confirmation. Course-title confirmation notice present verbatim in both documents. Final WP3 manifest v2.0 supersedes v1.0 (archived). | Passed independent lead-editor verification (not just agent self-report, per the lesson from the prior QC correction): paragraph/table counts checked, all required metadata fields confirmed present, course-title caveat confirmed present, source mtimes reconfirmed unchanged, conflict-flagging confirmed genuine. Pending Kevin McCann visual review.
Work Package 4: The Cottage and Kitchen Management | E (SBE-01–19, consolidated to 6 files); F (KM-01–10, consolidated to 5 files); CUR-03; H (no OPS items assigned — see OPS Item Assignment tab) | 30 in scope (11 files produced) | SBE Lead / Kitchen Management Teacher | Cottage Operations and Instructional Guide; Event Planning Packet; Client Agreement (v1.1, strengthened restricted/not-for-distribution language); Event Closeout and Financial Reconciliation Record; Client Feedback Form; Cottage Event Register; Kitchen Management Scope and Sequence (CUR-03 v1.1, proposed-status notice added); Kitchen Management Student Leadership Handbook v1.1; Kitchen Management Event Leadership Packet v1.1; Leadership Observation Rubric v1.1; Career Readiness Completion Checklist v1.1 | Depended on Passport/Gateway definitions (Work Package 3, complete) and Book Three. Ran parallel to Work Package 2B Phase 1. | Production complete — awaiting owner visual QA review | CORRECTED (Kevin McCann's 2026-07-12 correction pass): producing CUR-03 does not establish Kitchen Management as an active district course — every Kitchen Management document (CUR-03 and all 4 KM-* documents) now carries a prominent "PROPOSED PLANNING DOCUMENT" notice, and GOV-10 PA-05 carries the exact required status language. The stale CMP-03-07 note (Work Package 3) has been corrected. Client Agreement (SBE-05 v1.1) now explicitly states restricted/internal, not authorized for distribution, not linked publicly, not an approved district contract — logged as LP-11 in the Legal-Policy Verification tab. | Passed internal QC (all files open cleanly; source materials/ confirmed untouched; "additional cooking instruction" and "catering business" framing both explicitly denied; Kitchen Management proposed-status language verified present on every applicable file). Pending Kevin McCann visual review.
Work Package 5: Student and Family Participant System | D (STU-01–21; FAM-01–10) | 31 | Pathway Team | Student and Family Pathway Handbooks; course/Gateway maps; orientation, safety, support, and concern materials; Portfolio, résumé, and interview guides; midpoint/completion communications | Eligible to proceed after Work Package 1, but ON HOLD. | On hold — do not begin | Kevin McCann decision, 2026-07-12: hold Work Package 5 while Work Packages 2A and 3 proceed. External WBL-specific student/family items (STU-13–21, FAM-05) will additionally be CONDITIONAL planning drafts once this package starts. | N/A — on hold
Work Package 6: Employer, Mentor, and External WBL System | G (EMP-01–22, consolidated to 15 files); H (OPS-04–14, OPS-19 consolidated into 1 workbook + 1 checklist) | 35 in scope (18 files produced) | WBL Coordinator | Partnership overview and interest form; training-station profile, screening, and decision notice set; partnership agreement; mentor handbook and orientation packet; individualized training plan and placement record; minor-employment guidance; midpoint/final employer evaluation; change request; concern and corrective-action record; incident report (structural, links to district process); placement suspension/termination record; partner closeout and renewal review; WBL Coordinator Operations Workbook (11 trackers in one workbook); legal/insurance/risk review checklist; WP6 Legal-Policy Dependency Log | Depended on the correction pass completing (Work Package 3 real course documents; Kitchen Management status corrections). Ran parallel to Work Package 2B Phase 2A. | Production complete — awaiting owner visual QA review | No training-station partnerships currently exist for this pathway (PA-14, GOV-10) — this entire package is CONDITIONAL on Board/NYSED authorization of the Senior WBL course. Every one of the 18 files carries the exact boxed conditional statement, independently verified (not just self-reported) across all 15 Word docs and 2 Excel workbooks — the agent's own report flagged and fixed a paraphrase gap on the Excel files before declaring done, and the lead editor re-confirmed the fix landed. 5 new legal-policy dependencies discovered and logged (LP-12 incident-reporting process, LP-13 working papers, LP-14 wage/payroll mechanics, LP-15 mandated-reporting authority off-site, LP-16 pre-agreement public disclosure) — none invented, all marked "Not yet verified" with a named responsible reviewer. | Passed independent lead-editor verification: all 18 files reopened and checked (paragraph/table/sheet counts), exact conditional statement confirmed present in every file, EMP-06 confirmed follows the SBE-05 district-counsel-placeholder pattern (no invented legal terms), source materials/ mtimes reconfirmed unchanged. Pending Kevin McCann visual review.
Work Package 7: Evaluation, Board, and Public Accountability | I (EVAL-01–15); J (BRD-01–13); H (OPS-03 — 1 item, see OPS Item Assignment tab) | 29 | Evaluation Lead / District Leadership | Gateway outcome tracker; training-station quality rubric; annual program evaluation template; student/family/employer/staff surveys; Board brief, deck, script, and resolution; fiscal note; launch-readiness memorandum; annual launch-readiness checklist | Uses Books Two and Four; do not publish unapproved claims or projected outcomes as actual results. | Not started | No Board resolution has been proposed or scheduled (PA-15, GOV-10) — BRD-01–04 cannot proceed to Board use until Kevin McCann sets a target date. | N/A — not yet produced
Work Package 8: Communications and Archive | L (COM-01–12); M (ARC-11 legacy sources); H (OPS-20 — 1 item, already produced under WP2A) | 13 | Communications | One-page flyer; presentation table/trifold; public information deck; social media calendar; SkillsUSA campaign; media standards; employer recruitment packet; orientation decks; recognition templates; news release template | Runs after the public architecture (Work Package 2) is stable. | Not started | SkillsUSA is recorded as "Exploratory / interest-development stage — active chapter status not confirmed" (PA-13, GOV-10) — use "SkillsUSA development initiative" language, never an active-chapter claim, when drafting COM-05. OPS-20 (Accessibility and Digital-Document Review Checklist) was already produced as an appendix inside WEB-20 under Work Package 2A — do not recreate it here. | N/A — not yet produced
Governance / Lead Editor: cross-program operations coordination (not a numbered work package) | H (OPS-01, 02, 15, 16, 17, 18, 21 — 7 items, see OPS Item Assignment tab) | 7 | Lead Editor / Program Administration | Annual roles and responsibility matrix; master operational calendar; records retention and archive schedule; privacy and access protocol; annual closeout and staff handoff checklist; emergency and escalation contact tree; program risk and mitigation register | Per Kevin McCann's 2026-07-12 correction (UD-04): OPS is a document category, not a work package. These 7 items span every work package's staff roles, calendars, records procedures, and Book Three controls, so the lead editor coordinates them as an ongoing governance responsibility rather than a 9th numbered work package. | Not started | None — this row exists only to show where the remaining OPS items live; it does not compete with Work Packages 1-8 for sequencing. | N/A — not yet produced
Total register items

## OPS Item Assignment
OPS Item Assignment — individual domain assignment per Kevin McCann's 2026-07-12 correction (UD-04): OPS is a document category, not a work package.
Register ID | Document / Asset | Assigned To | Rationale
OPS-01 | Annual Roles and Responsibility Matrix | Governance / Lead Editor | Cross-program staff roles — spans every work package, not owned by one.
OPS-02 | Master Operational Calendar | Governance / Lead Editor | Cross-program calendar integrating instruction, Gateways, Cottage, SkillsUSA, WBL, evaluation, and document review.
OPS-03 | Annual Launch-Readiness Checklist | Work Package 7 | Operational companion to BRD-12 Launch-Readiness Decision Memorandum — a Board/authorization decision-gate document.
OPS-04 | Student Roster and Prelaunch Tracker | Work Package 6 | External WBL / training-station operations.
OPS-05 | Partner and Training Station Database | Work Package 6 | External WBL / training-station operations.
OPS-06 | Student-to-Training-Station Matching Record | Work Package 6 | External WBL / training-station operations.
OPS-07 | Agreement and Training Plan Status Tracker | Work Package 6 | External WBL / training-station operations.
OPS-08 | Coordinator Communication Log | Work Package 6 | External WBL / training-station operations.
OPS-09 | Coordinator Site-Visit and Monitoring Record | Work Package 6 | External WBL / training-station operations.
OPS-10 | WBL Hour Reconciliation Record | Work Package 6 | External WBL / training-station operations.
OPS-11 | Portfolio Progress Tracker | Work Package 6 | Tracks the Senior WBL portfolio specifically (Book Three Ch.20) — External WBL operations.
OPS-12 | Incident and Corrective-Action Register | Work Package 6 | Training-station quality and incident pattern review tie to External WBL operations; cross-reference Work Package 7 for annual evaluation use.
OPS-13 | Placement Status and Change Tracker | Work Package 6 | External WBL / training-station operations.
OPS-14 | Transportation and Student-Support Coordination Record | Work Package 6 | Tied to off-site placement transportation — External WBL operations.
OPS-15 | Records Retention and Archive Schedule | Governance / Lead Editor | Cross-program records procedure (Book Three control).
OPS-16 | Privacy and Access Protocol | Governance / Lead Editor | Cross-program records procedure (Book Three control) — separates public/participant/restricted content district-wide.
OPS-17 | Annual Closeout and Staff Handoff Checklist | Governance / Lead Editor | Cross-program annual cycle, not specific to one work package.
OPS-18 | Emergency and Escalation Contact Tree | Governance / Lead Editor | Explicitly spans classroom, SBE, events, travel, and external WBL — cross-program by definition.
OPS-19 | Legal, Insurance, Working Papers, and Risk Review Checklist | Work Package 6 | Required specifically before External WBL authorization (cross-referenced in the Production Control Log's Legal-Policy Verification tab, LP-01–LP-06).
OPS-20 | Accessibility and Digital-Document Review Checklist | Work Package 8 (already produced under Work Package 2A) | Communications/publication operations — already delivered as an appendix inside WEB-20 Accessibility Statement; do not recreate.
OPS-21 | Program Risk and Mitigation Register | Governance / Lead Editor | Spans safety, staffing, capacity, transportation, equity, partner, financial, communication, and authorization risk — cross-program by nature; cross-reference Work Package 7 for Board-facing use.

## Website Audit
Current Website Audit vs. Target 13-Page Public Structure
Current Page | Target Structure Item | Register Action | Finding
index.html — "Greece Culinary Work-Based Learning" | 1. Home + 2. Pathway at a Glance | REVISE (WEB-02, WEB-03) | Structurally complete but branded around a generic WBL program. Must rebrand around the full three-year Culinary Pathway and add current status labeling (GOV-10).
pages/what-is-wbl.html | 5. Courses and Learning Environments (partial) | CREATE/REVISE (WEB-05) | Explains WBL generically. Needs to become Courses and Learning Environments covering Culinary 1/2, Advanced Culinary, Kitchen Management, The Cottage, SkillsUSA, and the proposed senior WBL course with accurate status labels.
pages/student-pathway.html | 3. Six Gateways and the Culinary Passport | REPLACE (WEB-04, ARC-02) | Uses a generic staged WBL journey model. Register explicitly prohibits a parallel progression system — must be replaced entirely with the Six Gateway Model and Culinary Passport.
pages/family-information.html | 8. Students and Families (partial) | REVISE (WEB-09, ARC-03) | Usable introductory language per prior gap analysis, but 5 of 11 FAQ answers defer to unresolved policy. Needs the full participation lifecycle and a link into the Family Resource Center.
pages/employer-partners.html | 9. Employer and Community Partners (partial) | REVISE (WEB-10, ARC-04) | Needs training-station lifecycle, mentor role, learning-before-labor framing, and a link into the Employer and Mentor Resource Center.
pages/school-based-enterprise.html | 5. The Cottage | REPLACE (WEB-06, ARC-05) | Currently a generic SBE explanation. Must be replaced with The Cottage, named and connected to Advanced Culinary, Kitchen Management, and Gateway 4.
pages/forms-resources.html | 12. Contact / Document Download Index (split) | REPLACE (WEB-22, ARC-07) | 53 undifferentiated resource cards, 46 still placeholder. Must be replaced with role-, status-, and access-aware navigation split across the Participant Resource Center and a public download index.
pages/evaluation-impact.html | 10. Results and Accountability | REVISE (WEB-12, ARC-06) | Framework-only, no real instruments or data (appropriate for current stage) but does not yet separate student competency, training-station quality, and program quality as three distinct evaluation objects.
pages/media-gallery.html | (supporting content, not a numbered target page) | n/a | Entirely placeholder tiles; every photo/video slot is empty. Gated on real events and signed consent, not on document production.
pages/contact.html | 11. Contact, Help, and Concerns | CREATE (WEB-13) | No named coordinator or working submission target yet. Needs separated routes for general inquiry, student/family support, employer interest, accessibility help, and urgent concerns.
(none) | 4. Leadership, Kitchen Management, and SkillsUSA | CREATE (WEB-07) | No current page exists — net-new.
(none) | 6. Credentials and Recognition | CREATE (WEB-11) | No current page exists — net-new.
(none) | 13. Frequently Asked Questions (standalone, expanded) | REVISE (WEB-23) | FAQ content currently lives inline on other pages; needs to become its own audience-organized page.
(none) | Participant Resource Center (landing + Student/Family/Employer/Staff) | CREATE (WEB-14–18) | No role-based, access-gated resource center currently exists — the site is entirely public-facing today.

## Files Produced
Files Produced Through This Pass — Work Packages 1, 2A, 2B (Phase 1 + 2A), 3, 4, and 6
Register ID | File | Format | Location | QC Notes
GOV-08 | pathway-documents/work-package-1-governance/GCSD_CulinaryPathway_GOV-08_Canonical-Glossary_v1.0_2026-07-12.docx | Word | pathway-documents/work-package-1-governance/ | Passed acceptance checklist — see Read Me sheet.
GOV-09 | pathway-documents/work-package-1-governance/GCSD_CulinaryPathway_GOV-09_Document-Control-Versioning-Procedure_v1.1_2026-07-14.docx | Word | pathway-documents/work-package-1-governance/ | v1.1 clarifies GOV-01–GOV-07 identities, the archive-filename suffix position, and access-versus-storage rules. Owner visual QA remains pending.
GOV-10 | pathway-documents/work-package-1-governance/GCSD_CulinaryPathway_GOV-10_Program-Status-Authorization-Register_v4.0_2026-07-12.xlsx | Excel | pathway-documents/work-package-1-governance/ | v4.0 — corrects PA-05 Kitchen Management to the exact required "Proposed planning document" status language (v3.0 corrected PA-02/03/04 course-title language). v1.0-v3.0 archived. Contains COUNTIF/COUNTA summary formulas — recalculates automatically on open in Excel; could not be force-recalculated in this environment (no LibreOffice installed).
GOV-11 | pathway-documents/work-package-1-governance/GCSD_CulinaryPathway_GOV-11_Annual-Document-Review-Calendar_v1.0_2026-07-12.xlsx | Excel | pathway-documents/work-package-1-governance/ | Passed acceptance checklist. Proposed rhythm — confirm against Book Three, Chapter 3 before adoption.
GOV-12 | pathway-documents/work-package-1-governance/GCSD_CulinaryPathway_GOV-12_Companion-Document-Map_v1.1_2026-07-12.docx | Word | pathway-documents/work-package-1-governance/ | Passed acceptance checklist.
GOV-13 | pathway-documents/work-package-1-governance/GCSD_CulinaryPathway_GOV-13_Website-Page-Template-Content-Standards_v1.0_2026-07-12.docx | Word | pathway-documents/work-package-1-governance/ | Relocated from provisional WEB-25 per Kevin McCann's UD-06 decision, 2026-07-12 — was in pathway-documents/work-package-2-website/, now here as a governance/publication-control document. Prior file archived.
WEB-01 | pathway-documents/work-package-2-website/GCSD_CulinaryPathway_WEB-01_Website-Content-Map-Migration-Spec_v1.0_2026-07-12.docx | Word | pathway-documents/work-package-2-website/ | Updated 2026-07-12 to reference GOV-13 instead of provisional WEB-25 (Section 8 and the deliverable table).
WEB-19 | pathway-documents/work-package-2-website/GCSD_CulinaryPathway_WEB-19_Status-Label-System_v1.0_2026-07-12.docx | Word | pathway-documents/work-package-2-website/ | Points to GOV-10 as sole status source — does not invent new categories.
WEB-22 | pathway-documents/work-package-2-website/GCSD_CulinaryPathway_WEB-22_Document-Download-Index_v1.0_2026-07-12.docx | Word | pathway-documents/work-package-2-website/ | Structure only, as instructed — no content rows yet.
WEB-24 | pathway-documents/work-package-2-website/GCSD_CulinaryPathway_WEB-24_Content-Ownership-Update-Schedule_v1.0_2026-07-12.xlsx | Excel | pathway-documents/work-package-2-website/ | 29-row tracker covering live pages, WP2A deliverables, and WP2B targets.
WEB-02 | pathway-documents/work-package-2-website/staging-pages/GCSD_CulinaryPathway_WEB-02_Home-Page_v1.0_2026-07-12.html | HTML (staged) | pathway-documents/work-package-2-website/staging-pages/ | Verified no premature Gateway/credential claims. Not linked from live nav.
WEB-13 | pathway-documents/work-package-2-website/staging-pages/GCSD_CulinaryPathway_WEB-13_Contact-Help-Concerns_v1.0_2026-07-12.html | HTML (staged) | pathway-documents/work-package-2-website/staging-pages/ | Contact points use labeled placeholders, not the live site's real-looking address.
WEB-21 | pathway-documents/work-package-2-website/staging-pages/GCSD_CulinaryPathway_WEB-21_Privacy-Records-Notice_v1.0_2026-07-12.html | HTML (staged) | pathway-documents/work-package-2-website/staging-pages/ | Passed acceptance checklist.
WEB-20 | pathway-documents/work-package-2-website/staging-pages/GCSD_CulinaryPathway_WEB-20_Accessibility-Statement_v1.0_2026-07-12.html | HTML (staged) | pathway-documents/work-package-2-website/staging-pages/ | Includes OPS-20 checklist as an in-page appendix per the reconciliation memo's CONSOLIDATE decision.
— | pathway-documents/work-package-2-website/staging-pages/assets/status-labels.css | CSS | pathway-documents/work-package-2-website/staging-pages/assets/ | Additive-only stylesheet layered on the existing assets/css/styles.css — live CSS confirmed unmodified.
— | pathway-documents/work-package-3-curriculum-passport-gateways/GCSD_CulinaryPathway_WP3-File-Manifest_v2.0_2026-07-12.xlsx | Excel | pathway-documents/work-package-3-curriculum-passport-gateways/ | v2.0 supersedes v1.0 (archived). Confirms CUR-01/CUR-02 now exist as real, versioned course documents — independently re-verified by the lead editor, not just self-reported.
CUR-01 | pathway-documents/work-package-3-curriculum-passport-gateways/GCSD_CulinaryPathway_CUR-01_Culinary-1-2-Revised-Course-Document_v1.0_2026-07-12.docx | Word | pathway-documents/work-package-3-curriculum-passport-gateways/ | NEW, 2026-07-12: the actual revised course document (305 substantive paragraphs, 5 tables) — 35-week, 9-unit content reorganized from the real source outline with Gateway 1-3 alignment. Verified NOT memo-shaped. Flags a genuine, unresolved Skills Map week-split conflict (UD-10) rather than silently resolving it. Source materials/CA 1 & 2 outline 8_8_25.docx confirmed untouched (mtime unchanged).
CUR-02 | pathway-documents/work-package-3-curriculum-passport-gateways/GCSD_CulinaryPathway_CUR-02_Advanced-Culinary-Revised-Course-Document_v1.0_2026-07-12.docx | Word | pathway-documents/work-package-3-curriculum-passport-gateways/ | NEW, 2026-07-12: the actual revised course document (172 substantive paragraphs, 9 tables) — 7-unit content with Gateway 4/Cottage alignment. Source materials/Advanced Culinary - Scope and Sequence 2023-2024.docx confirmed untouched.
CUR-01-02 | pathway-documents/work-package-3-curriculum-passport-gateways/GCSD_CulinaryPathway_CUR-01-02_Course-Alignment-Memo_v1.0_2026-07-12.docx | Word | pathway-documents/work-package-3-curriculum-passport-gateways/ | Retained as the analysis record that informed CUR-01/CUR-02 above — no longer the operative course document.
CUR-05 | pathway-documents/work-package-3-curriculum-passport-gateways/GCSD_CulinaryPathway_CUR-05_Culinary-Pathway-Skills-Map_v1.2_2026-07-12.xlsx | Excel | pathway-documents/work-package-3-curriculum-passport-gateways/ | v1.2, 2026-07-12: Kitchen Management status language corrected (~95 cells) to reflect CUR-03's actual proposed status (v1.1 reclassified "Strategies for Success" per UD-07). v1.0/v1.1 archived.
CUR-06 | pathway-documents/work-package-3-curriculum-passport-gateways/GCSD_CulinaryPathway_CUR-06_Course-Gateway-Evidence-Crosswalk_v1.1_2026-07-12.xlsx | Excel | pathway-documents/work-package-3-curriculum-passport-gateways/ | v1.1: Kitchen Management status language corrected (6 cells). v1.0 archived.
CUR-07 | pathway-documents/work-package-3-curriculum-passport-gateways/GCSD_CulinaryPathway_CUR-07_Credential-Recognition-Crosswalk_v1.0_2026-07-12.xlsx | Excel | pathway-documents/work-package-3-curriculum-passport-gateways/ | Passed acceptance checklist.
CUR-08 | pathway-documents/work-package-3-curriculum-passport-gateways/GCSD_CulinaryPathway_CUR-08_Assessment-Evidence-Inventory_v1.1_2026-07-12.xlsx | Excel | pathway-documents/work-package-3-curriculum-passport-gateways/ | v1.1: Read Me note corrected re: Kitchen Management/CUR-03 status. v1.0 archived.
CMP-01 | pathway-documents/work-package-3-curriculum-passport-gateways/GCSD_CulinaryPathway_CMP-01_Employability-Profile_v1.0_2026-07-12.docx | Word | pathway-documents/work-package-3-curriculum-passport-gateways/ | REVISED COPY, separately named — source Employability Profile- Culinary Pathway-Template.docx confirmed untouched (mtime predates session; original typo and placeholder text still present in source). Verified original tables/checkboxes/grading scales preserved. Checked for a stale course-alignment-memo reference during WP3 completion — none found, no edit needed.
CMP-02 | pathway-documents/work-package-3-curriculum-passport-gateways/GCSD_CulinaryPathway_CMP-02_Culinary-Passport_v1.0_2026-07-12.xlsx | Excel | pathway-documents/work-package-3-curriculum-passport-gateways/ | Blank record template with one example row each — not a filled student record. Gateway 4/5/6 evidence from Work Packages 4 and 6 routes into this file's Evidence Log, no competing record created.
CMP-03–07 | pathway-documents/work-package-3-curriculum-passport-gateways/GCSD_CulinaryPathway_CMP-03-07_Gateway-1-5-Standards-Rubrics_v1.1_2026-07-12.docx | Word | pathway-documents/work-package-3-curriculum-passport-gateways/ | v1.1: stale note claiming CUR-03 doesn't exist corrected to distinguish "CUR-03 exists as a proposed planning document" from "district-authorized/active status remains unconfirmed." v1.0 archived. Note: this edit was made directly in place before the file was renamed/archived — a minor process gap flagged transparently (this is the project's own output, not an immutable source, so the impact is low, but the archive-before-edit sequence should have been followed).
CMP-08 | pathway-documents/work-package-3-curriculum-passport-gateways/GCSD_CulinaryPathway_CMP-08_Gateway-6-Standard-Rubric_v1.0_2026-07-12.docx | Word | pathway-documents/work-package-3-curriculum-passport-gateways/ | Verified: boxed "CONDITIONAL PLANNING DRAFT / Not adopted district policy / Not authorized for implementation" statement present near the top and in an appendix table.
CMP-14 | pathway-documents/work-package-3-curriculum-passport-gateways/GCSD_CulinaryPathway_CMP-14_Evidence-Naming-Storage-Guide_v1.0_2026-07-12.docx | Word | pathway-documents/work-package-3-curriculum-passport-gateways/ | Cross-references GOV-09 rather than restating it, per the reconciliation memo.
WEB-02 | pathway-documents/work-package-2-website/staging-pages/GCSD_CulinaryPathway_WEB-02_Home-Page_v1.0_2026-07-12.html | HTML (staged) | pathway-documents/work-package-2-website/staging-pages/ | Nav/footer unified across all 15 staged pages (see cross-package correction row above).
WEB-03 | pathway-documents/work-package-2-website/staging-pages/GCSD_CulinaryPathway_WEB-03_Pathway-at-a-Glance_v1.0_2026-07-12.html | HTML (staged) | pathway-documents/work-package-2-website/staging-pages/ | Internal Review status. Summary-level three-year sequence. Nav unified.
WEB-04 | pathway-documents/work-package-2-website/staging-pages/GCSD_CulinaryPathway_WEB-04_Six-Gateways-Culinary-Passport_v1.0_2026-07-12.html | HTML (staged) | pathway-documents/work-package-2-website/staging-pages/ | Internal Review status. Verified: exact boxed conditional-draft statement present on Gateway 6; explicitly states individual Passport records are private/restricted. Nav unified.
WEB-05 | pathway-documents/work-package-2-website/staging-pages/GCSD_CulinaryPathway_WEB-05_Courses-Learning-Environments_v1.0_2026-07-12.html | HTML (staged) | pathway-documents/work-package-2-website/staging-pages/ | Updated twice: (1) corrected stale "scope and sequence has not yet been written" claim now that CUR-03 exists, with exact Kitchen Management proposed-status language; (2) surgically edited to link the Cottage/KM brief mentions to the new WEB-06/07 pages. Nav unified.
WEB-06 | pathway-documents/work-package-2-website/staging-pages/GCSD_CulinaryPathway_WEB-06_The-Cottage_v1.0_2026-07-12.html | HTML (staged) | pathway-documents/work-package-2-website/staging-pages/ | NEW, 2026-07-12: full detail page. Verified no restricted Work Package 4 document named or linked in visible content (scanned outside HTML comments).
WEB-07 | pathway-documents/work-package-2-website/staging-pages/GCSD_CulinaryPathway_WEB-07_Leadership-Kitchen-Management_v1.0_2026-07-12.html | HTML (staged) | pathway-documents/work-package-2-website/staging-pages/ | NEW, 2026-07-12: full detail page. Proposed status stated at every section heading, not just once — verified.
WEB-08 | pathway-documents/work-package-2-website/staging-pages/GCSD_CulinaryPathway_WEB-08_External-Work-Based-Learning_v1.0_2026-07-12.html | HTML (staged) | pathway-documents/work-package-2-website/staging-pages/ | CURRENT, 2026-07-12: conditional public-safe External Work-Based Learning page replacing the archived structure draft. Preserves GOV-10 PA-06 conditional planning draft / not-authorized status; does not authorize implementation.
WEB-10 | pathway-documents/work-package-2-website/staging-pages/GCSD_CulinaryPathway_WEB-10_Employer-Community-Partners_v1.0_2026-07-12.html | HTML (staged) | pathway-documents/work-package-2-website/staging-pages/ | CURRENT, 2026-07-12: conditional public-safe Employer and Community Partners page replacing the archived structure draft. Preserves GOV-10 PA-14 no-partnerships-established status and PA-06 dependency; does not authorize implementation.
WEB-09 | pathway-documents/work-package-2-website/staging-pages/GCSD_CulinaryPathway_WEB-09_Students-Families_v1.0_2026-07-12.html | HTML (staged) | pathway-documents/work-package-2-website/staging-pages/ | Internal Review status. General discovery overview. Nav unified.
WEB-11 | pathway-documents/work-package-2-website/staging-pages/GCSD_CulinaryPathway_WEB-11_Credentials-Recognition_v1.0_2026-07-12.html | HTML (staged) | pathway-documents/work-package-2-website/staging-pages/ | Internal Review status. Only ServSafe carries a status badge (GOV-10 PA-10). Nav unified.
WEB-12 | pathway-documents/work-package-2-website/staging-pages/GCSD_CulinaryPathway_WEB-12_Results-Accountability_v1.0_2026-07-12.html | HTML (staged) | pathway-documents/work-package-2-website/staging-pages/ | Internal Review status. States plainly that no real outcome data exists yet. Nav unified.
WEB-13 | pathway-documents/work-package-2-website/staging-pages/GCSD_CulinaryPathway_WEB-13_Contact-Help-Concerns_v1.0_2026-07-12.html | HTML (staged) | pathway-documents/work-package-2-website/staging-pages/ | Nav/footer unified.
WEB-20 | pathway-documents/work-package-2-website/staging-pages/GCSD_CulinaryPathway_WEB-20_Accessibility-Statement_v1.0_2026-07-12.html | HTML (staged) | pathway-documents/work-package-2-website/staging-pages/ | Moved to footer-only utility link in the unified nav pass (not in the primary 13-item nav).
WEB-21 | pathway-documents/work-package-2-website/staging-pages/GCSD_CulinaryPathway_WEB-21_Privacy-Records-Notice_v1.0_2026-07-12.html | HTML (staged) | pathway-documents/work-package-2-website/staging-pages/ | Moved to footer-only utility link, same treatment as WEB-20.
WEB-23 | pathway-documents/work-package-2-website/staging-pages/GCSD_CulinaryPathway_WEB-23_FAQ-Partial_v1.0_2026-07-12.html | HTML (staged) | pathway-documents/work-package-2-website/staging-pages/ | Internal Review status. Partial — only Gateways/Passport, Courses, and Credentials sections. Nav unified.
SBE-02,04,08,09,10,12,13,17 | pathway-documents/work-package-4-cottage-kitchen-management/GCSD_CulinaryPathway_SBE-02-04-08-09-10-12-13-17_Cottage-Operations-Instructional-Guide_v1.0_2026-07-12.docx | Word | pathway-documents/work-package-4-cottage-kitchen-management/ | Master reference manual, 8 Register items consolidated into sections/appendices. Includes Gateway 4 → CMP-02 Passport cross-reference.
SBE-03,06,07,11 | pathway-documents/work-package-4-cottage-kitchen-management/GCSD_CulinaryPathway_SBE-03-06-07-11_Event-Planning-Packet_v1.0_2026-07-12.docx | Word | pathway-documents/work-package-4-cottage-kitchen-management/ | Fillable 4-part planning packet, completed together during the planning phase.
SBE-05 | pathway-documents/work-package-4-cottage-kitchen-management/GCSD_CulinaryPathway_SBE-05_Client-Agreement_v1.1_2026-07-12.docx | Word | pathway-documents/work-package-4-cottage-kitchen-management/ | v1.1: strengthened to state explicitly "Restricted/internal, not authorized for distribution, not linked publicly, not an approved district contract" per Kevin McCann's correction. Logged as new Legal-Policy item LP-11. v1.0 archived.
SBE-15,16,17 | pathway-documents/work-package-4-cottage-kitchen-management/GCSD_CulinaryPathway_SBE-15-16-17_Event-Closeout-Financial-Reconciliation-Record_v1.0_2026-07-12.docx | Word | pathway-documents/work-package-4-cottage-kitchen-management/ | Financial/inventory reconciliation, closeout review, and student reflection combined — staff-facing, RESTRICTED.
SBE-14 | pathway-documents/work-package-4-cottage-kitchen-management/GCSD_CulinaryPathway_SBE-14_Client-Feedback-Form_v1.0_2026-07-12.docx | Word | pathway-documents/work-package-4-cottage-kitchen-management/ | Kept separate (external client-facing).
SBE-19 | pathway-documents/work-package-4-cottage-kitchen-management/GCSD_CulinaryPathway_SBE-19_Cottage-Event-Register_v1.0_2026-07-12.xlsx | Excel | pathway-documents/work-package-4-cottage-kitchen-management/ | RESTRICTED annual log, 3 tabs including a live-formula Annual Summary. Example rows clearly marked, to be deleted at first real use.
CUR-03 | pathway-documents/work-package-4-cottage-kitchen-management/GCSD_CulinaryPathway_CUR-03_Kitchen-Management-Scope-Sequence_v1.1_2026-07-12.docx | Word | pathway-documents/work-package-4-cottage-kitchen-management/ | v1.1: prominent "PROPOSED PLANNING DOCUMENT" status notice added per Kevin McCann's correction — producing this document does not establish active district course status. v1.0 archived.
KM-02,03,04,05 | pathway-documents/work-package-4-cottage-kitchen-management/GCSD_CulinaryPathway_KM-02-03-04-05_Kitchen-Management-Student-Leadership-Handbook_v1.1_2026-07-12.docx | Word | pathway-documents/work-package-4-cottage-kitchen-management/ | v1.1: same proposed-status notice added. v1.0 archived.
KM-06,08 | pathway-documents/work-package-4-cottage-kitchen-management/GCSD_CulinaryPathway_KM-06-08_Kitchen-Management-Event-Leadership-Packet_v1.1_2026-07-12.docx | Word | pathway-documents/work-package-4-cottage-kitchen-management/ | v1.1: same proposed-status notice added. v1.0 archived.
KM-07 | pathway-documents/work-package-4-cottage-kitchen-management/GCSD_CulinaryPathway_KM-07_Kitchen-Management-Leadership-Observation-Rubric_v1.1_2026-07-12.docx | Word | pathway-documents/work-package-4-cottage-kitchen-management/ | v1.1: same proposed-status notice added. v1.0 archived.
KM-10 | pathway-documents/work-package-4-cottage-kitchen-management/GCSD_CulinaryPathway_KM-10_Career-Readiness-Completion-Checklist_v1.1_2026-07-12.docx | Word | pathway-documents/work-package-4-cottage-kitchen-management/ | v1.1: same proposed-status notice added. v1.0 archived.
EMP-01 | pathway-documents/work-package-6-employer-mentor-wbl/GCSD_CulinaryPathway_EMP-01_Employer-Community-Partnership-Overview_v1.0_2026-07-12.docx | Word | pathway-documents/work-package-6-employer-mentor-wbl/ | Feeds the future public WEB-10 page (Work Package 2B Phase 2B, not yet commissioned). Educator/mentor authority division stated explicitly.
EMP-02 | pathway-documents/work-package-6-employer-mentor-wbl/GCSD_CulinaryPathway_EMP-02_Partner-Interest-Form_v1.0_2026-07-12.docx | Word | pathway-documents/work-package-6-employer-mentor-wbl/ | States clearly that submission is not approval or a placement guarantee.
EMP-03 | pathway-documents/work-package-6-employer-mentor-wbl/GCSD_CulinaryPathway_EMP-03_Training-Station-Profile_v1.0_2026-07-12.docx | Word | pathway-documents/work-package-6-employer-mentor-wbl/ | Passed acceptance checklist.
EMP-04 | pathway-documents/work-package-6-employer-mentor-wbl/GCSD_CulinaryPathway_EMP-04_Training-Station-Screening-Site-Review-Checklist_v1.0_2026-07-12.docx | Word | pathway-documents/work-package-6-employer-mentor-wbl/ | Passed acceptance checklist.
EMP-05 | pathway-documents/work-package-6-employer-mentor-wbl/GCSD_CulinaryPathway_EMP-05_Training-Station-Decision-Notice-Set_v1.0_2026-07-12.docx | Word | pathway-documents/work-package-6-employer-mentor-wbl/ | One document, six notice templates (approval/conditional/denial/suspension/renewal/discontinuation) — consolidated.
EMP-06 | pathway-documents/work-package-6-employer-mentor-wbl/GCSD_CulinaryPathway_EMP-06_Employer-Partnership-Agreement_v1.0_2026-07-12.docx | Word | pathway-documents/work-package-6-employer-mentor-wbl/ | RESTRICTED. Follows the SBE-05 pattern: compliance section explicitly PENDING DISTRICT COUNSEL REVIEW, no invented legal terms — independently verified.
EMP-07,08,09 | pathway-documents/work-package-6-employer-mentor-wbl/GCSD_CulinaryPathway_EMP-07-08-09_Mentor-Handbook-Orientation-Packet_v1.0_2026-07-12.docx | Word | pathway-documents/work-package-6-employer-mentor-wbl/ | Handbook + orientation presentation outline + acknowledgment form, consolidated. Educator/mentor authority division stated explicitly.
EMP-10,11,13 | pathway-documents/work-package-6-employer-mentor-wbl/GCSD_CulinaryPathway_EMP-10-11-13_Individualized-Training-Plan-Placement-Record_v1.0_2026-07-12.docx | Word | pathway-documents/work-package-6-employer-mentor-wbl/ | Training Plan + Approved Duties/Equipment + Emergency Contact Sheet, consolidated as one per-student placement record.
EMP-12 | pathway-documents/work-package-6-employer-mentor-wbl/GCSD_CulinaryPathway_EMP-12_Minor-Employment-Scheduling-Guidance_v1.0_2026-07-12.docx | Word | pathway-documents/work-package-6-employer-mentor-wbl/ | No legal thresholds invented — cross-references LP-01 as the tracked dependency.
EMP-15,16 | pathway-documents/work-package-6-employer-mentor-wbl/GCSD_CulinaryPathway_EMP-15-16_Midpoint-Final-Employer-Evaluation_v1.0_2026-07-12.docx | Word | pathway-documents/work-package-6-employer-mentor-wbl/ | Two sections in one document, aligned to the Training Plan and Gateway 6 evidence.
EMP-18 | pathway-documents/work-package-6-employer-mentor-wbl/GCSD_CulinaryPathway_EMP-18_Schedule-Duty-Mentor-Location-Change-Request_v1.0_2026-07-12.docx | Word | pathway-documents/work-package-6-employer-mentor-wbl/ | Passed acceptance checklist.
EMP-19 | pathway-documents/work-package-6-employer-mentor-wbl/GCSD_CulinaryPathway_EMP-19_Concern-Corrective-Action-Record_v1.0_2026-07-12.docx | Word | pathway-documents/work-package-6-employer-mentor-wbl/ | Passed acceptance checklist.
EMP-20 | pathway-documents/work-package-6-employer-mentor-wbl/GCSD_CulinaryPathway_EMP-20_Incident-Report_v1.0_2026-07-12.docx | Word | pathway-documents/work-package-6-employer-mentor-wbl/ | Structural template only — does not invent a district incident-reporting process; logged as new LP-12.
EMP-21 | pathway-documents/work-package-6-employer-mentor-wbl/GCSD_CulinaryPathway_EMP-21_Placement-Change-Suspension-Early-Termination-Record_v1.0_2026-07-12.docx | Word | pathway-documents/work-package-6-employer-mentor-wbl/ | Passed acceptance checklist.
EMP-22 | pathway-documents/work-package-6-employer-mentor-wbl/GCSD_CulinaryPathway_EMP-22_Partner-Closeout-Renewal-Review_v1.0_2026-07-12.docx | Word | pathway-documents/work-package-6-employer-mentor-wbl/ | Passed acceptance checklist.
OPS-19 | pathway-documents/work-package-6-employer-mentor-wbl/GCSD_CulinaryPathway_OPS-19_Legal-Insurance-Working-Papers-Risk-Review-Checklist_v1.0_2026-07-12.docx | Word | pathway-documents/work-package-6-employer-mentor-wbl/ | Kept separate from the Coordinator Operations Workbook — a pre-authorization gate document for district leadership, not a day-to-day tracker.
OPS-04–14 | pathway-documents/work-package-6-employer-mentor-wbl/GCSD_CulinaryPathway_OPS-04-05-06-07-08-09-10-11-12-13-14_WBL-Coordinator-Operations-Workbook_v1.0_2026-07-12.xlsx | Excel | pathway-documents/work-package-6-employer-mentor-wbl/ | 11 tracker tabs consolidated into one workbook, each a blank template with one EXAMPLE row. Conditional statement initially present only as a paraphrase — corrected by the agent and re-verified by the lead editor before acceptance.
— | pathway-documents/work-package-6-employer-mentor-wbl/GCSD_CulinaryPathway_WP6-Legal-Policy-Dependency-Log_v1.0_2026-07-12.xlsx | Excel | pathway-documents/work-package-6-employer-mentor-wbl/ | 6 items cross-referenced from the existing Production Control Log (LP-01–LP-06) plus 5 new items (LP-12–LP-16) — all marked "Not yet verified" with a named responsible reviewer, none invented.
GOV-01 | pathway-documents/work-package-1-governance/GCSD_Culinary_Pathway_Canon_v3.0.docx | Word | pathway-documents/work-package-1-governance/ | Canon v3.0; administratively relocated under durable repository control without content or version change. SHA-256 preservation verified; owner visual QA remains pending.
GOV-02 | pathway-documents/work-package-1-governance/GCSD_Culinary_Pathway_Operating_Principles_v1.0.docx | Word | pathway-documents/work-package-1-governance/ | Operating Principles v1.0; administratively relocated under durable repository control without content or version change. SHA-256 preservation verified; owner visual QA remains pending.
GOV-03 | pathway-documents/work-package-1-governance/GCSD_Culinary_Pathway_Book_1_Program_Blueprint_V4.0_Refined.docx | Word | pathway-documents/work-package-1-governance/ | Book One v4.0; administratively relocated under durable repository control without content or version change. SHA-256 preservation verified; owner visual QA remains pending.
GOV-04 | pathway-documents/work-package-1-governance/GCSD_Culinary_Pathway_Book_2_Assessment_Evaluation_Continuous_Improvement_V4.1_Refined.docx | Word | pathway-documents/work-package-1-governance/ | Book Two v4.1; administratively relocated under durable repository control without content or version change. SHA-256 preservation verified; owner visual QA remains pending.
GOV-05 | pathway-documents/work-package-1-governance/GCSD_Culinary_Pathway_Book_3_Operations_Manual_V4.0_Refined.docx | Word | pathway-documents/work-package-1-governance/ | Book Three v4.0; administratively relocated under durable repository control without content or version change. SHA-256 preservation verified; owner visual QA remains pending.
GOV-06 | pathway-documents/work-package-1-governance/GCSD_Culinary_Pathway_Book_4_Board_Proposal_Implementation_Plan_V4.0_Refined.docx | Word | pathway-documents/work-package-1-governance/ | Book Four v4.0; administratively relocated under durable repository control without content or version change. SHA-256 preservation verified; owner visual QA remains pending.
GOV-07 | pathway-documents/work-package-1-governance/GCSD_Culinary_Pathway_Master_Document_Register_v1.0.docx | Word | pathway-documents/work-package-1-governance/ | Master Document Register v1.0; administratively relocated under durable repository control without content or version change. SHA-256 preservation verified; owner visual QA remains pending.