GCSD Culinary Pathway | Production Control Memo

Work Package 2A / Work Package 3 Production Reconciliation Memo

The consolidation test applied, the resulting deliverable lists, and the shared terminology contract both leads work from.

| Document ID | GOV-13 (working, not in original Register — production-control memo) |
| --- | --- |
| Title | Work Package 2A / Work Package 3 Production Reconciliation Memo |
| Audience | Web Lead (WP2A); Pathway Team / Culinary Teachers (WP3); Lead Editor |
| Purpose | Apply Kevin McCann's consolidation test to the Register's WP2 and WP3 deliverable lists, fix the final CREATE/CONSOLIDATE/DEFER decisions, and set the shared terminology contract before either package starts producing content. |
| Owner | Lead Editor |
| Version | 1.0 |
| Date | July 2026 |
| Approval / Planning Status | Planning document; not adopted district policy |
| Access Classification | RESTRICTED — production control document |
| Governing Source | Master Document Register v1.0; Kevin McCann's 2026-07-12 sequencing and consolidation instructions |
| Review Date | Superseded once Work Packages 2A and 3 are reconciled and closed |
| Superseded Document | None — first issue |

Provide clear direction. Inspect what you expect. Prepare students. Verify competence. Increase responsibility.

# 1. The Consolidation Test

Applied to every candidate document before it is produced, per Kevin McCann's instruction:

- Does an existing authoritative record already perform this function?

- Can this requirement be incorporated into an existing handbook, form, Passport record, Employability Profile, training plan, or operational packet?

- Does the proposed document cause the user to take a distinct action or preserve a distinct authoritative record?

- Would combining it with another document reduce confusion without weakening record control?

The goal is a complete documentation system, not the maximum number of documents. Where two Register items serve the same audience, the same moment of use, and don't need independently controlled version/approval status, they are combined below. Where an item carries different approval status than its neighbors (most importantly, anything CONDITIONAL on Senior WBL authorization), it stays a separate file even if that means more files — mixed status inside one document is not acceptable.

# 2. Work Package 2A — Final Deliverable List

Scope: everything Kevin authorized for immediate production. Explicitly excludes final page copy for any page whose content depends on Work Package 3's Gateway, Passport, credential, or assessment language — that is Work Package 2B.

| Deliverable | Register Item(s) | Decision | Rationale |
| --- | --- | --- | --- |
| Website Content Map and Migration Specification | WEB-01 + redirect/archive plan + ARC-01–08 decisions + access classification per page | CONSOLIDATE | Register's own WEB-01 description already includes redirect/archive action as a column. Folding the access map and archive plan in avoids a second document that would need to stay in sync with the first. |
| Public / Participant / Restricted Page Template Set | New — supports WEB-02 through WEB-24 authoring | CREATE | A distinct working tool used repeatedly during page authoring, not a planning document — different audience and use from the Migration Spec. |
| Home page (status-safe refresh) | WEB-02 (partial) | CREATE (partial) | Value proposition, current-status framing, and audience navigation can be finalized now. Any specific Gateway/credential claim is held for Work Package 2B. |
| Contact, Help, and Concerns page | WEB-13 | CREATE (full) | Does not depend on Work Package 3 terminology. |
| Privacy and Records Notice | WEB-21 | CREATE (full) | Does not depend on Work Package 3 terminology. |
| Accessibility Statement (with OPS-20 checklist as an appendix) | WEB-20 + OPS-20 | CONSOLIDATE | Same audience and same moment of use — a separate checklist would just be an appendix no one opens on its own. |
| Content Ownership and Update Schedule | WEB-24 | CREATE | Distinct restricted tracker with its own owner/reviewer/cadence fields — not foldable into the Migration Spec, which is a one-time planning document, not a running schedule. |
| Status-Label System (display rules only) | WEB-19 | CREATE (thin) | Must not re-invent status categories — this is a display-rules document that points to GOV-10 as the source of truth, not a parallel authorization register. |
| Document Download Index — structure only | WEB-22 (structure) | CREATE (structure only) | Full content awaits documents that don't exist yet across other work packages; only the navigational schema (role, status, version, audience, access columns) is produced now. |

Not produced in this pass, and not to be produced until Work Package 3 sets the terms: WEB-03 (Pathway at a Glance), WEB-04 (Six Gateways and Passport), WEB-05 (Courses and Learning Environments), WEB-06 (The Cottage — needs Gateway 4 language), WEB-07 (Kitchen Management/SkillsUSA — needs Gateway 5 and the SkillsUSA exploratory-language decision applied consistently), WEB-08 (External WBL), WEB-09/10 (Students and Families / Employer Partners full versions), WEB-11 (Credentials and Recognition), WEB-12 (Results and Accountability), WEB-14 through WEB-18 (Resource Center pages), WEB-23 (FAQ). These are Work Package 2B.

Files are produced as working HTML in a staging location, not inside the live pages/ directory and not linked from the live navigation — nothing is deployed or published.

# 3. Work Package 3 — Final Deliverable List

| Deliverable | Register Item(s) | Decision | Rationale |
| --- | --- | --- | --- |
| Course Alignment Memo: Culinary 1, Culinary 2, and Advanced Culinary | CUR-01, CUR-02 | CONSOLIDATE | Same owner (Culinary Teachers), same revision logic (align terminology, Gateways, evidence), reviewed together — one memo instead of two or three avoids drift between them. |
| Kitchen Management Scope and Sequence | CUR-03 | DEFER to Work Package 4 | Register groups Kitchen Management's instructional and operational content together under Work Package 4. Gateway 5's rubric (below) is produced now since Kevin's list calls for Gateway standards; the full course document waits so it isn't written twice against two different operational pictures. |
| Culinary Pathway Skills Map — reconciled and revised | CUR-05 | CONSOLIDATE (first) then REVISE | Three duplicate spreadsheet versions exist in source materials (Culinary_Pathway_Skills_Map.xlsx and two numbered copies). These are reconciled into one authoritative file before revision, per the Register's own instruction not to leave duplicative or fragmented materials in place. |
| Course-to-Gateway Evidence Crosswalk | CUR-06 | CREATE | Different audience and purpose than the Skills Map (evaluators locating evidence, not teachers planning instruction) — Register keeps these as two distinct documents and this memo agrees. |
| Credential and Recognition Crosswalk | CUR-07 | CREATE | No existing authoritative record distinguishes ServSafe, YouScience, ProStart, CDOS, and postsecondary credit — net new. |
| Assessment and Evidence Inventory | CUR-08 | CREATE | Inventories what already exists before any new assessment is authored — a control document, not optional. |
| GCSD Culinary Employability Profile — revised | CMP-01 | REVISE | An authoritative template already exists in source materials and is edited directly rather than replaced. |
| Culinary Passport (record template, with Gateway Verification, Reassessment, and Reverification as linked sections, not separate documents) | CMP-02, CMP-09, CMP-10, CMP-11 | CONSOLIDATE | Register explicitly instructs CMP-09 to be "linked to the Passport rather than duplicating it." The same logic applies to reassessment and reverification — a student's competency record, its verification signoffs, and its reassessment/reverification history are one record, not four. |
| Gateway 1–5 Performance Standards and Rubrics (one document, five sections) | CMP-03, CMP-04, CMP-05, CMP-06, CMP-07 | CONSOLIDATE | Same approval status, same audience (teachers), reviewed as a set. Combining avoids five near-identical cover pages and keeps the progression visibly sequential. |
| Gateway 6 Performance Standard and Rubric — CONDITIONAL PLANNING DRAFT | CMP-08 | CREATE (separate file, mandatory) | Must stay a separate file specifically because its approval status differs from Gateways 1–5 (Conditional Planning Draft vs. Approved for Planning Use). Mixing statuses inside one document is not acceptable per GOV-09. |
| Evidence Naming and Storage Guide | CMP-14 | CREATE (short) | Governs student evidence files, a different object than the program documents GOV-09 already covers — kept separate but cross-referenced to GOV-09 rather than restating its rules. |

# 4. Shared Terminology Contract

Both leads use the Canonical Glossary (GOV-08) as the sole source of definitions. The following points are called out because they are the terms most likely to drift between a website description and an instructional document if not fixed here:

- Gateways are always “Gateway 1” through “Gateway 6,” never renumbered, renamed, or combined — WP2A's page templates and WP3's rubrics must use identical Gateway names and competency lists.

- “The Cottage” is always named as such and never described as only a catering business, on the website or in any Gateway 4 evidence document.

- “Kitchen Management” is always framed as leadership development, never as additional cooking instruction, in both the (deferred) website page and the Gateway 5 rubric.

- “Travel Rights” is the student-facing term for Gateway 5 completion / External WBL Educational Readiness — WP3's Gateway 5 rubric and WP2B's future Kitchen Management page must use it identically.

- Senior External WBL materials, wherever they appear (website or curriculum), carry the exact status line: “Conditional planning draft. Not adopted district policy. Not authorized for implementation.”

- SkillsUSA is referred to as the “SkillsUSA development initiative,” exploratory/interest-development stage, active chapter status not confirmed — never as an active chapter, in any document from either package.

Neither lead may coin a working definition for a term the Canon doesn't already define. If a genuine gap is found (a concept neither package's source material covers), it is raised to the lead editor as an architectural question for Kevin McCann, not resolved locally.

# 5. Conventions Both Packages Follow

- File naming and versioning per GOV-09: GCSD_CulinaryPathway_[Register-ID]_[Short-Title]_v[Major.Minor]_[YYYY-MM-DD].[ext].

- Every document opens with the standard metadata block (title, audience, purpose, owner, version, date, approval/planning status, access classification, storage location, review date, superseded-document info, required action).

- Word via the docx skill (helper module at the shared scratchpad path, already configured with the program's cover-page and table styles); spreadsheets via the xlsx skill (openpyxl).

- Any CONDITIONAL planning draft (Senior WBL-dependent content) carries the boxed status statement prominently, not buried in a footnote.

- Output locations: pathway-documents/work-package-2-website/ and pathway-documents/work-package-3-curriculum-passport-gateways/. Nothing is copied into the live pages/ directory or linked from the live site.

- Log every substantive judgment call (a CONSOLIDATE beyond what this memo already decided, a term that needed clarification, a source-document conflict) back to the lead editor for the Production Control Log.