GCSD CULINARY PATHWAY | PROGRAM CONTROL DOCUMENT

Master Document Register and Website Migration Map

Existing Materials, Required Revisions, New Deliverables, and Production Priorities

| Version | 2.0 |
| --- | --- |
| Prepared by | Kevin McCann |
| Date | July 14, 2026 |
| Status | Internal Review; planning document; not adopted district policy |
| Authority | Authoritative inventory for the Canon, Operating Principles, Four-Book Series, companion system, and delivery channels |

Provide clear direction. Inspect what you expect.

Prepare students. Verify competence. Increase responsibility.

# Purpose and Authority

This register is the controlling inventory for the GCSD Culinary Pathway document system. It identifies the materials that already exist, the revisions required to align them with the current program architecture, and the documents that still must be created. It also translates the Four-Book Series into manageable production work without creating new systems, terminology, gateways, philosophies, or organizational structures.

The Culinary Pathway Canon and Operating Principles govern every item in this register. Books One through Four remain the authoritative source for program design, assessment and evaluation, operations, and Board authorization. Supporting documents should make that system usable for a defined audience; they should not restate or redesign it.

# Document Hierarchy

| Level | Contents |
| --- | --- |
| 1. Governance | Culinary Pathway Canon; Operating Principles; Master Document Register |
| 2. Core Program Series | Book One: Program Blueprint; Book Two: Assessment, Evaluation, and Continuous Improvement; Book Three: Operations Manual; Book Four: Board Proposal and Implementation Plan |
| 3. Implementation Materials | Curriculum maps, Passport and Gateway tools, handbooks, forms, procedures, records, evaluation tools, and Board deliverables |
| 4. Delivery Channels | Public Pathway Website; role-based Participant Resource Center; restricted administrative system |

# Production Rules

Do not create new program architecture. All production must remain consistent with the Canon, Operating Principles, and Four-Book Series.

Preserve the current division of responsibility among the four books. Supporting materials should implement the books, not duplicate them.

Use existing evidence before creating a new test, rubric, form, or tracker. Revise and consolidate whenever one authoritative record can serve the need.

Keep proposed, pilot, approved, active, and archived materials visibly distinct. Planning documents must not appear to be adopted district policy.

Use plain, accessible language. A document has failed when its intended users cannot understand what to do with it.

Every procedure should identify its trigger, owner, required action, authoritative record, completion check, and escalation route.

Public materials may explain the system but must not expose student records, partner review records, incident records, or restricted administrative information.

Adapt source-course and district documents into current pathway materials; do not publish raw course files as public website resources.

Every published item must show a title, audience, owner, version, effective or review date, approval status, and access classification.

Prepare students. Verify competence. Increase responsibility. Learning comes before labor, and quality comes before quantity.

# Register Codes

| Code | Meaning | Use |
| --- | --- | --- |
| KEEP | Current and aligned | Retain as authoritative; only final proofreading or approved minor correction. |
| REVISE | Current asset requires alignment | Update terminology, structure, dates, status, content, or usability while preserving its purpose. |
| CREATE | No adequate standalone document exists | Produce a new document from the governing books and existing evidence. |
| CONSOLIDATE | Duplicative or fragmented materials exist | Combine into one authoritative record and retire redundant versions. |
| REPLACE | Current asset no longer reflects the program | Publish a new version and redirect or archive the old version. |
| ARCHIVE | Historical reference only | Remove from active use; retain in controlled archive with superseded status. |
| CONDITIONAL | Dependent on authorization or decision | Draft only when needed; do not publish or operationalize before approval. |

# Priority and Access Codes

| Code | Meaning | Use |
| --- | --- | --- |
| P0 | Governance control | Required before distributed production begins. |
| P1 | Public relaunch | Required for website restructuring and accurate public communication. |
| P2 | School-based implementation | Required before full Passport, Gateway, The Cottage, or Kitchen Management use. |
| P3 | External WBL launch | Required before student placement in the senior course. |
| P4 | First operating cycle | Required for annual evaluation, reporting, refinement, and expansion decisions. |
| PUBLIC | Open access | Interest, information gathering, recruitment, and public accountability. |
| PARTICIPANT | Role-based access | Current students, families, mentors, and staff who need instructions or forms. |
| RESTRICTED | Authorized personnel only | Student records, partner review, incidents, compliance, evaluation data, and internal decisions. |

A. Governance, Architecture, and Document Control

| ID | Document / Asset | Current Status and Required Action | Audience / Access | Authority / Dependency | Priority / Owner |
| --- | --- | --- | --- | --- | --- |
| GOV-01 | Culinary Pathway Canon v3.0 | PRODUCED — RETAIN AS CURRENT PLANNING MATERIAL. Current authoritative file: GCSD_Culinary_Pathway_Canon_v3.0.docx (v3.0). | All / PUBLIC | Canon source text; Four-Book Series Current location: pathway-documents/work-package-1-governance/. | P0 / Pathway Lead |
| GOV-02 | Culinary Pathway Operating Principles v1.0 | PRODUCED — RETAIN AS CURRENT PLANNING MATERIAL. Current authoritative file: GCSD_Culinary_Pathway_Operating_Principles_v1.0.docx (v1.0). | All / PUBLIC | Operating Principles source text Current location: pathway-documents/work-package-1-governance/. | P0 / Pathway Lead |
| GOV-03 | Book One: Program Blueprint v4.0 | PRODUCED — RETAIN AS CURRENT PLANNING MATERIAL. Current authoritative file: GCSD_Culinary_Pathway_Book_1_Program_Blueprint_V4.0_Refined.docx (v4.0). | Leadership, staff, partners / PUBLIC | Canon; Operating Principles Current location: pathway-documents/work-package-1-governance/. | P0 / Pathway Lead |
| GOV-04 | Book Two: Assessment, Evaluation, and Continuous Improvement v4.1 | PRODUCED — RETAIN AS CURRENT PLANNING MATERIAL. Current authoritative file: GCSD_Culinary_Pathway_Book_2_Assessment_Evaluation_Continuous_Improvement_V4.1_Refined.docx (v4.1). | Leadership, evaluators / PUBLIC | Canon; Book One Current location: pathway-documents/work-package-1-governance/. | P0 / Pathway Lead |
| GOV-05 | Book Three: Operations Manual v4.0 | PRODUCED — RETAIN AS CURRENT PLANNING MATERIAL. Current authoritative file: GCSD_Culinary_Pathway_Book_3_Operations_Manual_V4.0_Refined.docx (v4.0). | Staff, coordinator / PARTICIPANT | Canon; Books One–Two Current location: pathway-documents/work-package-1-governance/. | P0 / Pathway Lead |
| GOV-06 | Book Four: Board Proposal and Implementation Plan v4.0 | PRODUCED — RETAIN AS CURRENT PLANNING MATERIAL. Current authoritative file: GCSD_Culinary_Pathway_Book_4_Board_Proposal_Implementation_Plan_V4.0_Refined.docx (v4.0). | Board, district leadership / PUBLIC | Canon; Books One–Three Current location: pathway-documents/work-package-1-governance/. | P0 / Pathway Lead |
| GOV-07 | Master Document Register and Website Migration Map v2.0 | PRODUCED — RETAIN AS CURRENT PLANNING MATERIAL. Current authoritative file: GCSD_CulinaryPathway_GOV-07_Master-Document-Register_v2.0_2026-07-14.docx (v2.0). | Production team / PARTICIPANT | Canon; Operating Principles; Books One–Four Current location: pathway-documents/work-package-1-governance/. | P0 / Pathway Lead |
| GOV-08 | Canonical Glossary and Terminology Sheet | PRODUCED — RETAIN AS CURRENT PLANNING MATERIAL. Current authoritative file: GCSD_CulinaryPathway_GOV-08_Canonical-Glossary_v1.0_2026-07-12.docx (v1.0). | Writers, staff, web team / PARTICIPANT | Canon v3.0 Current location: pathway-documents/work-package-1-governance/. | P0 / Pathway Lead |
| GOV-09 | Document Control and Versioning Procedure | PRODUCED — RETAIN AS CURRENT PLANNING MATERIAL. Current authoritative file: GCSD_CulinaryPathway_GOV-09_Document-Control-Versioning-Procedure_v1.1_2026-07-14.docx (v1.1). | Staff, web team / RESTRICTED | Book Three; this register Current location: pathway-documents/work-package-1-governance/. | P0 / Program Administration |
| GOV-10 | Program Status and Authorization Register | PRODUCED — RETAIN AS CURRENT PLANNING MATERIAL. Current authoritative file: GCSD_CulinaryPathway_GOV-10_Program-Status-Authorization-Register_v4.0_2026-07-12.xlsx (v4.0). | Leadership, web team / RESTRICTED | Book Four Current location: pathway-documents/work-package-1-governance/. | P0 / District Leadership |
| GOV-11 | Annual Document Review Calendar | PRODUCED — RETAIN AS CURRENT PLANNING MATERIAL. Current authoritative file: GCSD_CulinaryPathway_GOV-11_Annual-Document-Review-Calendar_v2.0_2026-07-14.xlsx (v2.0). | Staff / RESTRICTED | Book Three; document control procedure Current location: pathway-documents/work-package-1-governance/. | P1 / Program Administration |
| GOV-12 | Companion Document Map | PRODUCED — RETAIN AS CURRENT PLANNING MATERIAL. Current authoritative file: GCSD_CulinaryPathway_GOV-12_Companion-Document-Map_v1.2_2026-07-14.docx (v1.2). | All / PARTICIPANT | Books One–Four Current location: pathway-documents/work-package-1-governance/. | P1 / Pathway Lead |
| GOV-13 | Website Page Template and Content Standards | PRODUCED — RETAIN AS CURRENT PLANNING MATERIAL. Current authoritative file: GCSD_CulinaryPathway_GOV-13_Website-Page-Template-Content-Standards_v2.0_2026-07-14.docx (v2.0). | Staff and web team / RESTRICTED | GOV-09; WEB-01; GOV-10. Current location: pathway-documents/work-package-1-governance/. | P1 / Web Lead |

B. Curriculum, Course Sequence, and Instructional Alignment

| ID | Document / Asset | Current Status and Required Action | Audience / Access | Authority / Dependency | Priority / Owner |
| --- | --- | --- | --- | --- | --- |
| CUR-01 | Culinary 1 and 2 Outline (8/8/25) | PRODUCED — HOLD FOR JASON/COREY FEEDBACK. Proposed planning material; do not operationalize before confirmation. Current authoritative file: GCSD_CulinaryPathway_CUR-01_Culinary-1-2-Revised-Course-Document_v1.0_2026-07-12.docx (v1.0). | Teachers, students / PARTICIPANT | Book One; Book Two; Canon Current location: pathway-documents/work-package-3-curriculum-passport-gateways/. | P2 / Culinary Teachers |
| CUR-02 | Advanced Culinary Scope and Sequence 2023–2024 | PRODUCED — HOLD FOR JASON/COREY FEEDBACK. Proposed planning material; do not operationalize before confirmation. Current authoritative file: GCSD_CulinaryPathway_CUR-02_Advanced-Culinary-Revised-Course-Document_v1.0_2026-07-12.docx (v1.0). | Teachers, students / PARTICIPANT | Book One; Book Two; Book Three Current location: pathway-documents/work-package-3-curriculum-passport-gateways/. | P2 / Culinary Teachers |
| CUR-03 | Kitchen Management Scope and Sequence | PRODUCED — HOLD FOR JASON/COREY FEEDBACK. Proposed planning material; do not operationalize before confirmation. Current authoritative file: GCSD_CulinaryPathway_CUR-03_Kitchen-Management-Scope-Sequence_v1.1_2026-07-12.docx (v1.1). | Teachers, students / PARTICIPANT | Canon; Books One–Three Current location: pathway-documents/work-package-4-cottage-kitchen-management/. | P2 / Kitchen Management Teacher |
| CUR-04 | Senior External WBL Course Curriculum and Scope and Sequence | CONDITIONAL CREATE following district authorization. Include 1.0 credit, 300 verified hours, portfolio, workplace performance, reflection, presentation, and standards-based evaluation. | Students, coordinator / PARTICIPANT | Canon; Books Two–Four | P3 / WBL Coordinator |
| CUR-05 | Culinary Pathway Skills Map | PRODUCED — RETAIN AS CURRENT PLANNING MATERIAL. Current authoritative file: GCSD_CulinaryPathway_CUR-05_Culinary-Pathway-Skills-Map_v1.2_2026-07-12.xlsx (v1.2). | Teachers, evaluators / PARTICIPANT | Book Two; existing spreadsheet Current location: pathway-documents/work-package-3-curriculum-passport-gateways/. | P2 / Pathway Team |
| CUR-06 | Course-to-Gateway Evidence Crosswalk | PRODUCED — RETAIN AS CURRENT PLANNING MATERIAL. Current authoritative file: GCSD_CulinaryPathway_CUR-06_Course-Gateway-Evidence-Crosswalk_v1.1_2026-07-12.xlsx (v1.1). | Teachers, evaluators / PARTICIPANT | Book Two; revised Skills Map Current location: pathway-documents/work-package-3-curriculum-passport-gateways/. | P2 / Pathway Team |
| CUR-07 | Credential and Recognition Crosswalk | PRODUCED — RETAIN AS CURRENT PLANNING MATERIAL. Current authoritative file: GCSD_CulinaryPathway_CUR-07_Credential-Recognition-Crosswalk_v1.0_2026-07-12.xlsx (v1.0). | Students, families, staff / PUBLIC | Books One–Two; current course documents Current location: pathway-documents/work-package-3-curriculum-passport-gateways/. | P1 / Pathway Lead |
| CUR-08 | Assessment and Evidence Inventory | PRODUCED — RETAIN AS CURRENT PLANNING MATERIAL. Current authoritative file: GCSD_CulinaryPathway_CUR-08_Assessment-Evidence-Inventory_v1.1_2026-07-12.xlsx (v1.1). | Teachers / RESTRICTED | Book Two; existing course materials Current location: pathway-documents/work-package-3-curriculum-passport-gateways/. | P2 / Culinary Teachers |
| CUR-09 | Standard Recipe, Lab, and Production Documentation Set | INVENTORY and REVISE existing department formats; CONSOLIDATE into shared templates only where inconsistency blocks evidence or operations. | Teachers, students / PARTICIPANT | Book Two; Book Three | P2 / Culinary Teachers |
| CUR-10 | The Cottage Annual Instructional and Event Calendar | CREATE. Coordinate authentic events with instructional objectives, Gateway evidence, staffing, facilities, and district calendar constraints. | Staff, students / PARTICIPANT | Books One–Three | P2 / SBE Lead |
| CUR-11 | SkillsUSA Integration Plan | CREATE. Define recruitment, instructional alignment, competition preparation, leadership development, funding, supervision, and recognition. | Students, advisors / PARTICIPANT | Operating Principles; Book One; Book Three | P2 / SkillsUSA Advisor |
| CUR-12 | Culinary Pathway Capstone Framework | CONDITIONAL CREATE if adopted. Define purpose, eligibility, evidence, presentation, and relationship to Passport completion without creating a seventh Gateway. | Students, staff / PARTICIPANT | Canon; Books One–Three | P3 / Pathway Team |
| CUR-13 | Postsecondary and Articulation Map | CREATE. Document approved dual-credit, articulation, advanced standing, and transition opportunities; distinguish current agreements from aspirations. | Students, families / PUBLIC | Book One; district agreements | P1 / Pathway Lead |
| CUR-14 | Annual Instructional Alignment Review | CREATE a short annual record confirming that course pacing, evidence, credentials, events, and Gateway expectations remain coherent. | Staff / RESTRICTED | Book Two; Book Three | P4 / Pathway Team |

C. Competency, Gateway, Passport, and Employability Records

| ID | Document / Asset | Current Status and Required Action | Audience / Access | Authority / Dependency | Priority / Owner |
| --- | --- | --- | --- | --- | --- |
| CMP-01 | GCSD Culinary Employability Profile | PRODUCED — RETAIN AS CURRENT PLANNING MATERIAL. Current authoritative file: GCSD_CulinaryPathway_CMP-01_Employability-Profile_v1.0_2026-07-12.docx (v1.0). | Students, evaluators / RESTRICTED | Existing template; Book Two Current location: pathway-documents/work-package-3-curriculum-passport-gateways/. | P2 / Pathway Team |
| CMP-02 | Culinary Passport | PRODUCED — HOLD FOR JASON/COREY FEEDBACK. Proposed planning material; do not operationalize before confirmation. Current authoritative file: GCSD_CulinaryPathway_CMP-02_Culinary-Passport_v1.0_2026-07-12.xlsx (v1.0). | Students, staff / RESTRICTED | Canon; Book Two; Book Three Current location: pathway-documents/work-package-3-curriculum-passport-gateways/. | P2 / Pathway Team |
| CMP-03 | Gateway 1 Performance Standard and Rubric | PRODUCED — RETAIN AS CURRENT PLANNING MATERIAL. Current authoritative file: GCSD_CulinaryPathway_CMP-03-07_Gateway-1-5-Standards-Rubrics_v1.1_2026-07-12.docx (v1.1). | Students, teachers / PARTICIPANT | Canon; Book Two; current curriculum Current location: pathway-documents/work-package-3-curriculum-passport-gateways/. | P2 / Culinary Teachers |
| CMP-04 | Gateway 2 Performance Standard and Rubric | PRODUCED — RETAIN AS CURRENT PLANNING MATERIAL. Current authoritative file: GCSD_CulinaryPathway_CMP-03-07_Gateway-1-5-Standards-Rubrics_v1.1_2026-07-12.docx (v1.1). | Students, teachers / PARTICIPANT | Canon; Book Two; current curriculum Current location: pathway-documents/work-package-3-curriculum-passport-gateways/. | P2 / Culinary Teachers |
| CMP-05 | Gateway 3 Performance Standard and Rubric | PRODUCED — RETAIN AS CURRENT PLANNING MATERIAL. Current authoritative file: GCSD_CulinaryPathway_CMP-03-07_Gateway-1-5-Standards-Rubrics_v1.1_2026-07-12.docx (v1.1). | Students, teachers / PARTICIPANT | Canon; Book Two; current curriculum Current location: pathway-documents/work-package-3-curriculum-passport-gateways/. | P2 / Culinary Teachers |
| CMP-06 | Gateway 4 Performance Standard and Rubric | PRODUCED — RETAIN AS CURRENT PLANNING MATERIAL. Current authoritative file: GCSD_CulinaryPathway_CMP-03-07_Gateway-1-5-Standards-Rubrics_v1.1_2026-07-12.docx (v1.1). | Students, teachers / PARTICIPANT | Canon; Books Two–Three Current location: pathway-documents/work-package-3-curriculum-passport-gateways/. | P2 / Advanced Culinary Teacher |
| CMP-07 | Gateway 5 Performance Standard and Rubric | PRODUCED — RETAIN AS CURRENT PLANNING MATERIAL. Current authoritative file: GCSD_CulinaryPathway_CMP-03-07_Gateway-1-5-Standards-Rubrics_v1.1_2026-07-12.docx (v1.1). | Students, teachers / PARTICIPANT | Canon; Books Two–Three Current location: pathway-documents/work-package-3-curriculum-passport-gateways/. | P2 / Kitchen Management Teacher |
| CMP-08 | Gateway 6 Performance Standard and Rubric | PRODUCED — CONDITIONAL PLANNING MATERIAL. Retain for planning; the component remains not authorized. Current authoritative file: GCSD_CulinaryPathway_CMP-08_Gateway-6-Standard-Rubric_v1.0_2026-07-12.docx (v1.0). | Students, coordinator / PARTICIPANT | Canon; Books Two–Four Current location: pathway-documents/work-package-3-curriculum-passport-gateways/. | P3 / WBL Coordinator |
| CMP-09 | Gateway Verification and Completion Record | CREATE one controlled signoff format usable across Gateways, linked to the Passport rather than duplicating it. | Teachers, coordinator / RESTRICTED | Book Two; Book Three | P2 / Pathway Team |
| CMP-10 | Reassessment Plan and Record | CREATE. Document feedback, reflection, additional practice or remediation, equivalent reassessment, result, and next step. | Students, teachers / RESTRICTED | Canon; Book Two | P2 / Pathway Team |
| CMP-11 | Reverification Record | CREATE for critical competencies requiring confirmation when students enter more advanced environments. | Students, teachers / RESTRICTED | Canon; Book Two | P2 / Pathway Team |
| CMP-12 | Student Competency Progress Summary | CREATE a readable family/student progress view derived from the Passport without exposing internal notes or creating a second record. | Students, families / PARTICIPANT | Book Two; Passport | P2 / Pathway Team |
| CMP-13 | Completion-Level Criteria Sheet | CREATE a concise explanation of Completion with Distinction, Completion, and Not Yet Completed for students, families, and evaluators. | All / PUBLIC | Canon; Book Two | P1 / Pathway Lead |
| CMP-14 | Evidence Naming and Storage Guide | PRODUCED — RETAIN AS CURRENT PLANNING MATERIAL. Current authoritative file: GCSD_CulinaryPathway_CMP-14_Evidence-Naming-Storage-Guide_v1.0_2026-07-12.docx (v1.0). | Staff / RESTRICTED | Book Three; district systems Current location: pathway-documents/work-package-3-curriculum-passport-gateways/. | P2 / Program Administration |

D. Student and Family Information, Orientation, and Participation

| ID | Document / Asset | Current Status and Required Action | Audience / Access | Authority / Dependency | Priority / Owner |
| --- | --- | --- | --- | --- | --- |
| STU-01 | Student Pathway Overview | CREATE or REPLACE the generic WBL journey with the three-year course sequence, Six Gateways, Passport, The Cottage, Kitchen Management, credentials, and External WBL culmination. | Prospective students / PUBLIC | Book One; Canon | P1 / Web and Pathway Team |
| STU-02 | Student Pathway Handbook | CREATE. Explain expectations, progression, supports, reassessment, leadership, The Cottage, SkillsUSA, career preparation, and participant responsibilities. | Current students / PARTICIPANT | Books One–Three | P2 / Pathway Team |
| STU-03 | Student Interest and Career Goals Survey | REVISE or ADAPT existing survey work. Use for awareness, planning, and support—not as a barrier to access. | Students / PARTICIPANT | Book One; needs-assessment work | P1 / Pathway Team |
| STU-04 | Pathway Interest or Application Form | CONDITIONAL. Create only if district enrollment procedures require it; avoid turning the pathway into a selective gate unrelated to readiness or support. | Students / PARTICIPANT | Book One; district policy | P1 / District Leadership |
| STU-05 | Student Orientation Acknowledgment | CREATE for course, lab, SBE, and leadership expectations; use separate WBL acknowledgment when external placement begins. | Students / RESTRICTED | Book Three | P2 / Teachers |
| STU-06 | Safety, Stop-Work, and Emergency Guide | CREATE a plain-language quick reference covering immediate stop-work authority, reporting, emergency response, and adult contacts. | Students / PARTICIPANT | Book Three; district safety rules | P2 / Safety and Pathway Team |
| STU-07 | Student Support and Help-Seeking Guide | CREATE. Explain how students request clarification, remediation, accessibility support, scheduling help, transportation help, or concern review. | Students / PARTICIPANT | Operating Principles; Book Three | P2 / Student Support Team |
| STU-08 | Student Concern Report | CREATE a non-retaliatory route for safety, supervision, workload, treatment, accessibility, or placement concerns. | Students / RESTRICTED | Book Three | P2 / Program Administration |
| STU-09 | Professional Portfolio Guide | CREATE. Define common required evidence, individualized evidence, employer feedback, coordinator evaluation, reflection, file standards, checkpoints, and final review. | Students / PARTICIPANT | Canon; Books Two–Three | P2 / Pathway Team |
| STU-10 | Résumé Development Guide and Template | CREATE or adapt district career resources; align to Kitchen Management and Gateway 5. | Students / PARTICIPANT | Canon; Book One | P2 / Kitchen Management Teacher |
| STU-11 | Interview Preparation Guide | CREATE or adapt existing district resources; include practice, feedback, professional communication, and workplace questions. | Students / PARTICIPANT | Canon; Book One | P2 / Kitchen Management Teacher |
| STU-12 | Gateway Feedback Notice | CREATE a concise student-facing communication showing evidence reviewed, current status, feedback, next step, and reassessment or reverification date. | Students, families / RESTRICTED | Book Two | P2 / Teachers |
| STU-13 | External WBL Eligibility and Prelaunch Checklist | CONDITIONAL CREATE. Confirm Gateway 5, Travel Rights, approvals, agreements, training plan, schedule, transportation, safety, supports, and record readiness. | Students, families, coordinator / RESTRICTED | Canon; Book Three | P3 / WBL Coordinator |
| STU-14 | External WBL Student Agreement | CONDITIONAL CREATE. Define attendance, communication, conduct, safety, reporting, coursework, hours, portfolio, and consequences. | Students / RESTRICTED | Book Three; district policy | P3 / WBL Coordinator |
| STU-15 | Student Schedule and Transportation Plan | CONDITIONAL CREATE. Record school/work schedule, travel responsibility, backup plan, contacts, and approved changes. | Students, families / RESTRICTED | Book Three | P3 / WBL Coordinator |
| STU-16 | External WBL Hours and Activity Log | CONDITIONAL CREATE. Verify date, hours, duties, learning connection, mentor confirmation, and reconciliation. | Students, mentors / RESTRICTED | Canon; Book Three | P3 / WBL Coordinator |
| STU-17 | External WBL Check-In and Reflection Form | CONDITIONAL CREATE. Use at defined intervals for learning, feedback, safety, duties, progress, and support needs. | Students, coordinator / RESTRICTED | Books Two–Three | P3 / WBL Coordinator |
| STU-18 | Midpoint Student Self-Evaluation | CONDITIONAL CREATE and align to Gateway 6 evidence and Employability Profile categories. | Students / RESTRICTED | Book Two | P3 / WBL Coordinator |
| STU-19 | Final Student Self-Evaluation | CONDITIONAL CREATE and connect to portfolio, employer evaluation, final presentation, and transition plan. | Students / RESTRICTED | Book Two | P3 / WBL Coordinator |
| STU-20 | Final Presentation Guide and Rubric | CONDITIONAL CREATE. Define purpose, evidence, reflection, professional presentation expectations, and evaluation. | Students / PARTICIPANT | Canon; Book Two | P3 / WBL Coordinator |
| STU-21 | Exit Interview and Career Transition Plan | CONDITIONAL CREATE. Document learning, next education or employment step, references, credential status, and continuing-development goals. | Students / RESTRICTED | Book Three | P3 / WBL Coordinator |
| FAM-01 | Family Pathway Handbook | CREATE. Explain the full pathway, Gateway and Passport system, safety, supports, scheduling, credentials, The Cottage, leadership, and External WBL status. | Families / PARTICIPANT | Books One–Three | P1 / Pathway Team |
| FAM-02 | Family Course and Gateway Map | CREATE a one-page visual companion to the handbook. | Families / PUBLIC | Book One; Canon | P1 / Communications |
| FAM-03 | Family Safety and Supervision Overview | CREATE. Distinguish classroom, SBE, competition, field experience, and external WBL supervision and concern routes. | Families / PARTICIPANT | Book Three | P2 / Program Administration |
| FAM-04 | Family Permission and Participation Acknowledgment | REVISE or CREATE only for actual district-required permissions; avoid one oversized universal form. | Families / RESTRICTED | District policy; Book Three | P2 / Program Administration |
| FAM-05 | Transportation Responsibility Agreement | CONDITIONAL CREATE for external WBL and off-campus activities, with clear district, family, student, and employer responsibilities. | Families / RESTRICTED | Book Three; district policy | P3 / Transportation and WBL |
| FAM-06 | Media and Privacy Permission | REVISE existing district forms or link to them; do not create a competing release. | Families / RESTRICTED | District policy | P1 / Communications |
| FAM-07 | Family Support Planning Guide | CREATE. Explain contacts and procedures for IEP/504, accessibility, scheduling, transportation, language access, and other participation supports without collecting unnecessary sensitive data publicly. | Families / PARTICIPANT | Books One and Three | P2 / Student Support Team |
| FAM-08 | Family Concern and Emergency Routing Guide | CREATE a one-page contact and escalation guide. | Families / PARTICIPANT | Book Three | P2 / Program Administration |
| FAM-09 | Midpoint Progress Communication | CREATE a standard communication derived from Passport and placement evidence. | Families / RESTRICTED | Book Two | P2 / Teachers or Coordinator |
| FAM-10 | Pathway Completion Summary | CREATE. Summarize Gateways, credentials, recognition, WBL hours, portfolio, and next steps without duplicating the permanent record. | Students, families / RESTRICTED | Book Two; Passport; Employability Profile | P4 / Pathway Team |

E. The Cottage School-Based Enterprise

| ID | Document / Asset | Current Status and Required Action | Audience / Access | Authority / Dependency | Priority / Owner |
| --- | --- | --- | --- | --- | --- |
| SBE-01 | The Cottage Public Overview | REPLACE the generic SBE explanation with the named Culinary Pathway enterprise, its educational purpose, client-centered learning, Gateway 4, and learning-before-labor protections. | Public, clients / PUBLIC | Canon; Book One | P1 / Web and SBE Lead |
| SBE-02 | The Cottage Operations and Instructional Guide | PRODUCED — RETAIN AS CURRENT PLANNING MATERIAL. Current authoritative file: GCSD_CulinaryPathway_SBE-02-04-08-09-10-12-13-17_Cottage-Operations-Instructional-Guide_v1.0_2026-07-12.docx (v1.0). | Staff / RESTRICTED | Books One–Three Current location: pathway-documents/work-package-4-cottage-kitchen-management/. | P2 / SBE Lead |
| SBE-03 | Client Inquiry and Event Request Form | PRODUCED — RETAIN AS CURRENT PLANNING MATERIAL. Current authoritative file: GCSD_CulinaryPathway_SBE-03-06-07-11_Event-Planning-Packet_v1.0_2026-07-12.docx (v1.0). | Clients, staff / PUBLIC intake; RESTRICTED record | Book Three Current location: pathway-documents/work-package-4-cottage-kitchen-management/. | P2 / SBE Lead |
| SBE-04 | Event Feasibility and Approval Checklist | PRODUCED — RETAIN AS CURRENT PLANNING MATERIAL. Current authoritative file: GCSD_CulinaryPathway_SBE-02-04-08-09-10-12-13-17_Cottage-Operations-Instructional-Guide_v1.0_2026-07-12.docx (v1.0). | Staff / RESTRICTED | Book Three Current location: pathway-documents/work-package-4-cottage-kitchen-management/. | P2 / SBE Lead |
| SBE-05 | Client Agreement | PRODUCED — RETAIN AS CURRENT PLANNING MATERIAL. Current authoritative file: GCSD_CulinaryPathway_SBE-05_Client-Agreement_v1.1_2026-07-12.docx (v1.1). | Client, district / RESTRICTED | Book Three; district policy Current location: pathway-documents/work-package-4-cottage-kitchen-management/. | P2 / SBE Lead and Administration |
| SBE-06 | Event Educational Purpose and Gateway Evidence Plan | PRODUCED — RETAIN AS CURRENT PLANNING MATERIAL. Current authoritative file: GCSD_CulinaryPathway_SBE-03-06-07-11_Event-Planning-Packet_v1.0_2026-07-12.docx (v1.0). | Teachers / RESTRICTED | Book Two; Book Three Current location: pathway-documents/work-package-4-cottage-kitchen-management/. | P2 / Teachers |
| SBE-07 | Menu, Production, and Costing Proposal | PRODUCED — RETAIN AS CURRENT PLANNING MATERIAL. Current authoritative file: GCSD_CulinaryPathway_SBE-03-06-07-11_Event-Planning-Packet_v1.0_2026-07-12.docx (v1.0). | Students, teachers / RESTRICTED | Current curriculum; Book Three Current location: pathway-documents/work-package-4-cottage-kitchen-management/. | P2 / SBE Lead |
| SBE-08 | Purchasing and Receiving Plan | PRODUCED — RETAIN AS CURRENT PLANNING MATERIAL. Current authoritative file: GCSD_CulinaryPathway_SBE-02-04-08-09-10-12-13-17_Cottage-Operations-Instructional-Guide_v1.0_2026-07-12.docx (v1.0). | Staff, student leaders / RESTRICTED | Book Three; food safety rules Current location: pathway-documents/work-package-4-cottage-kitchen-management/. | P2 / SBE Lead |
| SBE-09 | Allergen and Food-Safety Review | PRODUCED — RETAIN AS CURRENT PLANNING MATERIAL. Current authoritative file: GCSD_CulinaryPathway_SBE-02-04-08-09-10-12-13-17_Cottage-Operations-Instructional-Guide_v1.0_2026-07-12.docx (v1.0). | Staff / RESTRICTED | Current curriculum; Book Three Current location: pathway-documents/work-package-4-cottage-kitchen-management/. | P2 / Safety and SBE Lead |
| SBE-10 | Facilities and Equipment Plan | PRODUCED — RETAIN AS CURRENT PLANNING MATERIAL. Current authoritative file: GCSD_CulinaryPathway_SBE-02-04-08-09-10-12-13-17_Cottage-Operations-Instructional-Guide_v1.0_2026-07-12.docx (v1.0). | Staff / RESTRICTED | Book Three Current location: pathway-documents/work-package-4-cottage-kitchen-management/. | P2 / SBE Lead |
| SBE-11 | Student Role and Responsibility Assignment | PRODUCED — RETAIN AS CURRENT PLANNING MATERIAL. Current authoritative file: GCSD_CulinaryPathway_SBE-03-06-07-11_Event-Planning-Packet_v1.0_2026-07-12.docx (v1.0). | Students, staff / PARTICIPANT | Operating Principles; Book Three Current location: pathway-documents/work-package-4-cottage-kitchen-management/. | P2 / Teachers |
| SBE-12 | Event Timeline and Communication Plan | PRODUCED — RETAIN AS CURRENT PLANNING MATERIAL. Current authoritative file: GCSD_CulinaryPathway_SBE-02-04-08-09-10-12-13-17_Cottage-Operations-Instructional-Guide_v1.0_2026-07-12.docx (v1.0). | Staff, student leaders / RESTRICTED | Book Three Current location: pathway-documents/work-package-4-cottage-kitchen-management/. | P2 / SBE Lead |
| SBE-13 | Production and Service Checklist | PRODUCED — RETAIN AS CURRENT PLANNING MATERIAL. Current authoritative file: GCSD_CulinaryPathway_SBE-02-04-08-09-10-12-13-17_Cottage-Operations-Instructional-Guide_v1.0_2026-07-12.docx (v1.0). | Students, staff / PARTICIPANT | Book Three Current location: pathway-documents/work-package-4-cottage-kitchen-management/. | P2 / Teachers |
| SBE-14 | Client Feedback Form | PRODUCED — RETAIN AS CURRENT PLANNING MATERIAL. Current authoritative file: GCSD_CulinaryPathway_SBE-14_Client-Feedback-Form_v1.0_2026-07-12.docx (v1.0). | Clients / PUBLIC response; RESTRICTED record | Book Two Current location: pathway-documents/work-package-4-cottage-kitchen-management/. | P2 / SBE Lead |
| SBE-15 | Student Event Reflection | PRODUCED — RETAIN AS CURRENT PLANNING MATERIAL. Current authoritative file: GCSD_CulinaryPathway_SBE-15-16-17_Event-Closeout-Financial-Reconciliation-Record_v1.0_2026-07-12.docx (v1.0). | Students / RESTRICTED | Book Two Current location: pathway-documents/work-package-4-cottage-kitchen-management/. | P2 / Teachers |
| SBE-16 | Financial and Inventory Reconciliation | PRODUCED — RETAIN AS CURRENT PLANNING MATERIAL. Current authoritative file: GCSD_CulinaryPathway_SBE-15-16-17_Event-Closeout-Financial-Reconciliation-Record_v1.0_2026-07-12.docx (v1.0). | Staff / RESTRICTED | Book Three; district finance rules Current location: pathway-documents/work-package-4-cottage-kitchen-management/. | P2 / SBE Lead and Business Office |
| SBE-17 | Event Closeout and Instructional Review | PRODUCED — RETAIN AS CURRENT PLANNING MATERIAL. Current authoritative file: GCSD_CulinaryPathway_SBE-15-16-17_Event-Closeout-Financial-Reconciliation-Record_v1.0_2026-07-12.docx (v1.0). | Staff / RESTRICTED | Books Two–Three Current location: pathway-documents/work-package-4-cottage-kitchen-management/. | P2 / SBE Lead |
| SBE-18 | Gateway 4 Evidence Record | CREATE as a controlled link to the Passport for client-centered performance; avoid a separate permanent record. | Teachers / RESTRICTED | Book Two; Passport | P2 / Advanced Culinary Teacher |
| SBE-19 | The Cottage Event Register | PRODUCED — RETAIN AS CURRENT PLANNING MATERIAL. Current authoritative file: GCSD_CulinaryPathway_SBE-19_Cottage-Event-Register_v1.0_2026-07-12.xlsx (v1.0). | Staff / RESTRICTED | Book Three Current location: pathway-documents/work-package-4-cottage-kitchen-management/. | P2 / SBE Lead |

F. Kitchen Management and Student Leadership

| ID | Document / Asset | Current Status and Required Action | Audience / Access | Authority / Dependency | Priority / Owner |
| --- | --- | --- | --- | --- | --- |
| KM-01 | Kitchen Management Public Course Overview | CREATE. Explain leadership, supervision, management, career readiness, Gateway 5, and Travel Rights. | Students, families / PUBLIC | Canon; Book One | P1 / Web and Teacher |
| KM-02 | Kitchen Management Student Leadership Handbook | PRODUCED — HOLD FOR JASON/COREY FEEDBACK. Proposed planning material; do not operationalize before confirmation. Current authoritative file: GCSD_CulinaryPathway_KM-02-03-04-05_Kitchen-Management-Student-Leadership-Handbook_v1.1_2026-07-12.docx (v1.1). | Students / PARTICIPANT | Operating Principles; Books One–Three Current location: pathway-documents/work-package-4-cottage-kitchen-management/. | P2 / Kitchen Management Teacher |
| KM-03 | Leadership Assignment Brief | PRODUCED — HOLD FOR JASON/COREY FEEDBACK. Proposed planning material; do not operationalize before confirmation. Current authoritative file: GCSD_CulinaryPathway_KM-02-03-04-05_Kitchen-Management-Student-Leadership-Handbook_v1.1_2026-07-12.docx (v1.1). | Students / PARTICIPANT | Book Three Current location: pathway-documents/work-package-4-cottage-kitchen-management/. | P2 / Kitchen Management Teacher |
| KM-04 | Crew Briefing and Communication Plan | PRODUCED — HOLD FOR JASON/COREY FEEDBACK. Proposed planning material; do not operationalize before confirmation. Current authoritative file: GCSD_CulinaryPathway_KM-02-03-04-05_Kitchen-Management-Student-Leadership-Handbook_v1.1_2026-07-12.docx (v1.1). | Students / PARTICIPANT | Operating Principles; Book Three Current location: pathway-documents/work-package-4-cottage-kitchen-management/. | P2 / Kitchen Management Teacher |
| KM-05 | Resource Management Plan | PRODUCED — HOLD FOR JASON/COREY FEEDBACK. Proposed planning material; do not operationalize before confirmation. Current authoritative file: GCSD_CulinaryPathway_KM-02-03-04-05_Kitchen-Management-Student-Leadership-Handbook_v1.1_2026-07-12.docx (v1.1). | Students / RESTRICTED | Book Three Current location: pathway-documents/work-package-4-cottage-kitchen-management/. | P2 / Kitchen Management Teacher |
| KM-06 | Event Leadership Record | PRODUCED — HOLD FOR JASON/COREY FEEDBACK. Proposed planning material; do not operationalize before confirmation. Current authoritative file: GCSD_CulinaryPathway_KM-06-08_Kitchen-Management-Event-Leadership-Packet_v1.1_2026-07-12.docx (v1.1). | Students, teacher / RESTRICTED | Book Two; Book Three Current location: pathway-documents/work-package-4-cottage-kitchen-management/. | P2 / Kitchen Management Teacher |
| KM-07 | Leadership Observation Rubric | PRODUCED — HOLD FOR JASON/COREY FEEDBACK. Proposed planning material; do not operationalize before confirmation. Current authoritative file: GCSD_CulinaryPathway_KM-07_Kitchen-Management-Leadership-Observation-Rubric_v1.1_2026-07-12.docx (v1.1). | Students, teacher / RESTRICTED | Canon; Book Two Current location: pathway-documents/work-package-4-cottage-kitchen-management/. | P2 / Kitchen Management Teacher |
| KM-08 | Post-Event Leadership Debrief | PRODUCED — HOLD FOR JASON/COREY FEEDBACK. Proposed planning material; do not operationalize before confirmation. Current authoritative file: GCSD_CulinaryPathway_KM-06-08_Kitchen-Management-Event-Leadership-Packet_v1.1_2026-07-12.docx (v1.1). | Students / RESTRICTED | Operating Principles; Book Two Current location: pathway-documents/work-package-4-cottage-kitchen-management/. | P2 / Kitchen Management Teacher |
| KM-09 | Gateway 5 Evidence Record | CREATE as a Passport-linked verification record for leadership and career readiness. | Teacher / RESTRICTED | Book Two; Passport | P2 / Kitchen Management Teacher |
| KM-10 | Career Readiness Completion Checklist | PRODUCED — HOLD FOR JASON/COREY FEEDBACK. Proposed planning material; do not operationalize before confirmation. Current authoritative file: GCSD_CulinaryPathway_KM-10_Career-Readiness-Completion-Checklist_v1.1_2026-07-12.docx (v1.1). | Students, teacher / RESTRICTED | Canon; Book Two Current location: pathway-documents/work-package-4-cottage-kitchen-management/. | P2 / Kitchen Management Teacher |

G. Employer, Mentor, Training Station, and External WBL Documents

| ID | Document / Asset | Current Status and Required Action | Audience / Access | Authority / Dependency | Priority / Owner |
| --- | --- | --- | --- | --- | --- |
| EMP-01 | Employer and Community Partnership Overview | PRODUCED — CONDITIONAL PLANNING MATERIAL. Retain for planning; the component remains not authorized. Current authoritative file: GCSD_CulinaryPathway_EMP-01_Employer-Community-Partnership-Overview_v1.0_2026-07-12.docx (v1.0). | Employers, community / PUBLIC | Book One; Book Three Current location: pathway-documents/work-package-6-employer-mentor-wbl/. | P1 / WBL Coordinator |
| EMP-02 | Partner Interest Form | PRODUCED — CONDITIONAL PLANNING MATERIAL. Retain for planning; the component remains not authorized. Current authoritative file: GCSD_CulinaryPathway_EMP-02_Partner-Interest-Form_v1.0_2026-07-12.docx (v1.0). | Employers / PUBLIC intake | Book Three Current location: pathway-documents/work-package-6-employer-mentor-wbl/. | P1 / WBL Coordinator |
| EMP-03 | Training Station Profile | PRODUCED — CONDITIONAL PLANNING MATERIAL. Retain for planning; the component remains not authorized. Current authoritative file: GCSD_CulinaryPathway_EMP-03_Training-Station-Profile_v1.0_2026-07-12.docx (v1.0). | Employer, coordinator / RESTRICTED | Book Three Current location: pathway-documents/work-package-6-employer-mentor-wbl/. | P3 / WBL Coordinator |
| EMP-04 | Training Station Screening and Site Review Checklist | PRODUCED — CONDITIONAL PLANNING MATERIAL. Retain for planning; the component remains not authorized. Current authoritative file: GCSD_CulinaryPathway_EMP-04_Training-Station-Screening-Site-Review-Checklist_v1.0_2026-07-12.docx (v1.0). | Coordinator / RESTRICTED | Book Two; Book Three Current location: pathway-documents/work-package-6-employer-mentor-wbl/. | P3 / WBL Coordinator |
| EMP-05 | Training Station Decision Notice | PRODUCED — CONDITIONAL PLANNING MATERIAL. Retain for planning; the component remains not authorized. Current authoritative file: GCSD_CulinaryPathway_EMP-05_Training-Station-Decision-Notice-Set_v1.0_2026-07-12.docx (v1.0). | Employer / RESTRICTED | Book Three Current location: pathway-documents/work-package-6-employer-mentor-wbl/. | P3 / WBL Coordinator |
| EMP-06 | Employer Partnership Agreement | PRODUCED — CONDITIONAL PLANNING MATERIAL. Retain for planning; the component remains not authorized. Current authoritative file: GCSD_CulinaryPathway_EMP-06_Employer-Partnership-Agreement_v1.0_2026-07-12.docx (v1.0). | Employer, district / RESTRICTED | Book Three; district legal review Current location: pathway-documents/work-package-6-employer-mentor-wbl/. | P3 / WBL Coordinator |
| EMP-07 | Mentor Handbook | PRODUCED — CONDITIONAL PLANNING MATERIAL. Retain for planning; the component remains not authorized. Current authoritative file: GCSD_CulinaryPathway_EMP-07-08-09_Mentor-Handbook-Orientation-Packet_v1.0_2026-07-12.docx (v1.0). | Mentors / PARTICIPANT | Books One–Three Current location: pathway-documents/work-package-6-employer-mentor-wbl/. | P3 / WBL Coordinator |
| EMP-08 | Mentor Orientation Presentation | PRODUCED — CONDITIONAL PLANNING MATERIAL. Retain for planning; the component remains not authorized. Current authoritative file: GCSD_CulinaryPathway_EMP-07-08-09_Mentor-Handbook-Orientation-Packet_v1.0_2026-07-12.docx (v1.0). | Mentors / PARTICIPANT | Book Three Current location: pathway-documents/work-package-6-employer-mentor-wbl/. | P3 / WBL Coordinator |
| EMP-09 | Mentor Orientation Acknowledgment | PRODUCED — CONDITIONAL PLANNING MATERIAL. Retain for planning; the component remains not authorized. Current authoritative file: GCSD_CulinaryPathway_EMP-07-08-09_Mentor-Handbook-Orientation-Packet_v1.0_2026-07-12.docx (v1.0). | Mentor / RESTRICTED | Book Three Current location: pathway-documents/work-package-6-employer-mentor-wbl/. | P3 / WBL Coordinator |
| EMP-10 | Individualized Training Plan | PRODUCED — CONDITIONAL PLANNING MATERIAL. Retain for planning; the component remains not authorized. Current authoritative file: GCSD_CulinaryPathway_EMP-10-11-13_Individualized-Training-Plan-Placement-Record_v1.0_2026-07-12.docx (v1.0). | Student, employer, coordinator / RESTRICTED | Book Three; Operating Principles Current location: pathway-documents/work-package-6-employer-mentor-wbl/. | P3 / WBL Coordinator |
| EMP-11 | Approved Duties and Equipment List | PRODUCED — CONDITIONAL PLANNING MATERIAL. Retain for planning; the component remains not authorized. Current authoritative file: GCSD_CulinaryPathway_EMP-10-11-13_Individualized-Training-Plan-Placement-Record_v1.0_2026-07-12.docx (v1.0). | Student, mentor / RESTRICTED | Book Three; labor/safety rules Current location: pathway-documents/work-package-6-employer-mentor-wbl/. | P3 / WBL Coordinator |
| EMP-12 | Minor Employment and Scheduling Guidance | PRODUCED — CONDITIONAL PLANNING MATERIAL. Retain for planning; the component remains not authorized. Current authoritative file: GCSD_CulinaryPathway_EMP-12_Minor-Employment-Scheduling-Guidance_v1.0_2026-07-12.docx (v1.0). | Employers, families / PARTICIPANT | Current law; district guidance Current location: pathway-documents/work-package-6-employer-mentor-wbl/. | P3 / District Administration |
| EMP-13 | Placement Emergency Contact Sheet | PRODUCED — CONDITIONAL PLANNING MATERIAL. Retain for planning; the component remains not authorized. Current authoritative file: GCSD_CulinaryPathway_EMP-10-11-13_Individualized-Training-Plan-Placement-Record_v1.0_2026-07-12.docx (v1.0). | Student, employer / RESTRICTED | Book Three Current location: pathway-documents/work-package-6-employer-mentor-wbl/. | P3 / WBL Coordinator |
| EMP-14 | Employer Hours Verification | CREATE or integrate with the student log; one authoritative hour record should be reconciled and retained. | Mentor, coordinator / RESTRICTED | Book Three | P3 / WBL Coordinator |
| EMP-15 | Midpoint Employer Evaluation | PRODUCED — CONDITIONAL PLANNING MATERIAL. Retain for planning; the component remains not authorized. Current authoritative file: GCSD_CulinaryPathway_EMP-15-16_Midpoint-Final-Employer-Evaluation_v1.0_2026-07-12.docx (v1.0). | Employer, student, coordinator / RESTRICTED | Book Two Current location: pathway-documents/work-package-6-employer-mentor-wbl/. | P3 / WBL Coordinator |
| EMP-16 | Final Employer Evaluation | PRODUCED — CONDITIONAL PLANNING MATERIAL. Retain for planning; the component remains not authorized. Current authoritative file: GCSD_CulinaryPathway_EMP-15-16_Midpoint-Final-Employer-Evaluation_v1.0_2026-07-12.docx (v1.0). | Employer, student, coordinator / RESTRICTED | Book Two Current location: pathway-documents/work-package-6-employer-mentor-wbl/. | P3 / WBL Coordinator |
| EMP-17 | Employer and Mentor Experience Survey | CREATE for training-station quality and program improvement; separate from student performance evaluation. | Employer / RESTRICTED | Book Two | P4 / WBL Coordinator |
| EMP-18 | Schedule, Duty, Mentor, or Location Change Request | PRODUCED — CONDITIONAL PLANNING MATERIAL. Retain for planning; the component remains not authorized. Current authoritative file: GCSD_CulinaryPathway_EMP-18_Schedule-Duty-Mentor-Location-Change-Request_v1.0_2026-07-12.docx (v1.0). | Employer, student / RESTRICTED | Book Three Current location: pathway-documents/work-package-6-employer-mentor-wbl/. | P3 / WBL Coordinator |
| EMP-19 | Concern and Corrective-Action Record | PRODUCED — CONDITIONAL PLANNING MATERIAL. Retain for planning; the component remains not authorized. Current authoritative file: GCSD_CulinaryPathway_EMP-19_Concern-Corrective-Action-Record_v1.0_2026-07-12.docx (v1.0). | Coordinator, administration / RESTRICTED | Book Three Current location: pathway-documents/work-package-6-employer-mentor-wbl/. | P3 / WBL Coordinator |
| EMP-20 | Incident Report | PRODUCED — CONDITIONAL PLANNING MATERIAL. Retain for planning; the component remains not authorized. Current authoritative file: GCSD_CulinaryPathway_EMP-20_Incident-Report_v1.0_2026-07-12.docx (v1.0). | Authorized staff / RESTRICTED | District policy; Book Three Current location: pathway-documents/work-package-6-employer-mentor-wbl/. | P3 / District Administration |
| EMP-21 | Placement Change, Suspension, or Early Termination Record | PRODUCED — CONDITIONAL PLANNING MATERIAL. Retain for planning; the component remains not authorized. Current authoritative file: GCSD_CulinaryPathway_EMP-21_Placement-Change-Suspension-Early-Termination-Record_v1.0_2026-07-12.docx (v1.0). | Coordinator, student, family / RESTRICTED | Book Three Current location: pathway-documents/work-package-6-employer-mentor-wbl/. | P3 / WBL Coordinator |
| EMP-22 | Partner Closeout and Renewal Review | PRODUCED — CONDITIONAL PLANNING MATERIAL. Retain for planning; the component remains not authorized. Current authoritative file: GCSD_CulinaryPathway_EMP-22_Partner-Closeout-Renewal-Review_v1.0_2026-07-12.docx (v1.0). | Coordinator, employer / RESTRICTED | Books Two–Three Current location: pathway-documents/work-package-6-employer-mentor-wbl/. | P4 / WBL Coordinator |
| EMP-23 | Partner Recognition and Thank-You Communication | CREATE templates for appropriate recognition without implying endorsement beyond approved partnership status. | Partners / PUBLIC | Book One; communications standards | P4 / Communications |

H. Program Operations, Records, Safety, and Administration

| ID | Document / Asset | Current Status and Required Action | Audience / Access | Authority / Dependency | Priority / Owner |
| --- | --- | --- | --- | --- | --- |
| OPS-01 | Annual Roles and Responsibility Matrix | CREATE. Assign district leadership, pathway lead, teachers, WBL coordinator, SBE lead, support staff, transportation, communications, and record owners. | Staff / RESTRICTED | Canon; Book Three | P2 / District Leadership |
| OPS-02 | Master Operational Calendar | CREATE. Integrate instruction, Gateways, The Cottage, SkillsUSA, partner development, WBL launch, site visits, evaluation, reporting, and document review. | Staff / RESTRICTED | Book Three | P2 / Program Administration |
| OPS-03 | Annual Launch-Readiness Checklist | CREATE. Verify authorization, staffing, capacity, courses, curriculum, records, training stations, safety, transportation, supports, website, and communication before launch. | Leadership / RESTRICTED | Book Four | P3 / District Leadership |
| OPS-04 | Student Roster and Prelaunch Tracker | PRODUCED — CONDITIONAL PLANNING MATERIAL. Retain for planning; the component remains not authorized. Current authoritative file: GCSD_CulinaryPathway_OPS-04-05-06-07-08-09-10-11-12-13-14_WBL-Coordinator-Operations-Workbook_v1.0_2026-07-12.xlsx (v1.0). | Coordinator / RESTRICTED | Book Three Current location: pathway-documents/work-package-6-employer-mentor-wbl/. | P3 / WBL Coordinator |
| OPS-05 | Partner and Training Station Database | PRODUCED — CONDITIONAL PLANNING MATERIAL. Retain for planning; the component remains not authorized. Current authoritative file: GCSD_CulinaryPathway_OPS-04-05-06-07-08-09-10-11-12-13-14_WBL-Coordinator-Operations-Workbook_v1.0_2026-07-12.xlsx (v1.0). | Coordinator / RESTRICTED | Books Two–Three Current location: pathway-documents/work-package-6-employer-mentor-wbl/. | P3 / WBL Coordinator |
| OPS-06 | Student-to-Training-Station Matching Record | PRODUCED — CONDITIONAL PLANNING MATERIAL. Retain for planning; the component remains not authorized. Current authoritative file: GCSD_CulinaryPathway_OPS-04-05-06-07-08-09-10-11-12-13-14_WBL-Coordinator-Operations-Workbook_v1.0_2026-07-12.xlsx (v1.0). | Coordinator / RESTRICTED | Book Three Current location: pathway-documents/work-package-6-employer-mentor-wbl/. | P3 / WBL Coordinator |
| OPS-07 | Agreement and Training Plan Status Tracker | PRODUCED — CONDITIONAL PLANNING MATERIAL. Retain for planning; the component remains not authorized. Current authoritative file: GCSD_CulinaryPathway_OPS-04-05-06-07-08-09-10-11-12-13-14_WBL-Coordinator-Operations-Workbook_v1.0_2026-07-12.xlsx (v1.0). | Coordinator / RESTRICTED | Book Three Current location: pathway-documents/work-package-6-employer-mentor-wbl/. | P3 / WBL Coordinator |
| OPS-08 | Coordinator Communication Log | PRODUCED — CONDITIONAL PLANNING MATERIAL. Retain for planning; the component remains not authorized. Current authoritative file: GCSD_CulinaryPathway_OPS-04-05-06-07-08-09-10-11-12-13-14_WBL-Coordinator-Operations-Workbook_v1.0_2026-07-12.xlsx (v1.0). | Coordinator / RESTRICTED | Book Three Current location: pathway-documents/work-package-6-employer-mentor-wbl/. | P3 / WBL Coordinator |
| OPS-09 | Coordinator Site-Visit and Monitoring Record | PRODUCED — CONDITIONAL PLANNING MATERIAL. Retain for planning; the component remains not authorized. Current authoritative file: GCSD_CulinaryPathway_OPS-04-05-06-07-08-09-10-11-12-13-14_WBL-Coordinator-Operations-Workbook_v1.0_2026-07-12.xlsx (v1.0). | Coordinator / RESTRICTED | Books Two–Three Current location: pathway-documents/work-package-6-employer-mentor-wbl/. | P3 / WBL Coordinator |
| OPS-10 | WBL Hour Reconciliation Record | PRODUCED — CONDITIONAL PLANNING MATERIAL. Retain for planning; the component remains not authorized. Current authoritative file: GCSD_CulinaryPathway_OPS-04-05-06-07-08-09-10-11-12-13-14_WBL-Coordinator-Operations-Workbook_v1.0_2026-07-12.xlsx (v1.0). | Coordinator / RESTRICTED | Book Three Current location: pathway-documents/work-package-6-employer-mentor-wbl/. | P3 / WBL Coordinator |
| OPS-11 | Portfolio Progress Tracker | PRODUCED — CONDITIONAL PLANNING MATERIAL. Retain for planning; the component remains not authorized. Current authoritative file: GCSD_CulinaryPathway_OPS-04-05-06-07-08-09-10-11-12-13-14_WBL-Coordinator-Operations-Workbook_v1.0_2026-07-12.xlsx (v1.0). | Student, coordinator / RESTRICTED | Book Two; portfolio guide Current location: pathway-documents/work-package-6-employer-mentor-wbl/. | P3 / WBL Coordinator |
| OPS-12 | Incident and Corrective-Action Register | PRODUCED — CONDITIONAL PLANNING MATERIAL. Retain for planning; the component remains not authorized. Current authoritative file: GCSD_CulinaryPathway_OPS-04-05-06-07-08-09-10-11-12-13-14_WBL-Coordinator-Operations-Workbook_v1.0_2026-07-12.xlsx (v1.0). | Administration / RESTRICTED | Books Two–Three Current location: pathway-documents/work-package-6-employer-mentor-wbl/. | P3 / District Administration |
| OPS-13 | Placement Status and Change Tracker | PRODUCED — CONDITIONAL PLANNING MATERIAL. Retain for planning; the component remains not authorized. Current authoritative file: GCSD_CulinaryPathway_OPS-04-05-06-07-08-09-10-11-12-13-14_WBL-Coordinator-Operations-Workbook_v1.0_2026-07-12.xlsx (v1.0). | Coordinator / RESTRICTED | Book Three Current location: pathway-documents/work-package-6-employer-mentor-wbl/. | P3 / WBL Coordinator |
| OPS-14 | Transportation and Student-Support Coordination Record | PRODUCED — CONDITIONAL PLANNING MATERIAL. Retain for planning; the component remains not authorized. Current authoritative file: GCSD_CulinaryPathway_OPS-04-05-06-07-08-09-10-11-12-13-14_WBL-Coordinator-Operations-Workbook_v1.0_2026-07-12.xlsx (v1.0). | Authorized staff / RESTRICTED | Books One and Three Current location: pathway-documents/work-package-6-employer-mentor-wbl/. | P3 / Support and Transportation |
| OPS-15 | Records Retention and Archive Schedule | CREATE with district review. Define official record, owner, system, access, retention, disposition, and superseded-document handling. | Staff / RESTRICTED | Book Three; district policy | P2 / Records Administration |
| OPS-16 | Privacy and Access Protocol | CREATE. Separate public content, participant materials, and restricted records; define permissions, sharing, and incident response. | Staff, web team / RESTRICTED | Book Three; district policy | P1 / IT and Administration |
| OPS-17 | Annual Closeout and Staff Handoff Checklist | CREATE. Confirm records, unresolved issues, partner renewal, inventory, finance, evaluation, archives, next-year calendar, and ownership. | Staff / RESTRICTED | Book Three | P4 / Program Administration |
| OPS-18 | Emergency and Escalation Contact Tree | CREATE for classroom, SBE, events, travel, and external WBL; maintain current names and after-hours procedures. | Staff / RESTRICTED | Book Three; district emergency plans | P2 / District Administration |
| OPS-19 | Legal, Insurance, Working Papers, and Risk Review Checklist | PRODUCED — CONDITIONAL PLANNING MATERIAL. Retain for planning; the component remains not authorized. Current authoritative file: GCSD_CulinaryPathway_OPS-19_Legal-Insurance-Working-Papers-Risk-Review-Checklist_v1.0_2026-07-12.docx (v1.0). | Leadership / RESTRICTED | Book Four; current law and policy Current location: pathway-documents/work-package-6-employer-mentor-wbl/. | P3 / District Administration |
| OPS-20 | Accessibility and Digital-Document Review Checklist | CREATE. Apply to website, forms, documents, presentations, and participant resources before publication. | Writers, web team / RESTRICTED | District accessibility requirements | P1 / Accessibility Lead |
| OPS-21 | Program Risk and Mitigation Register | CREATE. Track safety, staffing, capacity, transportation, equity, partner, financial, communication, and authorization risks with owners and review dates. | Leadership / RESTRICTED | Book Four | P3 / District Leadership |

I. Assessment, Evaluation, Accountability, and Continuous Improvement

| ID | Document / Asset | Current Status and Required Action | Audience / Access | Authority / Dependency | Priority / Owner |
| --- | --- | --- | --- | --- | --- |
| EVAL-01 | Student Gateway Outcome Tracker | CREATE in a restricted system. Aggregate completion, reassessment, reverification, evidence gaps, and progression without replacing the Passport. | Evaluators / RESTRICTED | Book Two | P2 / Pathway Team |
| EVAL-02 | Training Station Quality Rubric | CREATE. Evaluate safety, supervision, learning quality, duties, communication, access, student feedback, employer feedback, and corrective action. | Coordinator / RESTRICTED | Book Two | P3 / WBL Coordinator |
| EVAL-03 | Annual Program Evaluation Template | CREATE as the operational companion to Book Two. Separate student outcomes, training-station quality, and overall pathway quality. | Leadership / RESTRICTED | Book Two | P4 / Evaluation Lead |
| EVAL-04 | Student Experience Survey | CREATE for instruction, Gateway clarity, support, The Cottage, leadership, WBL, safety, belonging, and transition. | Students / RESTRICTED | Book Two | P4 / Evaluation Lead |
| EVAL-05 | Family Experience Survey | CREATE for communication, clarity, support, access, safety, scheduling, transportation, and perceived value. | Families / RESTRICTED | Book Two | P4 / Evaluation Lead |
| EVAL-06 | Employer and Mentor Program Survey | CREATE for program and training-station improvement; keep separate from individual student evaluation. | Partners / RESTRICTED | Book Two | P4 / Evaluation Lead |
| EVAL-07 | Teacher and Staff Implementation Survey | CREATE for workload, clarity, resources, evidence, operations, coordination, capacity, and improvement needs. | Staff / RESTRICTED | Book Two | P4 / Evaluation Lead |
| EVAL-08 | Advisory or Steering Committee Review Form | CREATE. Capture recommendations, evidence reviewed, conflicts, decisions, owners, and follow-up. | Committee / RESTRICTED | Books One–Two | P4 / District Leadership |
| EVAL-09 | Equity, Access, and Participation Review | CREATE. Examine awareness, enrollment, progression, supports, placement access, completion, and barriers without reducing quality standards. | Leadership / RESTRICTED | Operating Principles; Book Two | P4 / Evaluation Lead |
| EVAL-10 | Credential and Technical Assessment Results Summary | CREATE an annual aggregate report with participation, results, trends, gaps, and actions; protect student-level data. | Leadership / RESTRICTED; approved summary PUBLIC | Book Two | P4 / Pathway Team |
| EVAL-11 | WBL Participation, Hours, and Placement Summary | CONDITIONAL CREATE annually after launch. Include student count, hours, completion, site quality, incidents, changes, and outcomes. | Leadership / RESTRICTED; approved summary PUBLIC | Books Two–Three | P4 / WBL Coordinator |
| EVAL-12 | Annual Improvement Action Plan | CREATE. Convert evidence into specific actions, owners, resources, timelines, completion checks, and next review. | Leadership, staff / RESTRICTED | Book Two | P4 / Pathway Team |
| EVAL-13 | Public Annual Pathway Report | CREATE after the first complete operating cycle. Share approved outcomes, stories, credentials, partnerships, access, improvement priorities, and next steps. | Community / PUBLIC | Books Two and Four | P4 / District Leadership |
| EVAL-14 | Annual Board Accountability Report | CREATE. Provide the Board with authorization status, participation, outcomes, safety, capacity, fiscal impact, improvement, and continue/modify/pause/expand recommendation. | Board / PUBLIC or Board packet | Book Four | P4 / District Leadership |
| EVAL-15 | First-Year Implementation Report | CONDITIONAL CREATE after the first WBL operating year. Compare actual implementation with launch plan and identify required correction before expansion. | Leadership, Board / RESTRICTED or approved PUBLIC | Book Four | P4 / Program Administration |

J. Board, District Authorization, and Implementation Deliverables

| ID | Document / Asset | Current Status and Required Action | Audience / Access | Authority / Dependency | Priority / Owner |
| --- | --- | --- | --- | --- | --- |
| BRD-01 | One-Page Board Brief | CREATE from Book Four. Summarize purpose, pathway structure, request, readiness, protections, expected outcomes, and decision points. | Board / PUBLIC | Book Four | P1 / Pathway Lead |
| BRD-02 | Board Presentation Slide Deck | CREATE as a concise multimedia presentation; do not reproduce the four books. | Board / PUBLIC | Book Four | P1 / Pathway Lead |
| BRD-03 | Board Presentation Speaking Script | CREATE to accompany the deck, including transitions, anticipated questions, and clear requests. | Presenter / RESTRICTED until meeting | Book Four | P1 / Pathway Lead |
| BRD-04 | Proposed Board Resolution | CREATE with district review. Match staged authorization and reserve final authorization where required. | Board / PUBLIC packet | Book Four | P1 / District Leadership |
| BRD-05 | Fiscal Note and Resource Summary | CREATE. Identify staffing, coordinator time, transportation, equipment, professional learning, technology, insurance, and sustainability. | Board, administration / RESTRICTED or packet | Book Four | P1 / Business Office |
| BRD-06 | Staffing and Coordinator Capacity Plan | CREATE. Define roles, credentials, workload, release time, enrollment limits, supervision, and expansion thresholds. | Leadership / RESTRICTED | Book Four | P1 / District Leadership |
| BRD-07 | Transportation Implementation Plan | CREATE. Define eligible travel, responsibility, schedules, cost, contingency, communication, accessibility, and change process. | Leadership / RESTRICTED | Book Four; Book Three | P3 / Transportation |
| BRD-08 | Student Support and Accessibility Implementation Plan | CREATE. Explain how supports are planned without weakening competency or safety expectations. | Leadership / RESTRICTED | Books One and Four | P2 / Student Support Team |
| BRD-09 | Legal, Insurance, and Risk Review Memorandum | CREATE with authorized district personnel before external WBL launch. | Leadership / RESTRICTED | Book Four; current policy and law | P3 / District Administration |
| BRD-10 | Senior External WBL Course Proposal | CONDITIONAL CREATE for curriculum approval, credit, prerequisites, standards, staffing, grading, calendar, records, and evaluation. | Curriculum leadership, Board / RESTRICTED or packet | Canon; Books Two–Four | P3 / District Leadership |
| BRD-11 | CO-OP or Required State Registration Package | CONDITIONAL CREATE using current state requirements after district authorization; verify current forms and terminology at time of submission. | State/district / RESTRICTED | Book Four; current NYSED requirements | P3 / Credentialed WBL Coordinator |
| BRD-12 | Launch-Readiness Decision Memorandum | CREATE before the senior course begins. State whether required conditions are met and recommend launch, delay, limited pilot, or corrective action. | Leadership / RESTRICTED | Book Four; OPS-03 | P3 / District Leadership |
| BRD-13 | Implementation Timeline and Milestone Tracker | CREATE from Book Four. Show ownership, dependencies, decision gates, target dates, evidence, and completion status. | Leadership / RESTRICTED | Book Four | P1 / Program Administration |

K. Website, Participant Resource Center, and Digital Information Architecture

| ID | Document / Asset | Current Status and Required Action | Audience / Access | Authority / Dependency | Priority / Owner |
| --- | --- | --- | --- | --- | --- |
| WEB-01 | Website Content Map and Migration Specification | PRODUCED — STAGED ONLY. Retain as current planning material; not deployed to the live website. Current authoritative file: GCSD_CulinaryPathway_WEB-01_Website-Content-Map-Migration-Spec_v2.0_2026-07-14.docx (v2.0). | Web team / RESTRICTED | This register; Books One–Four Current location: pathway-documents/work-package-2-website/. | P1 / Web Lead |
| WEB-02 | Public Home Page | PRODUCED - STAGED ONLY. Retain as current planning material; not deployed to the live website. Current authoritative file: GCSD_CulinaryPathway_WEB-02_Home-Page_v2.0_2026-07-14.html (v2.0). | All / PUBLIC | Book One; Book Four Current location: pathway-documents/work-package-2-website/staging-pages/ | P1 / Web and Communications |
| WEB-03 | Pathway at a Glance Page | PRODUCED - STAGED ONLY. Retain as current planning material; not deployed to the live website. Current authoritative file: GCSD_CulinaryPathway_WEB-03_Pathway-at-a-Glance_v2.0_2026-07-14.html (v2.0). | All / PUBLIC | Book One; Canon Current location: pathway-documents/work-package-2-website/staging-pages/ | P1 / Web Team |
| WEB-04 | Six Gateways and Culinary Passport Page | PRODUCED - STAGED ONLY. Retain as current planning material; not deployed to the live website. Current authoritative file: GCSD_CulinaryPathway_WEB-04_Six-Gateways-Culinary-Passport_v2.0_2026-07-14.html (v2.0). | Students, families, partners / PUBLIC | Canon; Book Two Current location: pathway-documents/work-package-2-website/staging-pages/ | P1 / Web Team |
| WEB-05 | Courses and Learning Environments Page | PRODUCED - STAGED ONLY. Retain as current planning material; not deployed to the live website. Current authoritative file: GCSD_CulinaryPathway_WEB-05_Courses-Learning-Environments_v2.0_2026-07-14.html (v2.0). | Students, families / PUBLIC | Book One; current curriculum Current location: pathway-documents/work-package-2-website/staging-pages/ | P1 / Web Team |
| WEB-06 | The Cottage Page | PRODUCED - STAGED ONLY. Retain as current planning material; not deployed to the live website. Current authoritative file: GCSD_CulinaryPathway_WEB-06_The-Cottage_v2.0_2026-07-14.html (v2.0). | Community, clients / PUBLIC | Canon; Books One and Three Current location: pathway-documents/work-package-2-website/staging-pages/ | P1 / Web and SBE Lead |
| WEB-07 | Leadership, Kitchen Management, and SkillsUSA Page | PRODUCED - STAGED ONLY. Retain as current planning material; not deployed to the live website. Current authoritative file: GCSD_CulinaryPathway_WEB-07_Leadership-Kitchen-Management_v2.0_2026-07-14.html (v2.0). | Students, families, community / PUBLIC | Canon; Book One Current location: pathway-documents/work-package-2-website/staging-pages/ | P1 / Web Team |
| WEB-08 | External Work-Based Learning Page | PRODUCED - STAGED ONLY. Retain as current planning material; not deployed to the live website. Current authoritative file: GCSD_CulinaryPathway_WEB-08_External-Work-Based-Learning_v2.0_2026-07-14.html (v2.0). | Students, families, employers / PUBLIC | Canon; Books One and Four Current location: pathway-documents/work-package-2-website/staging-pages/ | P1 / Web Team |
| WEB-09 | Students and Families Page | PRODUCED - STAGED ONLY. Retain as current planning material; not deployed to the live website. Current authoritative file: GCSD_CulinaryPathway_WEB-09_Students-Families_v2.0_2026-07-14.html (v2.0). | Students, families / PUBLIC | Books One and Three Current location: pathway-documents/work-package-2-website/staging-pages/ | P1 / Web Team |
| WEB-10 | Employer and Community Partners Page | PRODUCED - STAGED ONLY. Retain as current planning material; not deployed to the live website. Current authoritative file: GCSD_CulinaryPathway_WEB-10_Employer-Community-Partners_v2.0_2026-07-14.html (v2.0). | Employers, community / PUBLIC | Books One and Three Current location: pathway-documents/work-package-2-website/staging-pages/ | P1 / Web Team |
| WEB-11 | Credentials and Recognition Page | PRODUCED - STAGED ONLY. Retain as current planning material; not deployed to the live website. Current authoritative file: GCSD_CulinaryPathway_WEB-11_Credentials-Recognition_v2.0_2026-07-14.html (v2.0). | All / PUBLIC | Books One–Two Current location: pathway-documents/work-package-2-website/staging-pages/ | P1 / Web Team |
| WEB-12 | Results and Accountability Page | PRODUCED - STAGED ONLY. Retain as current planning material; not deployed to the live website. Current authoritative file: GCSD_CulinaryPathway_WEB-12_Results-Accountability_v2.0_2026-07-14.html (v2.0). | Community, Board / PUBLIC | Book Two; Book Four Current location: pathway-documents/work-package-2-website/staging-pages/ | P1 / Web Team |
| WEB-13 | Contact, Help, and Concerns Page | PRODUCED - STAGED ONLY. Retain as current planning material; not deployed to the live website. Current authoritative file: GCSD_CulinaryPathway_WEB-13_Contact-Help-Concerns_v2.0_2026-07-14.html (v2.0). | All / PUBLIC | Book Three Current location: pathway-documents/work-package-2-website/staging-pages/ | P1 / Web Team |
| WEB-14 | Participant Resource Center Landing Page | PRODUCED - STAGED ONLY. Retain as current planning material; not deployed to the live website. Current authoritative file: GCSD_CulinaryPathway_WEB-14_Program-Resources_v1.0_2026-07-14.html (v1.0). | Participants / PARTICIPANT | Book Three Current location: pathway-documents/work-package-2-website/staging-pages/ | P1 / Web Team |
| WEB-15 | Student Resource Center | PRODUCED - STAGED ONLY. Retain as current planning material; not deployed to the live website. Current authoritative file: GCSD_CulinaryPathway_WEB-15_Student-Resources_v1.0_2026-07-14.html (v1.0). | Students / PARTICIPANT | Books Two–Three Current location: pathway-documents/work-package-2-website/staging-pages/ | P2 / Web and Pathway Team |
| WEB-16 | Family Resource Center | PRODUCED - STAGED ONLY. Retain as current planning material; not deployed to the live website. Current authoritative file: GCSD_CulinaryPathway_WEB-16_Family-Resources_v1.0_2026-07-14.html (v1.0). | Families / PARTICIPANT | Book Three Current location: pathway-documents/work-package-2-website/staging-pages/ | P2 / Web and Program Administration |
| WEB-17 | Employer and Mentor Resource Center | PRODUCED - STAGED ONLY. Retain as current planning material; not deployed to the live website. Current authoritative file: GCSD_CulinaryPathway_WEB-17_Employer-Mentor-Resources_v1.0_2026-07-14.html (v1.0). | Employers, mentors / PARTICIPANT | Book Three Current location: pathway-documents/work-package-2-website/staging-pages/ | P3 / Web and WBL Coordinator |
| WEB-18 | Staff and Coordinator Portal Structure | PRODUCED - STAGED ONLY. Retain as current planning material; not deployed to the live website. This file is a staged planning page only; no restricted staff portal or operational records platform has been authorized or created. Current authoritative file: GCSD_CulinaryPathway_WEB-18_Teacher-Staff-Resources_v1.0_2026-07-14.html (v1.0). | Authorized staff / RESTRICTED | Books Two–Three Current location: pathway-documents/work-package-2-website/staging-pages/ | P2 / IT and Program Administration |
| WEB-19 | Program Status and Approval Labels | PRODUCED — STAGED ONLY. Retain as current planning material; not deployed to the live website. Current authoritative file: GCSD_CulinaryPathway_WEB-19_Status-Label-System_v1.1_2026-07-14.docx (v1.1). | All / PUBLIC | GOV-10; Book Four Current location: pathway-documents/work-package-2-website/. | P1 / Web Lead |
| WEB-20 | Accessibility Statement and Digital Accessibility Audit | PRODUCED - STAGED ONLY. Retain as current planning material; not deployed to the live website. Current authoritative file: GCSD_CulinaryPathway_WEB-20_Accessibility-Statement_v2.0_2026-07-14.html (v2.0). | All / PUBLIC | Accessibility requirements; OPS-20 Current location: pathway-documents/work-package-2-website/staging-pages/ | P1 / Accessibility Lead |
| WEB-21 | Privacy and Records Notice | PRODUCED - STAGED ONLY. Retain as current planning material; not deployed to the live website. Current authoritative file: GCSD_CulinaryPathway_WEB-21_Privacy-Records-Notice_v2.0_2026-07-14.html (v2.0). | All / PUBLIC | OPS-16; district policy Current location: pathway-documents/work-package-2-website/staging-pages/ | P1 / IT and Administration |
| WEB-22 | Document Download Index and Version Display | PRODUCED — STAGED ONLY. Retain as current planning material; not deployed to the live website. Current authoritative file: GCSD_CulinaryPathway_WEB-22_Document-Download-Index_v2.0_2026-07-14.docx (v2.0). | All / PUBLIC and PARTICIPANT | GOV-09; this register Current location: pathway-documents/work-package-2-website/. | P1 / Web Team |
| WEB-23 | Frequently Asked Questions | PRODUCED - STAGED ONLY. Retain as current planning material; not deployed to the live website. Current authoritative file: GCSD_CulinaryPathway_WEB-23_FAQ-Partial_v2.0_2026-07-14.html (v2.0). | All / PUBLIC | Books One–Four Current location: pathway-documents/work-package-2-website/staging-pages/ | P1 / Web Team |
| WEB-24 | Website Content Ownership and Update Schedule | PRODUCED — STAGED ONLY. Retain as current planning material; not deployed to the live website. Current authoritative file: GCSD_CulinaryPathway_WEB-24_Content-Ownership-Update-Schedule_v2.0_2026-07-14.xlsx (v2.0). | Web team / RESTRICTED | GOV-09; GOV-11 Current location: pathway-documents/work-package-2-website/. | P1 / Web Lead |

L. Public Communication, Recruitment, Orientation, and Recognition

| ID | Document / Asset | Current Status and Required Action | Audience / Access | Authority / Dependency | Priority / Owner |
| --- | --- | --- | --- | --- | --- |
| COM-01 | One-Page Culinary Pathway Flyer | CREATE. Use the three-year sequence, Gateways, credentials, The Cottage, leadership, and contact information; show current planning status accurately. | Students, families, community / PUBLIC | Book One; website content | P1 / Communications |
| COM-02 | Presentation Table or Trifold Display | REVISE the CTE 566 presentation-table concept into a real pathway recruitment display with QR codes and concise audience paths. | Community events / PUBLIC | Book One; website | P1 / Communications |
| COM-03 | Public Information Slide Deck | CREATE for family nights, pathway events, partner meetings, and community presentations; distinguish it from the Board deck. | Public audiences / PUBLIC | Book One | P1 / Communications |
| COM-04 | Social Media Content Calendar | CREATE. Plan program awareness, student learning, The Cottage, SkillsUSA, partner recognition, credentials, events, and application information with approvals. | Community / PUBLIC | Book One; communications policy | P1 / Communications |
| COM-05 | SkillsUSA Interest and Information Campaign | REVISE existing post into an approved campaign set with informational-session details, website link, eligibility, and interest route. | Students, families / PUBLIC | SkillsUSA plan | P1 / Advisor and Communications |
| COM-06 | Photo, Video, Branding, and Media Standards | CREATE or link to district standards. Address consent, student privacy, customer identity, logos, alt text, captions, and approved storage. | Staff, students / RESTRICTED | District policy; accessibility requirements | P1 / Communications |
| COM-07 | Employer Recruitment Packet | CREATE. Combine one-page overview, interest process, educational purpose, mentor expectations, FAQ, and coordinator contact without including restricted agreements. | Employers / PUBLIC | Books One and Three | P1 / WBL Coordinator |
| COM-08 | Family Information Night Slide Deck | CREATE. Explain the pathway, Gateways, Passport, supports, safety, credentials, The Cottage, leadership, and WBL status. | Families / PARTICIPANT or PUBLIC event | Books One–Three | P1 / Pathway Team |
| COM-09 | Student Orientation Slide Deck | CREATE for current participants and link to the Student Handbook. | Students / PARTICIPANT | Book Three | P2 / Teachers |
| COM-10 | Employer and Mentor Orientation Slide Deck | CREATE from the Mentor Handbook and approval process. | Employers, mentors / PARTICIPANT | Book Three | P3 / WBL Coordinator |
| COM-11 | Student, Partner, and Community Recognition Templates | CREATE certificates, letters, website stories, and Board acknowledgments with consistent criteria and privacy controls. | Various / PUBLIC or PARTICIPANT | Book One; communications standards | P4 / Communications |
| COM-12 | News Release and Story Template | CREATE. Provide accurate program status, educational purpose, student voice, approvals, quotes, accessibility, and contact information. | Media, community / PUBLIC | Book One; district communications | P1 / Communications |

M. Current Asset Revision, Replacement, and Archive Decisions

| ID | Document / Asset | Current Status and Required Action | Audience / Access | Authority / Dependency | Priority / Owner |
| --- | --- | --- | --- | --- | --- |
| ARC-01 | Current Generic WBL Home and Program Overview | REVISE or REPLACE during migration. Preserve useful stakeholder language, but shift the center of gravity to the full Culinary Pathway. Archive the prior version after redirect verification. | Public website / PUBLIC | WEB-02 and WEB-03 | P1 / Web Lead |
| ARC-02 | Current Student Pathway Page with Generic Stages | REPLACE with the Six Gateways and Culinary Passport architecture. Do not present a parallel progression system. | Public website / PUBLIC | WEB-04 | P1 / Web Lead |
| ARC-03 | Current Family Information Page | REVISE. Preserve useful introductory content; add the full participant lifecycle, support, safety, Gateway, Passport, and resource-center links. | Public website / PUBLIC | WEB-09 and WEB-16 | P1 / Web Lead |
| ARC-04 | Current Employer Partners Page | REVISE. Add training-station approval, mentor role, learning-before-labor, lifecycle, resource-center links, and status language. | Public website / PUBLIC | WEB-10 and WEB-17 | P1 / Web Lead |
| ARC-05 | Current Generic School-Based Enterprise Page | REPLACE with The Cottage. Archive the generic page after redirects are active. | Public website / PUBLIC | WEB-06 | P1 / Web Lead |
| ARC-06 | Current Evaluation and Impact Page | REVISE. Separate student competency, training-station quality, and pathway quality; connect to annual public reporting. | Public website / PUBLIC | WEB-12 | P1 / Web Lead |
| ARC-07 | Current Forms and Resources Page | REPLACE with role-based navigation and document-control metadata. Remove samples, future forms, and restricted records from undifferentiated public download. | Public website / PUBLIC | WEB-14 through WEB-22 | P1 / Web Lead |
| ARC-08 | Introduction to School to Career Pathway Programming 25–26 Deck | REVISE only as a district-wide pathways presentation. Update Culinary content and contacts, but do not turn it into the Culinary Pathway Board or public-information deck. | District staff / PARTICIPANT | Current district programming | P1 / District Pathways Office |
| ARC-09 | Superseded Culinary Scope and Sequence Versions | ARCHIVE after approved replacements are published. Mark dates and superseded status; preserve historical record. | Staff / RESTRICTED archive | GOV-09 | P2 / Curriculum Office |
| ARC-10 | CTE 566 Course PDFs and Raw Assignment Materials | ARCHIVE as project sources. Do not publish as pathway documents or website downloads; adapt relevant requirements into current district materials. | Project team / RESTRICTED | Source-only materials | P0 / Pathway Lead |

Website Migration Summary

| Current Asset | Target Structure | Required Migration Action |
| --- | --- | --- |
| Current Home / Program Overview | Home + Pathway at a Glance | Rebrand around the full Culinary Pathway; retain useful stakeholder language; show current authorization status. |
| Current Student Pathway | Six Gateways and Culinary Passport | Replace the parallel generic progression model. |
| Current Family Information | Students and Families + Family Resource Center | Retain introductory content; add progression, supports, participation lifecycle, and role-based resources. |
| Current Employer Partners | Employer and Community Partners + Mentor Resource Center | Add training-station lifecycle, mentor responsibilities, learning-before-labor, and approved resource access. |
| Current School-Based Enterprise | The Cottage | Name and explain the actual SBE; connect to Advanced Culinary, Kitchen Management, and Gateway 4. |
| Current Evaluation and Impact | Results and Accountability | Separate three evaluation objects and publish only approved aggregate outcomes. |
| Current Forms and Resources | Participant Resource Center + Versioned Download Index | Replace the undifferentiated list with role, access, status, version, and purpose. |

Recommended Production Work Packages

| Work Package | Deliverables | Dependency / Gate |
| --- | --- | --- |
| Work Package 1: Governance and Control | Confirm Canon, Operating Principles, Four-Book final files, glossary, version procedure, authorization register, and document metadata standard. | P0; must finish first. |
| Work Package 2: Website Architecture and Public Content | Produce migration specification and public pages; replace generic WBL architecture; establish status labels, accessibility, privacy, and role-based navigation. | Depends on Work Package 1. |
| Work Package 3: Curriculum, Passport, and Gateways | Revise scope and sequence documents, Skills Map, Employability Profile, Passport, Gateway standards, evidence crosswalk, reassessment, and reverification. | Depends on governance; required before full pathway implementation. |
| Work Package 4: The Cottage and Kitchen Management | Build operating, event, leadership, evidence, finance, safety, and closeout materials. | Depends on Passport/Gateway definitions and Book Three. |
| Work Package 5: Student and Family Participant System | Build handbooks, orientation, support, progress, safety, portfolio, career-readiness, and participant resources. | Can proceed in parallel after governance. |
| Work Package 6: Employer, Mentor, and External WBL System | Build training-station lifecycle, agreements, orientation, training plan, logs, monitoring, evaluation, incidents, changes, closeout, and restricted trackers. | P3; requires district legal/policy verification before use. |
| Work Package 7: Evaluation, Board, and Public Accountability | Build evaluation templates, surveys, dashboards, improvement plan, Board brief/deck/script/resolution, implementation packages, and annual reports. | Use Books Two and Four; do not publish unapproved claims. |
| Work Package 8: Communications and Archive | Build flyers, event decks, social media, partner recruitment, media standards, recognition, redirects, and controlled archive. | Runs after public architecture is stable. |

Acceptance Standard for Every New or Revised Document

| ☐ Aligned to the Canon, Operating Principles, and correct source book. | ☐ Uses existing evidence and records before adding new paperwork. |
| --- | --- |
| ☐ Uses canonical terms and does not create a parallel system. | ☐ Explains the required action, submission or storage location, and next step. |
| ☐ Has one clear audience and purpose. | ☐ Is accessible, readable, and usable in both digital and printed form where appropriate. |
| ☐ States current approval or planning status accurately. | ☐ Contains no student, partner, incident, or administrative data in a public location. |
| ☐ Identifies owner, version, date, review date, and access classification. | ☐ Has been reviewed for duplication, legal/policy dependencies, broken links, and superseded versions. |

The purpose of this register is not to generate paperwork. It is to ensure that every necessary document exists once, in the right form, for the right audience, at the right level of access.

# Current Repository and Production Disposition

This section records the current disposition of produced files and major support areas. It does not change program authorization. GOV-10 remains the authority for whether a component is active, proposed, conditional, deferred, or unresolved.

| Area | Disposition | Authority / Evidence | Current location |
| --- | --- | --- | --- |
| GOV-01–GOV-13 | Retain as current planning material | Governance and authority layer | work-package-1-governance/ |
| Books 1–4 | Retain unchanged; hold architecture claims for meeting review | Canon and current four-book system | work-package-1-governance/ |
| CMP-02; CUR-01/02/03; KM documents | Hold for Jason/Corey feedback | Produced planning files; assumptions not yet confirmed | work packages 3 and 4 |
| External WBL and employer/mentor system | Retain as conditional planning material | GOV-10 PA-06/PA-14; not authorized | work-package-6-employer-mentor-wbl/ |
| Staged website | Revise now; staged only | WEB-01, GOV-13, WEB-19, GOV-10 | work-package-2-website/staging-pages/ |
| WP2A/WP3 reconciliation memo | Archive after its terminology and production decisions are absorbed | GOV-07 v2.0; Matrix; PCL | controlled archive |
| CUR-01/02 alignment memo | Archive after open questions enter the meeting decision register and controls | Meeting packet; Matrix; PCL | controlled archive |
| WP3 file manifest | Archive after current-file evidence enters GOV-07 and production controls | GOV-07 v2.0; Matrix; PCL | controlled archive |
| module-2-table-package/ | Historical coursework only; remove from active program authority without deleting history | Repository README and package README | module-2-table-package/ |
| README.md and TODO.md | Revise now | Repository continuity and current backlog | repository root |
| source materials/ | Retain ignored | External, district, course, and reference sources | local ignored directory |

Unproduced register items remain listed in their original categories. A retained ID is not evidence that a file exists, and a produced file is not evidence that the program component is authorized.