## Read Me
GCSD Culinary Pathway ¦ Production Control Document
Master Execution Matrix
Title | Master Execution Matrix — GCSD Culinary Pathway Documentation and Website Project
Audience | Kevin McCann (Pathway Lead); production team
Purpose | Show, at a glance, every work package's deliverables, dependencies, current status, unresolved decisions, files produced, and QC status.
Owner | Lead Editor / Pathway Lead
Version | 1.0
Date | July 2026
Approval / Planning Status | Planning document; not adopted district policy
Access Classification | RESTRICTED — production control document
Governing Source | Master Document Register v1.0, "Recommended Production Work Packages" table
Review Date | Update after every completed work package or Kevin McCann decision
Superseded Document | None — first issue
Headline status
• Work Package 1 (Governance and Control) is complete for this pass: the Canon, Operating Principles, and Master Document Register were audited; the current public website was audited against the target structure; and all five outstanding GOV-08–GOV-12 deliverables were produced.
• Work Packages 2 through 8 have not been produced yet. The Register's own dependency rule applies: Work Package 2 (Website) and Work Package 5 (Student/Family) can begin immediately; Work Packages 3, 4, 6, and 7 depend on governance and, for 6, on district legal/policy verification; Work Package 8 depends on the public architecture being stable.
• Three items require a decision only Kevin McCann or District Leadership can make before further production: (1) whether to authorize drafting of the Senior External WBL course materials now as CONDITIONAL/not-yet-authorized, or hold them entirely; (2) confirmation of current SkillsUSA chapter status, which is unconfirmed in source materials; (3) whether Work Package 2 (website) production should begin before or in parallel with Work Package 3 (curriculum), since both are eligible to start now.
• See the "Execution Matrix" tab for the full breakdown and the "Files Produced" tab for exact file paths.

## Execution Matrix
GCSD Culinary Pathway Master Execution Matrix — v1.0 — July 2026 — RESTRICTED — Planning document; not adopted district policy
Work Package | Register Categories | Deliverable Count | Owner / Assigned Role | Key Deliverables (sample) | Dependency / Gate | Current Status | Unresolved Decisions | QC Status
Work Package 1: Governance and Control | A (GOV-01–GOV-12) | 12 | Pathway Lead | Canon, Operating Principles, Register (existing); Glossary, Document Control Procedure, Authorization Register, Review Calendar, Companion Document Map (produced this pass) | P0 — must finish first; gates every other package. | Complete (this pass) | None outstanding for this package. | Passed internal QC (Section below); pending Kevin McCann review before distribution.
Work Package 2: Website Architecture and Public Content | K (WEB-01–24); M (ARC-01–10) | 34 | Web Lead | Website Content Map and Migration Specification; 13 target public pages; Participant Resource Center architecture; access map; redirect/archive plan; status labels; privacy and accessibility notices; version-aware download index; updated FAQ | Depends on Work Package 1 (complete). Do not deploy without Kevin McCann's review and authorization. | Not started — audit of current 9-page site complete (see website audit below) | Current site is organized around generic WBL, not the full Culinary Pathway — full page-by-page migration required per ARC-01–ARC-08. | N/A — not yet produced
Work Package 3: Curriculum, Passport, and Gateways | B (CUR-01–14); C (CMP-01–14) | 28 | Pathway Team / Culinary Teachers | Revised Culinary 1/2 and Advanced Culinary scope and sequence; new Kitchen Management scope and sequence; Skills Map; Evidence Crosswalk; Culinary Passport; Gateway 1–6 rubrics; reassessment/reverification records | Depends on Work Package 1 (complete); required before full pathway implementation. | Not started | Gateway 6 and its evidence record remain CONDITIONAL pending Senior WBL course authorization (see PA-06, GOV-10). | N/A — not yet produced
Work Package 4: The Cottage and Kitchen Management | E (SBE-01–19); F (KM-01–10) | 29 | SBE Lead / Kitchen Management Teacher | Cottage Operations and Instructional Guide; client intake through closeout document set; Gateway 4 evidence record; Kitchen Management Leadership Handbook; leadership briefs, rubric, and Gateway 5 evidence record | Depends on Passport/Gateway definitions (Work Package 3) and Book Three. | Not started | The Cottage formalizes an existing in-house catering/SBE activity (see PA-08/PA-09, GOV-10) — confirm current scope with SBE Lead before drafting operating detail. | N/A — not yet produced
Work Package 5: Student and Family Participant System | D (STU-01–21; FAM-01–10) | 31 | Pathway Team | Student and Family Pathway Handbooks; course/Gateway maps; orientation, safety, support, and concern materials; Portfolio, résumé, and interview guides; midpoint/completion communications | Can proceed in parallel after Work Package 1 (complete). | Not started | External WBL-specific student/family items (STU-13–21, FAM-05) are CONDITIONAL P3 — draft only after Senior WBL authorization. | N/A — not yet produced
Work Package 6: Employer, Mentor, and External WBL System | G (EMP-01–23) | 23 | WBL Coordinator | Partnership overview and interest form; training-station profile, screening, and decision notices; partnership agreement; mentor handbook and orientation; individualized training plan; evaluations; incident and closeout records | P3 — requires district legal/policy verification before use; depends on Senior WBL course authorization (PA-06). | Not started | No training-station partnerships currently exist for this pathway (PA-14, GOV-10) — this entire package is CONDITIONAL on Board/NYSED authorization of the Senior WBL course. | N/A — not yet produced
Work Package 7: Evaluation, Board, and Public Accountability | I (EVAL-01–15); J (BRD-01–13) | 28 | Evaluation Lead / District Leadership | Gateway outcome tracker; training-station quality rubric; annual program evaluation template; student/family/employer/staff surveys; Board brief, deck, script, and resolution; fiscal note; launch-readiness memorandum | Uses Books Two and Four; do not publish unapproved claims or projected outcomes as actual results. | Not started | No Board resolution has been proposed or scheduled (PA-15, GOV-10) — BRD-01–04 cannot proceed to Board use until Kevin McCann sets a target date. | N/A — not yet produced
Work Package 8: Communications and Archive | L (COM-01–12); M (ARC-11 legacy sources) | 12 | Communications | One-page flyer; presentation table/trifold; public information deck; social media calendar; SkillsUSA campaign; media standards; employer recruitment packet; orientation decks; recognition templates; news release template | Runs after the public architecture (Work Package 2) is stable. | Not started | SkillsUSA current chapter status is unconfirmed (PA-13, GOV-10) — confirm before drafting COM-05. | N/A — not yet produced
Cross-cutting: Program Operations, Records, Safety, Administration | H (OPS-01–21) | 21 | Program Administration / District Leadership | Roles matrix, operational calendar, launch-readiness checklist, trackers (roster, partner database, matching, agreement status, communication log, site-visit records, hour reconciliation, portfolio progress, incidents, placement status), records retention, privacy protocol, accessibility checklist, risk register | Not owned by a single work package — supports Work Package 4 (Cottage operations), Work Package 6 (WBL operations), and Work Package 7 (evaluation-adjacent registers) as each is produced. | Not started | The Register does not assign OPS to a single work package; recommend Kevin McCann confirm this cross-cutting treatment or assign it explicitly. | N/A — not yet produced
Total register items

## Website Audit
Current Website Audit vs. Target 13-Page Public Structure
Current Page | Target Structure Item | Register Action | Finding
index.html — "Greece Culinary Work-Based Learning" | 1. Home + 2. Pathway at a Glance | REVISE (WEB-02, WEB-03) | Structurally complete but branded around a generic WBL program. Must rebrand around the full three-year Culinary Pathway and add current status labeling (GOV-10).
pages/what-is-wbl.html | 5. Courses and Learning Environments (partial) | CREATE/REVISE (WEB-05) | Explains WBL generically. Needs to become Courses and Learning Environments covering Culinary 1/2, Advanced Culinary, Kitchen Management, The Cottage, SkillsUSA, and the proposed senior WBL course with accurate status labels.
pages/student-pathway.html | 3. Six Gateways and the Culinary Passport | REPLACE (WEB-04, ARC-02) | Uses a generic staged WBL journey model. Register explicitly prohibits a parallel progression system — must be replaced entirely with the Six Gateway Model and Culinary Passport.
pages/family-information.html | 8. Students and Families (partial) | REVISE (WEB-09, ARC-03) | Usable introductory language per prior gap analysis, but 5 of 11 FAQ answers defer to unresolved policy. Needs the full participation lifecycle and a link into the Family Resource Center.
pages/employer-partners.html | 9. Employer and Community Partners (partial) | REVISE (WEB-10, ARC-04) | Needs training-station lifecycle, mentor role, learning-before-labor framing, and a link into the Employer and Mentor Resource Center.
pages/school-based-enterprise.html | 5. The Cottage | REPLACE (WEB-06, ARC-05) | Currently a generic SBE explanation. Must be replaced with The Cottage, named and connected to Advanced Culinary, Kitchen Management, and Gateway 4.
pages/forms-resources.html | 12. Contact / Document Download Index (split) | REPLACE (WEB-22, ARC-07) | 53 undifferentiated resource cards, 46 still placeholder. Must be replaced with role-, status-, and access-aware navigation split across the Participant Resource Center and a public download index.
pages/evaluation-impact.html | 10. Results and Accountability | REVISE (WEB-12, ARC-06) | Framework-only, no real instruments or data (appropriate for current stage) but does not yet separate student competency, training-station quality, and program quality as three distinct evaluation objects.
pages/media-gallery.html | (supporting content, not a numbered target page) | n/a | Entirely placeholder tiles; every photo/video slot is empty. Gated on real events and signed consent, not on document production.
pages/contact.html | 11. Contact, Help, and Concerns | CREATE (WEB-13) | No named coordinator or working submission target yet. Needs separated routes for general inquiry, student/family support, employer interest, accessibility help, and urgent concerns.
(none) | 4. Leadership, Kitchen Management, and SkillsUSA | CREATE (WEB-07) | No current page exists — net-new.
(none) | 6. Credentials and Recognition | CREATE (WEB-11) | No current page exists — net-new.
(none) | 13. Frequently Asked Questions (standalone, expanded) | REVISE (WEB-23) | FAQ content currently lives inline on other pages; needs to become its own audience-organized page.
(none) | Participant Resource Center (landing + Student/Family/Employer/Staff) | CREATE (WEB-14–18) | No role-based, access-gated resource center currently exists — the site is entirely public-facing today.

## Files Produced
Files Produced This Pass (Work Package 1)
Register ID | File | Format | Location | QC Notes
GOV-08 | pathway-documents/work-package-1-governance/GCSD_CulinaryPathway_GOV-08_Canonical-Glossary_v1.0_2026-07-12.docx | Word | pathway-documents/work-package-1-governance/ | Passed acceptance checklist — see Read Me sheet.
GOV-09 | pathway-documents/work-package-1-governance/GCSD_CulinaryPathway_GOV-09_Document-Control-Versioning-Procedure_v1.0_2026-07-12.docx | Word | pathway-documents/work-package-1-governance/ | Passed acceptance checklist.
GOV-10 | pathway-documents/work-package-1-governance/GCSD_CulinaryPathway_GOV-10_Program-Status-Authorization-Register_v1.0_2026-07-12.xlsx | Excel | pathway-documents/work-package-1-governance/ | Passed acceptance checklist. Contains COUNTIF/COUNTA summary formulas — recalculates automatically on open in Excel; could not be force-recalculated in this environment (no LibreOffice installed).
GOV-11 | pathway-documents/work-package-1-governance/GCSD_CulinaryPathway_GOV-11_Annual-Document-Review-Calendar_v1.0_2026-07-12.xlsx | Excel | pathway-documents/work-package-1-governance/ | Passed acceptance checklist. Proposed rhythm — confirm against Book Three, Chapter 3 before adoption.
GOV-12 | pathway-documents/work-package-1-governance/GCSD_CulinaryPathway_GOV-12_Companion-Document-Map_v1.0_2026-07-12.docx | Word | pathway-documents/work-package-1-governance/ | Passed acceptance checklist.
(this file) | pathway-documents/work-package-1-governance/GCSD_CulinaryPathway_Master-Execution-Matrix_v1.0_2026-07-12.xlsx | Excel | pathway-documents/work-package-1-governance/ | This file.