## Read Me
GCSD Culinary Pathway ¦ Production Control Document
Master Execution Matrix
Title | Master Execution Matrix — GCSD Culinary Pathway Documentation and Website Project
Audience | Kevin McCann (Pathway Lead); production team
Purpose | Show, at a glance, every work package's deliverables, dependencies, current status, unresolved decisions, files produced, and QC status.
Owner | Lead Editor / Pathway Lead
Version | 3.0
Date | July 2026
Approval / Planning Status | Planning document; not adopted district policy
Access Classification | RESTRICTED — production control document
Governing Source | Master Document Register v1.0, "Recommended Production Work Packages" table
Review Date | Update after every completed work package or Kevin McCann decision
Superseded Document | v1.0 and v2.0, both superseded same day (2026-07-12) and archived to pathway-documents/_archive/. v3.0 reflects Work Package 2A and Work Package 3 production complete, awaiting owner visual QA review.
Headline status
• Work Package 1 (Governance and Control) is accepted as production complete and awaiting Kevin McCann's visual quality review of the Word documents and spreadsheets. That status holds until he confirms — nothing in Work Packages 2A/3 changes it.
• Work Package 2A (Website Architecture) and Work Package 3 (Curriculum, Passport, and Gateways) are both production complete as of 2026-07-12, produced in parallel per Kevin McCann's sequencing decision, reconciled by the lead editor for terminology consistency, and awaiting his visual QA review — same status as Work Package 1, not yet distributed or deployed.
• Kevin McCann's decisions, 2026-07-12: (1) draft Senior External WBL materials now as CONDITIONAL planning documents — every applicable document carries "Conditional planning draft. Not adopted district policy. Not authorized for implementation." prominently, and legal/labor-law/insurance/transportation/staffing/fiscal/NYSED-registration/district-policy claims stay flagged as unverified (see the Production Control Log's Legal-Policy Verification tab); (2) record SkillsUSA as "Exploratory / interest-development stage — active chapter status not confirmed," using "SkillsUSA development initiative" language, never an active-chapter claim; (3) began Work Packages 2 and 3 in parallel, held Work Package 5.
• Work Package 2B (final page copy for the pages that depend on Work Package 3's instructional/assessment terminology — Six Gateways/Passport, Courses and Learning Environments, Credentials and Recognition, Results and Accountability, Resource Centers) can now begin: Work Package 3 has established the authoritative Gateway, Passport, and credential language it needs.
• One open item from Work Package 2A: the reconciliation memo's Page Template Set deliverable had no ID in the Master Document Register's WEB-01–24 range. The Web Lead assigned it a provisional WEB-25 and flagged it — Kevin McCann should confirm or reassign that ID.
• One open item from Work Package 3: the original Skills Map's "Strategies for Success" column has no match in the Canon or Book Two. Retained as a legacy reference column pending Kevin McCann's confirmation of what it represents. Also, all three duplicate Skills Map source files were confirmed byte-identical (same MD5 hash) — one authoritative CUR-05 successor was produced; the three originals should be archived once Kevin confirms.
• See the "Execution Matrix" tab for the full breakdown and the "Files Produced" tab for exact file paths. See the project-wide Production Control Log for the running change log, unresolved-decision log, and legal/policy verification flags.

## Execution Matrix
GCSD Culinary Pathway Master Execution Matrix — v1.0 — July 2026 — RESTRICTED — Planning document; not adopted district policy
Work Package | Register Categories | Deliverable Count | Owner / Assigned Role | Key Deliverables (sample) | Dependency / Gate | Current Status | Unresolved Decisions | QC Status
Work Package 1: Governance and Control | A (GOV-01–GOV-12) | 12 | Pathway Lead | Canon, Operating Principles, Register (existing); Glossary, Document Control Procedure, Authorization Register, Review Calendar, Companion Document Map (produced this pass) | P0 — must finish first; gates every other package. | Production complete — awaiting owner visual QA review | None outstanding for this package. Status holds at "awaiting visual review" until Kevin McCann inspects the Word documents and spreadsheets. | Passed internal QC (Section below); pending Kevin McCann visual review before distribution.
Work Package 2A: Website Architecture (pre-terminology-lock) | K (WEB-01, 13, 19, 22, 24, 25-provisional); M (ARC-01–10 informed the audit) | 22 in scope (9 files produced) | Web Lead | Website Content Map and Migration Specification; page template standards; status-label system (points to GOV-10); document download index structure; content ownership and update schedule; Home page, Contact/Help/Concerns, Privacy and Records Notice, and Accessibility Statement produced as staged HTML (not deployed) | Depended on Work Package 1 (complete). Ran parallel to Work Package 3. Not deployed or published — staged in pathway-documents/work-package-2-website/. | Production complete — awaiting owner visual QA review | WEB-25 (Page Template Set) has no ID in the original Register's WEB-01–24 range — provisional ID assigned, needs Kevin McCann's confirmation. | Passed internal QC (files open cleanly; live site confirmed untouched; no premature Gateway/credential claims on the Home page). Pending Kevin McCann visual review.
Work Package 2B: Website Page Copy (terminology-locked) | K (WEB-02, 04–12, 14–18, 23) | 12 | Web Lead | Final page copy for the pages that depend on Work Package 3's instructional and assessment language (Six Gateways/Passport page, Courses and Learning Environments, Credentials and Recognition, Results and Accountability, Resource Centers) | Depended on Work Package 3 establishing authoritative instructional/assessment language — that dependency is now satisfied. | Not started — eligible to begin | None outstanding — ready to launch once Kevin McCann reviews Work Packages 1, 2A, and 3. | N/A — not yet produced
Work Package 3: Curriculum, Passport, and Gateways | B (CUR-01,02,05–08); C (CMP-01,02,03-07,08,14, consolidated) | 20 in scope (10 files produced) | Pathway Team / Culinary Teachers | Consolidated Culinary 1/2 + Advanced Culinary course alignment memo; reconciled Skills Map; Course-to-Gateway Evidence Crosswalk; Credential and Recognition Crosswalk; Assessment and Evidence Inventory; revised Employability Profile (edited in place); Culinary Passport workbook (Gateway Verification, Reassessment, and Reverification consolidated as linked tabs, not separate documents); Gateway 1-5 rubrics (one document); Gateway 6 rubric (separate CONDITIONAL PLANNING DRAFT); Evidence Naming and Storage Guide | Depended on Work Package 1 (complete); ran parallel to Work Package 2A; required before full pathway implementation. | Production complete — awaiting owner visual QA review | Gateway 6 and its evidence record remain CONDITIONAL PLANNING DRAFTS pending Senior WBL authorization (see PA-06, GOV-10 v2.0) — boxed statement confirmed present. Kitchen Management Scope and Sequence (CUR-03) deferred to Work Package 4. "Strategies for Success" Skills Map column has no Canon/Book Two match — needs Kevin McCann's confirmation. All three duplicate Skills Map source files confirmed byte-identical; originals should be archived once confirmed. | Passed internal QC (files open cleanly; conditional-draft language verified present; terminology cross-checked against Work Package 2A). Pending Kevin McCann visual review.
Work Package 4: The Cottage and Kitchen Management | E (SBE-01–19); F (KM-01–10); CUR-03 | 30 | SBE Lead / Kitchen Management Teacher | Cottage Operations and Instructional Guide; client intake through closeout document set; Gateway 4 evidence record; Kitchen Management Scope and Sequence; Kitchen Management Leadership Handbook; leadership briefs, rubric, and Gateway 5 evidence record | Depends on Passport/Gateway definitions (Work Package 3) and Book Three. | Not started | The Cottage formalizes an existing in-house catering/SBE activity (see PA-08/PA-09, GOV-10) — confirm current scope with SBE Lead before drafting operating detail. | N/A — not yet produced
Work Package 5: Student and Family Participant System | D (STU-01–21; FAM-01–10) | 31 | Pathway Team | Student and Family Pathway Handbooks; course/Gateway maps; orientation, safety, support, and concern materials; Portfolio, résumé, and interview guides; midpoint/completion communications | Eligible to proceed after Work Package 1, but ON HOLD. | On hold — do not begin | Kevin McCann decision, 2026-07-12: hold Work Package 5 while Work Packages 2A and 3 proceed. External WBL-specific student/family items (STU-13–21, FAM-05) will additionally be CONDITIONAL planning drafts once this package starts. | N/A — on hold
Work Package 6: Employer, Mentor, and External WBL System | G (EMP-01–23) | 23 | WBL Coordinator | Partnership overview and interest form; training-station profile, screening, and decision notices; partnership agreement; mentor handbook and orientation; individualized training plan; evaluations; incident and closeout records | P3 — requires district legal/policy verification before use; depends on Senior WBL course authorization (PA-06). | Not started | No training-station partnerships currently exist for this pathway (PA-14, GOV-10) — this entire package is CONDITIONAL on Board/NYSED authorization of the Senior WBL course. | N/A — not yet produced
Work Package 7: Evaluation, Board, and Public Accountability | I (EVAL-01–15); J (BRD-01–13) | 28 | Evaluation Lead / District Leadership | Gateway outcome tracker; training-station quality rubric; annual program evaluation template; student/family/employer/staff surveys; Board brief, deck, script, and resolution; fiscal note; launch-readiness memorandum | Uses Books Two and Four; do not publish unapproved claims or projected outcomes as actual results. | Not started | No Board resolution has been proposed or scheduled (PA-15, GOV-10) — BRD-01–04 cannot proceed to Board use until Kevin McCann sets a target date. | N/A — not yet produced
Work Package 8: Communications and Archive | L (COM-01–12); M (ARC-11 legacy sources) | 12 | Communications | One-page flyer; presentation table/trifold; public information deck; social media calendar; SkillsUSA campaign; media standards; employer recruitment packet; orientation decks; recognition templates; news release template | Runs after the public architecture (Work Package 2) is stable. | Not started | SkillsUSA current chapter status is unconfirmed (PA-13, GOV-10) — confirm before drafting COM-05. | N/A — not yet produced
Cross-cutting: Program Operations, Records, Safety, Administration | H (OPS-01–21) | 21 | Program Administration / District Leadership | Roles matrix, operational calendar, launch-readiness checklist, trackers (roster, partner database, matching, agreement status, communication log, site-visit records, hour reconciliation, portfolio progress, incidents, placement status), records retention, privacy protocol, accessibility checklist, risk register | Not owned by a single work package — supports Work Package 4 (Cottage operations), Work Package 6 (WBL operations), and Work Package 7 (evaluation-adjacent registers) as each is produced. | Not started | The Register does not assign OPS to a single work package; recommend Kevin McCann confirm this cross-cutting treatment or assign it explicitly. | N/A — not yet produced
Total register items

## Website Audit
Current Website Audit vs. Target 13-Page Public Structure
Current Page | Target Structure Item | Register Action | Finding
index.html — "Greece Culinary Work-Based Learning" | 1. Home + 2. Pathway at a Glance | REVISE (WEB-02, WEB-03) | Structurally complete but branded around a generic WBL program. Must rebrand around the full three-year Culinary Pathway and add current status labeling (GOV-10).
pages/what-is-wbl.html | 5. Courses and Learning Environments (partial) | CREATE/REVISE (WEB-05) | Explains WBL generically. Needs to become Courses and Learning Environments covering Culinary 1/2, Advanced Culinary, Kitchen Management, The Cottage, SkillsUSA, and the proposed senior WBL course with accurate status labels.
pages/student-pathway.html | 3. Six Gateways and the Culinary Passport | REPLACE (WEB-04, ARC-02) | Uses a generic staged WBL journey model. Register explicitly prohibits a parallel progression system — must be replaced entirely with the Six Gateway Model and Culinary Passport.
pages/family-information.html | 8. Students and Families (partial) | REVISE (WEB-09, ARC-03) | Usable introductory language per prior gap analysis, but 5 of 11 FAQ answers defer to unresolved policy. Needs the full participation lifecycle and a link into the Family Resource Center.
pages/employer-partners.html | 9. Employer and Community Partners (partial) | REVISE (WEB-10, ARC-04) | Needs training-station lifecycle, mentor role, learning-before-labor framing, and a link into the Employer and Mentor Resource Center.
pages/school-based-enterprise.html | 5. The Cottage | REPLACE (WEB-06, ARC-05) | Currently a generic SBE explanation. Must be replaced with The Cottage, named and connected to Advanced Culinary, Kitchen Management, and Gateway 4.
pages/forms-resources.html | 12. Contact / Document Download Index (split) | REPLACE (WEB-22, ARC-07) | 53 undifferentiated resource cards, 46 still placeholder. Must be replaced with role-, status-, and access-aware navigation split across the Participant Resource Center and a public download index.
pages/evaluation-impact.html | 10. Results and Accountability | REVISE (WEB-12, ARC-06) | Framework-only, no real instruments or data (appropriate for current stage) but does not yet separate student competency, training-station quality, and program quality as three distinct evaluation objects.
pages/media-gallery.html | (supporting content, not a numbered target page) | n/a | Entirely placeholder tiles; every photo/video slot is empty. Gated on real events and signed consent, not on document production.
pages/contact.html | 11. Contact, Help, and Concerns | CREATE (WEB-13) | No named coordinator or working submission target yet. Needs separated routes for general inquiry, student/family support, employer interest, accessibility help, and urgent concerns.
(none) | 4. Leadership, Kitchen Management, and SkillsUSA | CREATE (WEB-07) | No current page exists — net-new.
(none) | 6. Credentials and Recognition | CREATE (WEB-11) | No current page exists — net-new.
(none) | 13. Frequently Asked Questions (standalone, expanded) | REVISE (WEB-23) | FAQ content currently lives inline on other pages; needs to become its own audience-organized page.
(none) | Participant Resource Center (landing + Student/Family/Employer/Staff) | CREATE (WEB-14–18) | No role-based, access-gated resource center currently exists — the site is entirely public-facing today.

## Files Produced
Files Produced Through This Pass — Work Packages 1, 2A, and 3
Register ID | File | Format | Location | QC Notes
GOV-08 | pathway-documents/work-package-1-governance/GCSD_CulinaryPathway_GOV-08_Canonical-Glossary_v1.0_2026-07-12.docx | Word | pathway-documents/work-package-1-governance/ | Passed acceptance checklist — see Read Me sheet.
GOV-09 | pathway-documents/work-package-1-governance/GCSD_CulinaryPathway_GOV-09_Document-Control-Versioning-Procedure_v1.0_2026-07-12.docx | Word | pathway-documents/work-package-1-governance/ | Passed acceptance checklist.
GOV-10 | pathway-documents/work-package-1-governance/GCSD_CulinaryPathway_GOV-10_Program-Status-Authorization-Register_v2.0_2026-07-12.xlsx | Excel | pathway-documents/work-package-1-governance/ | v2.0 — updated with Kevin McCann's Senior WBL and SkillsUSA decisions, 2026-07-12. v1.0 archived to pathway-documents/_archive/. Contains COUNTIF/COUNTA summary formulas — recalculates automatically on open in Excel; could not be force-recalculated in this environment (no LibreOffice installed).
GOV-11 | pathway-documents/work-package-1-governance/GCSD_CulinaryPathway_GOV-11_Annual-Document-Review-Calendar_v1.0_2026-07-12.xlsx | Excel | pathway-documents/work-package-1-governance/ | Passed acceptance checklist. Proposed rhythm — confirm against Book Three, Chapter 3 before adoption.
GOV-12 | pathway-documents/work-package-1-governance/GCSD_CulinaryPathway_GOV-12_Companion-Document-Map_v1.0_2026-07-12.docx | Word | pathway-documents/work-package-1-governance/ | Passed acceptance checklist.
WEB-01 | pathway-documents/work-package-2-website/GCSD_CulinaryPathway_WEB-01_Website-Content-Map-Migration-Spec_v1.0_2026-07-12.docx | Word | pathway-documents/work-package-2-website/ | Passed acceptance checklist. Master migration plan for all 13 public pages + Participant Resource Center.
WEB-25 | pathway-documents/work-package-2-website/GCSD_CulinaryPathway_WEB-25_Page-Template-Standards_v1.0_2026-07-12.docx | Word | pathway-documents/work-package-2-website/ | Provisional Register ID (no WEB-01–24 slot fit) — needs Kevin McCann's confirmation.
WEB-19 | pathway-documents/work-package-2-website/GCSD_CulinaryPathway_WEB-19_Status-Label-System_v1.0_2026-07-12.docx | Word | pathway-documents/work-package-2-website/ | Points to GOV-10 as sole status source — does not invent new categories.
WEB-22 | pathway-documents/work-package-2-website/GCSD_CulinaryPathway_WEB-22_Document-Download-Index_v1.0_2026-07-12.docx | Word | pathway-documents/work-package-2-website/ | Structure only, as instructed — no content rows yet.
WEB-24 | pathway-documents/work-package-2-website/GCSD_CulinaryPathway_WEB-24_Content-Ownership-Update-Schedule_v1.0_2026-07-12.xlsx | Excel | pathway-documents/work-package-2-website/ | 29-row tracker covering live pages, WP2A deliverables, and WP2B targets.
WEB-02 | pathway-documents/work-package-2-website/staging-pages/GCSD_CulinaryPathway_WEB-02_Home-Page_v1.0_2026-07-12.html | HTML (staged) | pathway-documents/work-package-2-website/staging-pages/ | Verified no premature Gateway/credential claims. Not linked from live nav.
WEB-13 | pathway-documents/work-package-2-website/staging-pages/GCSD_CulinaryPathway_WEB-13_Contact-Help-Concerns_v1.0_2026-07-12.html | HTML (staged) | pathway-documents/work-package-2-website/staging-pages/ | Contact points use labeled placeholders, not the live site's real-looking address.
WEB-21 | pathway-documents/work-package-2-website/staging-pages/GCSD_CulinaryPathway_WEB-21_Privacy-Records-Notice_v1.0_2026-07-12.html | HTML (staged) | pathway-documents/work-package-2-website/staging-pages/ | Passed acceptance checklist.
WEB-20 | pathway-documents/work-package-2-website/staging-pages/GCSD_CulinaryPathway_WEB-20_Accessibility-Statement_v1.0_2026-07-12.html | HTML (staged) | pathway-documents/work-package-2-website/staging-pages/ | Includes OPS-20 checklist as an in-page appendix per the reconciliation memo's CONSOLIDATE decision.
— | pathway-documents/work-package-2-website/staging-pages/assets/status-labels.css | CSS | pathway-documents/work-package-2-website/staging-pages/assets/ | Additive-only stylesheet layered on the existing assets/css/styles.css — live CSS confirmed unmodified.
CUR-01/02 | pathway-documents/work-package-3-curriculum-passport-gateways/GCSD_CulinaryPathway_CUR-01-02_Course-Alignment-Memo_v1.0_2026-07-12.docx | Word | pathway-documents/work-package-3-curriculum-passport-gateways/ | Consolidated per reconciliation memo. Built from the actual 8/8/25 and 2023-24 source S&S documents.
CUR-05 | pathway-documents/work-package-3-curriculum-passport-gateways/GCSD_CulinaryPathway_CUR-05_Culinary-Pathway-Skills-Map_v1.0_2026-07-12.xlsx | Excel | pathway-documents/work-package-3-curriculum-passport-gateways/ | The three duplicate source files were confirmed byte-identical (same MD5) — one authoritative successor produced.
CUR-06 | pathway-documents/work-package-3-curriculum-passport-gateways/GCSD_CulinaryPathway_CUR-06_Course-Gateway-Evidence-Crosswalk_v1.0_2026-07-12.xlsx | Excel | pathway-documents/work-package-3-curriculum-passport-gateways/ | Built on the reconciled CUR-05.
CUR-07 | pathway-documents/work-package-3-curriculum-passport-gateways/GCSD_CulinaryPathway_CUR-07_Credential-Recognition-Crosswalk_v1.0_2026-07-12.xlsx | Excel | pathway-documents/work-package-3-curriculum-passport-gateways/ | Passed acceptance checklist.
CUR-08 | pathway-documents/work-package-3-curriculum-passport-gateways/GCSD_CulinaryPathway_CUR-08_Assessment-Evidence-Inventory_v1.0_2026-07-12.xlsx | Excel | pathway-documents/work-package-3-curriculum-passport-gateways/ | True gaps flagged rather than papered over with invented assessments.
CMP-01 | pathway-documents/work-package-3-curriculum-passport-gateways/GCSD_CulinaryPathway_CMP-01_Employability-Profile_v1.0_2026-07-12.docx | Word | pathway-documents/work-package-3-curriculum-passport-gateways/ | Existing district template edited in place — verified original tables/checkboxes/grading scales preserved (6 tables in source, 7 in revision, added table is the metadata block).
CMP-02 | pathway-documents/work-package-3-curriculum-passport-gateways/GCSD_CulinaryPathway_CMP-02_Culinary-Passport_v1.0_2026-07-12.xlsx | Excel | pathway-documents/work-package-3-curriculum-passport-gateways/ | Blank record template (Passport Summary, Gateway Status, Evidence/Reassessment/Reverification Logs) with one example row each — not a filled student record.
CMP-03–07 | pathway-documents/work-package-3-curriculum-passport-gateways/GCSD_CulinaryPathway_CMP-03-07_Gateway-1-5-Standards-Rubrics_v1.0_2026-07-12.docx | Word | pathway-documents/work-package-3-curriculum-passport-gateways/ | One document, five Gateway sections, per the reconciliation memo's CONSOLIDATE decision.
CMP-08 | pathway-documents/work-package-3-curriculum-passport-gateways/GCSD_CulinaryPathway_CMP-08_Gateway-6-Standard-Rubric_v1.0_2026-07-12.docx | Word | pathway-documents/work-package-3-curriculum-passport-gateways/ | Verified: boxed "CONDITIONAL PLANNING DRAFT / Not adopted district policy / Not authorized for implementation" statement present near the top and in an appendix table.
CMP-14 | pathway-documents/work-package-3-curriculum-passport-gateways/GCSD_CulinaryPathway_CMP-14_Evidence-Naming-Storage-Guide_v1.0_2026-07-12.docx | Word | pathway-documents/work-package-3-curriculum-passport-gateways/ | Cross-references GOV-09 rather than restating it, per the reconciliation memo.