## Read Me
GCSD Culinary Pathway ¦ Production Control Document
Master Execution Matrix
Title | Master Execution Matrix — GCSD Culinary Pathway Documentation and Website Project
Audience | Kevin McCann (Pathway Lead); production team
Purpose | Show, at a glance, every work package's deliverables, dependencies, current status, unresolved decisions, files produced, and QC status.
Owner | Lead Editor / Pathway Lead
Version | 5.0
Date | July 2026
Approval / Planning Status | Planning document; not adopted district policy
Access Classification | RESTRICTED — production control document
Governing Source | Master Document Register v1.0, "Recommended Production Work Packages" table; Kevin McCann's 2026-07-12 quality-control corrections
Review Date | Update after every completed work package or Kevin McCann decision
Superseded Document | v1.0–v4.0, all superseded 2026-07-12 and archived to pathway-documents/_archive/. v5.0 records Work Package 4 (Cottage/Kitchen Management) and Work Package 2B Phase 1 (website page copy) as production complete, both awaiting owner visual QA review.
Headline status
• Work Package 1 (Governance and Control) remains "production complete — awaiting owner visual QA review." That status holds until Kevin McCann confirms.
• Work Package 2A (Website Architecture) remains "production complete — awaiting owner visual QA review" — 9 files, GOV-13 relocation applied (see below), not deployed.
• Work Package 3 (Curriculum, Passport, and Gateways) status is CORRECTED to "Architecture and alignment complete — course-document revision pending." Kevin McCann's quality-control review found the earlier "production complete" label overstated: only an analysis memo exists for CUR-01/CUR-02, not the actual revised, versioned Culinary 1/2 and Advanced Culinary course documents. See the WP3 File Manifest (pathway-documents/work-package-3-curriculum-passport-gateways/GCSD_CulinaryPathway_WP3-File-Manifest_v1.0_2026-07-12.xlsx) for the file-by-file finding.
• Source-file immutability verified: no file in source materials/ was modified in place. All mtimes predate this session; the Employability Profile source still shows its original unfixed typo and placeholder text. The earlier "edited in place" report language was imprecise, not an actual violation — see the WP3 File Manifest's Source Immutability tab for the full verification.
• UD-04 (OPS category) resolved: OPS-01 through OPS-21 are reassigned individually by operational domain on the new "OPS Item Assignment" tab, per Kevin McCann's rule that OPS is a document category, not a work package. The prior single "Cross-cutting: Program Operations" row is removed.
• UD-05 (course status) resolved: GOV-10 v3.0 records Culinary 1, Culinary 2, and Advanced Culinary as "Active — existing GCSD instructional program; document title and course-sequence terminology pending final alignment with the official district course guide" — the Canon's course names are not assumed to be the exact official district titles.
• UD-06 (Page Template Set ID) resolved: relocated from provisional WEB-25 to GOV-13 (Website Page Template and Content Standards), moved to pathway-documents/work-package-1-governance/ as a governance/publication-control document.
• UD-07 (Strategies for Success) resolved: reclassified in CUR-05 v1.1 as an unverified legacy field, not used for Gateway, Passport, assessment, or public-claim purposes, pending confirmation from Jason Carlson, Corey Skinner, or another authorized GCSD representative.
• Work Package 4 (The Cottage and Kitchen Management) is production complete — 11 files, consolidated down from 30 raw Register items. Cottage and Kitchen Management framing verified compliant ("not just a catering business," "not additional cooking instruction" both explicitly stated). Gateway 4/5 evidence routes into the existing CMP-02 Passport, not a new file. One agent run hit a session rate limit partway through — the 7 Cottage-side files it had already completed were valid and kept; it was resumed to finish the 4 remaining Kitchen Management files with no rework or data loss.
• Work Package 2B Phase 1 (website page copy for the pages Work Package 3 unblocked) is production complete — 7 pages, all set to "Internal Review" status pending Pathway Lead sign-off. Dependency controls verified: exact conditional-draft language present on Gateway 6 content, SkillsUSA exploratory language used correctly, Cottage/Kitchen Management sections kept deliberately brief with a visible "pending Work Package 4" notice (written before Work Package 4 closed — now satisfied). Work Package 2B Phase 2 (Cottage/KM detail pages, External WBL, Employer Partners, Resource Centers) is next, gated on Work Package 6 for the WBL/Employer pages.
• Two new follow-ups, not blocking: the 7 new WP2B pages use a 9-item nav that differs from the 4 original WP2A pages' shorter nav — needs a unification pass before any deployment. CMP-03-07's Gateway 5 section (Work Package 3) now has a stale note claiming CUR-03 doesn't exist — Work Package 3's owner should update it now that Work Package 4 produced CUR-03.
• Work Package 5 remains on hold. Detailed External WBL and Employer Partners public copy still wait for Work Package 6 to verify the operational model, labor law, transportation, insurance, staffing, and authorization status.
• See the "Execution Matrix" and "OPS Item Assignment" tabs for the full breakdown and the "Files Produced" tab for exact file paths. See the project-wide Production Control Log for the running change log, unresolved-decision log, and legal/policy verification flags.

## Execution Matrix
GCSD Culinary Pathway Master Execution Matrix — v1.0 — July 2026 — RESTRICTED — Planning document; not adopted district policy
Work Package | Register Categories | Deliverable Count | Owner / Assigned Role | Key Deliverables (sample) | Dependency / Gate | Current Status | Unresolved Decisions | QC Status
Work Package 1: Governance and Control | A (GOV-01–GOV-12) | 12 | Pathway Lead | Canon, Operating Principles, Register (existing); Glossary, Document Control Procedure, Authorization Register, Review Calendar, Companion Document Map (produced this pass) | P0 — must finish first; gates every other package. | Production complete — awaiting owner visual QA review | None outstanding for this package. Status holds at "awaiting visual review" until Kevin McCann inspects the Word documents and spreadsheets. | Passed internal QC (Section below); pending Kevin McCann visual review before distribution.
Work Package 2A: Website Architecture (pre-terminology-lock) | K (WEB-01, 13, 19, 22, 24); M (ARC-01–10 informed the audit); GOV-13 (relocated from provisional WEB-25) | 21 in scope (9 files produced) | Web Lead | Website Content Map and Migration Specification; page template standards (now GOV-13, a governance document); status-label system (points to GOV-10); document download index structure; content ownership and update schedule; Home page, Contact/Help/Concerns, Privacy and Records Notice, and Accessibility Statement produced as staged HTML (not deployed) | Depended on Work Package 1 (complete). Ran parallel to Work Package 3. Not deployed or published — staged in pathway-documents/work-package-2-website/. | Production complete — awaiting owner visual QA review | RESOLVED (UD-06, 2026-07-12): the Page Template Set is now GOV-13 (Website Page Template and Content Standards), relocated to pathway-documents/work-package-1-governance/ as a governance/publication-control document, not a public website page. | Passed internal QC (files open cleanly; live site confirmed untouched; no premature Gateway/credential claims on the Home page). Pending Kevin McCann visual review.
Work Package 2B Phase 1: Website Page Copy (terminology-locked, non-Cottage/KM) | K (WEB-03, 04, 05, 09, 11, 12, 23-partial) | 7 | Web Lead | Pathway at a Glance; Six Gateways and Culinary Passport (Gateway 6 boxed conditional); Courses and Learning Environments (full detail on Culinary 1/2/Advanced Culinary, brief deferred mentions of Cottage/KM/SkillsUSA/WBL); Students and Families overview; Credentials and Recognition; Results and Accountability; partial FAQ | Depended on Work Package 3 establishing authoritative instructional/assessment language — satisfied. Ran parallel to Work Package 4. | Production complete — awaiting owner visual QA review | All 7 pages set to "Internal Review" approval status (not yet "Approved for Planning Use" like the WP2A pages) since the Pathway Lead/Web Lead have not yet reviewed them. Credentials page: GOV-10 only has an explicit status row for ServSafe (PA-10) — YouScience/ProStart/CDOS/technical assessment/CTE endorsement/postsecondary credit have no individual GOV-10 row, so no status badge was assigned to them rather than guessing; recommend Kevin McCann confirm whether GOV-10 needs new rows for these. Nav list on the 7 new pages (9 items) differs from the shorter nav baked into the 4 original WP2A pages — a follow-up reconciliation pass should unify them before any deployment. | Passed internal QC (all pages open cleanly, single H1, metadata block present, conditional-draft language verified present on WEB-04/05, SkillsUSA exploratory language verified, Cottage/KM sections confirmed brief and deferred). Pending Kevin McCann visual review.
Work Package 2B Phase 2: Website Page Copy (Cottage, Kitchen Management, remaining FAQ, Resource Centers) | K (WEB-06, 07, 08, 10, 14–18, 23-remainder) | 13 | Web Lead | The Cottage page; Kitchen Management/SkillsUSA page; External WBL page; Employer and Community Partners page; Participant Resource Center pages; remaining FAQ sections | Depends on Work Package 4 (Cottage/Kitchen Management operations — complete) for Cottage/KM pages, and Work Package 6 (External WBL verification) for the WBL and Employer pages. | Not started — eligible to begin for Cottage/KM pages now that Work Package 4 is complete | External WBL and Employer Partners pages remain blocked on Work Package 6. | N/A — not yet produced
Work Package 3: Curriculum, Passport, and Gateways | B (CUR-05–08 produced; CUR-01/02 memo only, revision pending); C (CMP-01,02,03-07,08,14, consolidated) | 20 in scope (10 files + 1 manifest produced; 2 course-document revisions still pending) | Pathway Team / Culinary Teachers | Course Alignment Memo (analysis only — NOT a revised course document, see WP3 File Manifest); reconciled Skills Map v1.1; Course-to-Gateway Evidence Crosswalk; Credential and Recognition Crosswalk; Assessment and Evidence Inventory; revised Employability Profile (genuine revision, original source confirmed untouched); Culinary Passport workbook (Gateway Verification, Reassessment, and Reverification consolidated as linked tabs); Gateway 1-5 rubrics (one document); Gateway 6 rubric (separate CONDITIONAL PLANNING DRAFT); Evidence Naming and Storage Guide | Depended on Work Package 1 (complete); ran parallel to Work Package 2A; required before full pathway implementation. | Architecture and alignment complete — course-document revision pending | CORRECTED (Kevin McCann, 2026-07-12): status was overstated as "production complete." File-level manifest (GCSD_CulinaryPathway_WP3-File-Manifest_v1.0_2026-07-12.xlsx) confirms only an analysis memo exists for CUR-01/CUR-02 — the actual revised, versioned Culinary 1/2 and Advanced Culinary course documents do not yet exist and remain pending. Gateway 6 and its evidence record remain CONDITIONAL PLANNING DRAFTS pending Senior WBL authorization (PA-06, GOV-10 v3.0) — boxed statement confirmed present. Kitchen Management Scope and Sequence (CUR-03) deferred to Work Package 4. Skills Map "Strategies for Success" column reclassified per UD-07 (see GOV-10 v3.0 / CUR-05 v1.1) as an unverified legacy field — not used for Gateway/Passport/assessment logic. All three duplicate Skills Map source files confirmed content-identical and left untouched in source materials/. | Passed internal QC on the 10 files that do exist (files open cleanly; conditional-draft language verified present; terminology cross-checked against Work Package 2A; source immutability verified — see Source Immutability tab of the manifest). Pending Kevin McCann visual review. NOT yet eligible for "production complete" status.
Work Package 4: The Cottage and Kitchen Management | E (SBE-01–19, consolidated to 6 files); F (KM-01–10, consolidated to 5 files); CUR-03; H (no OPS items assigned — see OPS Item Assignment tab) | 30 in scope (11 files produced) | SBE Lead / Kitchen Management Teacher | Cottage Operations and Instructional Guide; Event Planning Packet; Client Agreement; Event Closeout and Financial Reconciliation Record; Client Feedback Form; Cottage Event Register; Kitchen Management Scope and Sequence (CUR-03); Kitchen Management Student Leadership Handbook; Kitchen Management Event Leadership Packet; Leadership Observation Rubric; Career Readiness Completion Checklist | Depended on Passport/Gateway definitions (Work Package 3, complete) and Book Three. Ran parallel to Work Package 2B Phase 1. One agent run was interrupted by a session rate limit partway through (all 7 Cottage-side files completed cleanly first) and resumed to finish the remaining 4 Kitchen Management files — no rework needed, nothing lost. | Production complete — awaiting owner visual QA review | The Cottage formalizes an existing in-house catering/SBE activity (see PA-08/PA-09, GOV-10) — confirmed consistent, no conflict found. Gateway 4/5 evidence routes into the existing CMP-02 Passport rather than creating SBE-18/KM-09 as separate files. CUR-03's existence makes a status note inside CMP-03-07 (Work Package 3's Gateway 5 section, which said CUR-03 didn't exist yet) stale — flagged as a Work Package 3 follow-up, not corrected here since CMP-03-07 belongs to that package. Client Agreement (SBE-05) payment/cancellation/liability terms are explicit placeholders pending district counsel — no Legal-Policy Verification tab item currently covers Cottage contract terms specifically; recommend adding one. | Passed internal QC (all 11 files open cleanly; source materials/ confirmed untouched via git status and mtime check; "additional cooking instruction" and "catering business" framing both explicitly denied in the relevant documents). Pending Kevin McCann visual review.
Work Package 5: Student and Family Participant System | D (STU-01–21; FAM-01–10) | 31 | Pathway Team | Student and Family Pathway Handbooks; course/Gateway maps; orientation, safety, support, and concern materials; Portfolio, résumé, and interview guides; midpoint/completion communications | Eligible to proceed after Work Package 1, but ON HOLD. | On hold — do not begin | Kevin McCann decision, 2026-07-12: hold Work Package 5 while Work Packages 2A and 3 proceed. External WBL-specific student/family items (STU-13–21, FAM-05) will additionally be CONDITIONAL planning drafts once this package starts. | N/A — on hold
Work Package 6: Employer, Mentor, and External WBL System | G (EMP-01–23); H (OPS-04–14, OPS-19 — 12 items, see OPS Item Assignment tab) | 35 | WBL Coordinator | Partnership overview and interest form; training-station profile, screening, and decision notices; partnership agreement; mentor handbook and orientation; individualized training plan; evaluations; incident and closeout records; roster/partner-database/matching/agreement-status/communication-log/site-visit/hour-reconciliation/portfolio-progress/incident/placement-status trackers; legal-insurance-risk checklist | P3 — requires district legal/policy verification before use; depends on Senior WBL course authorization (PA-06). | Not started | No training-station partnerships currently exist for this pathway (PA-14, GOV-10) — this entire package is CONDITIONAL on Board/NYSED authorization of the Senior WBL course. | N/A — not yet produced
Work Package 7: Evaluation, Board, and Public Accountability | I (EVAL-01–15); J (BRD-01–13); H (OPS-03 — 1 item, see OPS Item Assignment tab) | 29 | Evaluation Lead / District Leadership | Gateway outcome tracker; training-station quality rubric; annual program evaluation template; student/family/employer/staff surveys; Board brief, deck, script, and resolution; fiscal note; launch-readiness memorandum; annual launch-readiness checklist | Uses Books Two and Four; do not publish unapproved claims or projected outcomes as actual results. | Not started | No Board resolution has been proposed or scheduled (PA-15, GOV-10) — BRD-01–04 cannot proceed to Board use until Kevin McCann sets a target date. | N/A — not yet produced
Work Package 8: Communications and Archive | L (COM-01–12); M (ARC-11 legacy sources); H (OPS-20 — 1 item, already produced under WP2A) | 13 | Communications | One-page flyer; presentation table/trifold; public information deck; social media calendar; SkillsUSA campaign; media standards; employer recruitment packet; orientation decks; recognition templates; news release template | Runs after the public architecture (Work Package 2) is stable. | Not started | SkillsUSA is recorded as "Exploratory / interest-development stage — active chapter status not confirmed" (PA-13, GOV-10) — use "SkillsUSA development initiative" language, never an active-chapter claim, when drafting COM-05. OPS-20 (Accessibility and Digital-Document Review Checklist) was already produced as an appendix inside WEB-20 under Work Package 2A — do not recreate it here. | N/A — not yet produced
Governance / Lead Editor: cross-program operations coordination (not a numbered work package) | H (OPS-01, 02, 15, 16, 17, 18, 21 — 7 items, see OPS Item Assignment tab) | 7 | Lead Editor / Program Administration | Annual roles and responsibility matrix; master operational calendar; records retention and archive schedule; privacy and access protocol; annual closeout and staff handoff checklist; emergency and escalation contact tree; program risk and mitigation register | Per Kevin McCann's 2026-07-12 correction (UD-04): OPS is a document category, not a work package. These 7 items span every work package's staff roles, calendars, records procedures, and Book Three controls, so the lead editor coordinates them as an ongoing governance responsibility rather than a 9th numbered work package. | Not started | None — this row exists only to show where the remaining OPS items live; it does not compete with Work Packages 1-8 for sequencing. | N/A — not yet produced
Total register items

## OPS Item Assignment
OPS Item Assignment — individual domain assignment per Kevin McCann's 2026-07-12 correction (UD-04): OPS is a document category, not a work package.
Register ID | Document / Asset | Assigned To | Rationale
OPS-01 | Annual Roles and Responsibility Matrix | Governance / Lead Editor | Cross-program staff roles — spans every work package, not owned by one.
OPS-02 | Master Operational Calendar | Governance / Lead Editor | Cross-program calendar integrating instruction, Gateways, Cottage, SkillsUSA, WBL, evaluation, and document review.
OPS-03 | Annual Launch-Readiness Checklist | Work Package 7 | Operational companion to BRD-12 Launch-Readiness Decision Memorandum — a Board/authorization decision-gate document.
OPS-04 | Student Roster and Prelaunch Tracker | Work Package 6 | External WBL / training-station operations.
OPS-05 | Partner and Training Station Database | Work Package 6 | External WBL / training-station operations.
OPS-06 | Student-to-Training-Station Matching Record | Work Package 6 | External WBL / training-station operations.
OPS-07 | Agreement and Training Plan Status Tracker | Work Package 6 | External WBL / training-station operations.
OPS-08 | Coordinator Communication Log | Work Package 6 | External WBL / training-station operations.
OPS-09 | Coordinator Site-Visit and Monitoring Record | Work Package 6 | External WBL / training-station operations.
OPS-10 | WBL Hour Reconciliation Record | Work Package 6 | External WBL / training-station operations.
OPS-11 | Portfolio Progress Tracker | Work Package 6 | Tracks the Senior WBL portfolio specifically (Book Three Ch.20) — External WBL operations.
OPS-12 | Incident and Corrective-Action Register | Work Package 6 | Training-station quality and incident pattern review tie to External WBL operations; cross-reference Work Package 7 for annual evaluation use.
OPS-13 | Placement Status and Change Tracker | Work Package 6 | External WBL / training-station operations.
OPS-14 | Transportation and Student-Support Coordination Record | Work Package 6 | Tied to off-site placement transportation — External WBL operations.
OPS-15 | Records Retention and Archive Schedule | Governance / Lead Editor | Cross-program records procedure (Book Three control).
OPS-16 | Privacy and Access Protocol | Governance / Lead Editor | Cross-program records procedure (Book Three control) — separates public/participant/restricted content district-wide.
OPS-17 | Annual Closeout and Staff Handoff Checklist | Governance / Lead Editor | Cross-program annual cycle, not specific to one work package.
OPS-18 | Emergency and Escalation Contact Tree | Governance / Lead Editor | Explicitly spans classroom, SBE, events, travel, and external WBL — cross-program by definition.
OPS-19 | Legal, Insurance, Working Papers, and Risk Review Checklist | Work Package 6 | Required specifically before External WBL authorization (cross-referenced in the Production Control Log's Legal-Policy Verification tab, LP-01–LP-06).
OPS-20 | Accessibility and Digital-Document Review Checklist | Work Package 8 (already produced under Work Package 2A) | Communications/publication operations — already delivered as an appendix inside WEB-20 Accessibility Statement; do not recreate.
OPS-21 | Program Risk and Mitigation Register | Governance / Lead Editor | Spans safety, staffing, capacity, transportation, equity, partner, financial, communication, and authorization risk — cross-program by nature; cross-reference Work Package 7 for Board-facing use.

## Website Audit
Current Website Audit vs. Target 13-Page Public Structure
Current Page | Target Structure Item | Register Action | Finding
index.html — "Greece Culinary Work-Based Learning" | 1. Home + 2. Pathway at a Glance | REVISE (WEB-02, WEB-03) | Structurally complete but branded around a generic WBL program. Must rebrand around the full three-year Culinary Pathway and add current status labeling (GOV-10).
pages/what-is-wbl.html | 5. Courses and Learning Environments (partial) | CREATE/REVISE (WEB-05) | Explains WBL generically. Needs to become Courses and Learning Environments covering Culinary 1/2, Advanced Culinary, Kitchen Management, The Cottage, SkillsUSA, and the proposed senior WBL course with accurate status labels.
pages/student-pathway.html | 3. Six Gateways and the Culinary Passport | REPLACE (WEB-04, ARC-02) | Uses a generic staged WBL journey model. Register explicitly prohibits a parallel progression system — must be replaced entirely with the Six Gateway Model and Culinary Passport.
pages/family-information.html | 8. Students and Families (partial) | REVISE (WEB-09, ARC-03) | Usable introductory language per prior gap analysis, but 5 of 11 FAQ answers defer to unresolved policy. Needs the full participation lifecycle and a link into the Family Resource Center.
pages/employer-partners.html | 9. Employer and Community Partners (partial) | REVISE (WEB-10, ARC-04) | Needs training-station lifecycle, mentor role, learning-before-labor framing, and a link into the Employer and Mentor Resource Center.
pages/school-based-enterprise.html | 5. The Cottage | REPLACE (WEB-06, ARC-05) | Currently a generic SBE explanation. Must be replaced with The Cottage, named and connected to Advanced Culinary, Kitchen Management, and Gateway 4.
pages/forms-resources.html | 12. Contact / Document Download Index (split) | REPLACE (WEB-22, ARC-07) | 53 undifferentiated resource cards, 46 still placeholder. Must be replaced with role-, status-, and access-aware navigation split across the Participant Resource Center and a public download index.
pages/evaluation-impact.html | 10. Results and Accountability | REVISE (WEB-12, ARC-06) | Framework-only, no real instruments or data (appropriate for current stage) but does not yet separate student competency, training-station quality, and program quality as three distinct evaluation objects.
pages/media-gallery.html | (supporting content, not a numbered target page) | n/a | Entirely placeholder tiles; every photo/video slot is empty. Gated on real events and signed consent, not on document production.
pages/contact.html | 11. Contact, Help, and Concerns | CREATE (WEB-13) | No named coordinator or working submission target yet. Needs separated routes for general inquiry, student/family support, employer interest, accessibility help, and urgent concerns.
(none) | 4. Leadership, Kitchen Management, and SkillsUSA | CREATE (WEB-07) | No current page exists — net-new.
(none) | 6. Credentials and Recognition | CREATE (WEB-11) | No current page exists — net-new.
(none) | 13. Frequently Asked Questions (standalone, expanded) | REVISE (WEB-23) | FAQ content currently lives inline on other pages; needs to become its own audience-organized page.
(none) | Participant Resource Center (landing + Student/Family/Employer/Staff) | CREATE (WEB-14–18) | No role-based, access-gated resource center currently exists — the site is entirely public-facing today.

## Files Produced
Files Produced Through This Pass — Work Packages 1, 2A, and 3
Register ID | File | Format | Location | QC Notes
GOV-08 | pathway-documents/work-package-1-governance/GCSD_CulinaryPathway_GOV-08_Canonical-Glossary_v1.0_2026-07-12.docx | Word | pathway-documents/work-package-1-governance/ | Passed acceptance checklist — see Read Me sheet.
GOV-09 | pathway-documents/work-package-1-governance/GCSD_CulinaryPathway_GOV-09_Document-Control-Versioning-Procedure_v1.0_2026-07-12.docx | Word | pathway-documents/work-package-1-governance/ | Passed acceptance checklist.
GOV-10 | pathway-documents/work-package-1-governance/GCSD_CulinaryPathway_GOV-10_Program-Status-Authorization-Register_v3.0_2026-07-12.xlsx | Excel | pathway-documents/work-package-1-governance/ | v3.0 — corrects PA-02/03/04 course-title language per Kevin McCann's UD-05 decision, 2026-07-12. v1.0/v2.0 archived to pathway-documents/_archive/. Contains COUNTIF/COUNTA summary formulas — recalculates automatically on open in Excel; could not be force-recalculated in this environment (no LibreOffice installed).
GOV-11 | pathway-documents/work-package-1-governance/GCSD_CulinaryPathway_GOV-11_Annual-Document-Review-Calendar_v1.0_2026-07-12.xlsx | Excel | pathway-documents/work-package-1-governance/ | Passed acceptance checklist. Proposed rhythm — confirm against Book Three, Chapter 3 before adoption.
GOV-12 | pathway-documents/work-package-1-governance/GCSD_CulinaryPathway_GOV-12_Companion-Document-Map_v1.0_2026-07-12.docx | Word | pathway-documents/work-package-1-governance/ | Passed acceptance checklist.
GOV-13 | pathway-documents/work-package-1-governance/GCSD_CulinaryPathway_GOV-13_Website-Page-Template-Content-Standards_v1.0_2026-07-12.docx | Word | pathway-documents/work-package-1-governance/ | Relocated from provisional WEB-25 per Kevin McCann's UD-06 decision, 2026-07-12 — was in pathway-documents/work-package-2-website/, now here as a governance/publication-control document. Prior file archived.
WEB-01 | pathway-documents/work-package-2-website/GCSD_CulinaryPathway_WEB-01_Website-Content-Map-Migration-Spec_v1.0_2026-07-12.docx | Word | pathway-documents/work-package-2-website/ | Updated 2026-07-12 to reference GOV-13 instead of provisional WEB-25 (Section 8 and the deliverable table).
WEB-19 | pathway-documents/work-package-2-website/GCSD_CulinaryPathway_WEB-19_Status-Label-System_v1.0_2026-07-12.docx | Word | pathway-documents/work-package-2-website/ | Points to GOV-10 as sole status source — does not invent new categories.
WEB-22 | pathway-documents/work-package-2-website/GCSD_CulinaryPathway_WEB-22_Document-Download-Index_v1.0_2026-07-12.docx | Word | pathway-documents/work-package-2-website/ | Structure only, as instructed — no content rows yet.
WEB-24 | pathway-documents/work-package-2-website/GCSD_CulinaryPathway_WEB-24_Content-Ownership-Update-Schedule_v1.0_2026-07-12.xlsx | Excel | pathway-documents/work-package-2-website/ | 29-row tracker covering live pages, WP2A deliverables, and WP2B targets.
WEB-02 | pathway-documents/work-package-2-website/staging-pages/GCSD_CulinaryPathway_WEB-02_Home-Page_v1.0_2026-07-12.html | HTML (staged) | pathway-documents/work-package-2-website/staging-pages/ | Verified no premature Gateway/credential claims. Not linked from live nav.
WEB-13 | pathway-documents/work-package-2-website/staging-pages/GCSD_CulinaryPathway_WEB-13_Contact-Help-Concerns_v1.0_2026-07-12.html | HTML (staged) | pathway-documents/work-package-2-website/staging-pages/ | Contact points use labeled placeholders, not the live site's real-looking address.
WEB-21 | pathway-documents/work-package-2-website/staging-pages/GCSD_CulinaryPathway_WEB-21_Privacy-Records-Notice_v1.0_2026-07-12.html | HTML (staged) | pathway-documents/work-package-2-website/staging-pages/ | Passed acceptance checklist.
WEB-20 | pathway-documents/work-package-2-website/staging-pages/GCSD_CulinaryPathway_WEB-20_Accessibility-Statement_v1.0_2026-07-12.html | HTML (staged) | pathway-documents/work-package-2-website/staging-pages/ | Includes OPS-20 checklist as an in-page appendix per the reconciliation memo's CONSOLIDATE decision.
— | pathway-documents/work-package-2-website/staging-pages/assets/status-labels.css | CSS | pathway-documents/work-package-2-website/staging-pages/assets/ | Additive-only stylesheet layered on the existing assets/css/styles.css — live CSS confirmed unmodified.
— | pathway-documents/work-package-3-curriculum-passport-gateways/GCSD_CulinaryPathway_WP3-File-Manifest_v1.0_2026-07-12.xlsx | Excel | pathway-documents/work-package-3-curriculum-passport-gateways/ | NEW, 2026-07-12: file-by-file manifest confirming what actually exists vs. what's pending, produced per Kevin McCann's quality-control correction. See its "Pending Deliverables" tab.
CUR-01-02 | pathway-documents/work-package-3-curriculum-passport-gateways/GCSD_CulinaryPathway_CUR-01-02_Course-Alignment-Memo_v1.0_2026-07-12.docx | Word | pathway-documents/work-package-3-curriculum-passport-gateways/ | ANALYSIS MEMO ONLY — not a revised course document (corrected 2026-07-12, see WP3 File Manifest). Built from the actual 8/8/25 and 2023-24 source S&S documents, which remain untouched in source materials/.
CUR-05 | pathway-documents/work-package-3-curriculum-passport-gateways/GCSD_CulinaryPathway_CUR-05_Culinary-Pathway-Skills-Map_v1.1_2026-07-12.xlsx | Excel | pathway-documents/work-package-3-curriculum-passport-gateways/ | v1.1, 2026-07-12: "Strategies for Success" column reclassified as an unverified legacy field per Kevin McCann's UD-07 decision (not used for Gateway/Passport/assessment logic; needs Jason Carlson/Corey Skinner confirmation). v1.0 archived. The three duplicate source files are confirmed content-identical (cell-by-cell comparison; raw file MD5 differs only due to xlsx zip-container metadata) and remain untouched in source materials/.
CUR-06 | pathway-documents/work-package-3-curriculum-passport-gateways/GCSD_CulinaryPathway_CUR-06_Course-Gateway-Evidence-Crosswalk_v1.0_2026-07-12.xlsx | Excel | pathway-documents/work-package-3-curriculum-passport-gateways/ | Built on the reconciled CUR-05.
CUR-07 | pathway-documents/work-package-3-curriculum-passport-gateways/GCSD_CulinaryPathway_CUR-07_Credential-Recognition-Crosswalk_v1.0_2026-07-12.xlsx | Excel | pathway-documents/work-package-3-curriculum-passport-gateways/ | Passed acceptance checklist.
CUR-08 | pathway-documents/work-package-3-curriculum-passport-gateways/GCSD_CulinaryPathway_CUR-08_Assessment-Evidence-Inventory_v1.0_2026-07-12.xlsx | Excel | pathway-documents/work-package-3-curriculum-passport-gateways/ | True gaps flagged rather than papered over with invented assessments.
CMP-01 | pathway-documents/work-package-3-curriculum-passport-gateways/GCSD_CulinaryPathway_CMP-01_Employability-Profile_v1.0_2026-07-12.docx | Word | pathway-documents/work-package-3-curriculum-passport-gateways/ | REVISED COPY, separately named — source Employability Profile- Culinary Pathway-Template.docx confirmed untouched (mtime predates session; original typo and placeholder text still present in source). Verified original tables/checkboxes/grading scales preserved (6 tables in source, 7 in revision, added table is the metadata block).
CMP-02 | pathway-documents/work-package-3-curriculum-passport-gateways/GCSD_CulinaryPathway_CMP-02_Culinary-Passport_v1.0_2026-07-12.xlsx | Excel | pathway-documents/work-package-3-curriculum-passport-gateways/ | Blank record template (Passport Summary, Gateway Status, Evidence/Reassessment/Reverification Logs) with one example row each — not a filled student record.
CMP-03–07 | pathway-documents/work-package-3-curriculum-passport-gateways/GCSD_CulinaryPathway_CMP-03-07_Gateway-1-5-Standards-Rubrics_v1.0_2026-07-12.docx | Word | pathway-documents/work-package-3-curriculum-passport-gateways/ | One document, five Gateway sections, per the reconciliation memo's CONSOLIDATE decision.
CMP-08 | pathway-documents/work-package-3-curriculum-passport-gateways/GCSD_CulinaryPathway_CMP-08_Gateway-6-Standard-Rubric_v1.0_2026-07-12.docx | Word | pathway-documents/work-package-3-curriculum-passport-gateways/ | Verified: boxed "CONDITIONAL PLANNING DRAFT / Not adopted district policy / Not authorized for implementation" statement present near the top and in an appendix table.
CMP-14 | pathway-documents/work-package-3-curriculum-passport-gateways/GCSD_CulinaryPathway_CMP-14_Evidence-Naming-Storage-Guide_v1.0_2026-07-12.docx | Word | pathway-documents/work-package-3-curriculum-passport-gateways/ | Cross-references GOV-09 rather than restating it, per the reconciliation memo.
WEB-03 | pathway-documents/work-package-2-website/staging-pages/GCSD_CulinaryPathway_WEB-03_Pathway-at-a-Glance_v1.0_2026-07-12.html | HTML (staged) | pathway-documents/work-package-2-website/staging-pages/ | Internal Review status. Summary-level three-year sequence.
WEB-04 | pathway-documents/work-package-2-website/staging-pages/GCSD_CulinaryPathway_WEB-04_Six-Gateways-Culinary-Passport_v1.0_2026-07-12.html | HTML (staged) | pathway-documents/work-package-2-website/staging-pages/ | Internal Review status. Verified: exact boxed conditional-draft statement present on Gateway 6; explicitly states individual Passport records are private/restricted.
WEB-05 | pathway-documents/work-package-2-website/staging-pages/GCSD_CulinaryPathway_WEB-05_Courses-Learning-Environments_v1.0_2026-07-12.html | HTML (staged) | pathway-documents/work-package-2-website/staging-pages/ | Internal Review status. Verified: Cottage/KM/SkillsUSA/WBL sections kept brief with a visible deferral notice; full detail on Culinary 1/2/Advanced Culinary.
WEB-09 | pathway-documents/work-package-2-website/staging-pages/GCSD_CulinaryPathway_WEB-09_Students-Families_v1.0_2026-07-12.html | HTML (staged) | pathway-documents/work-package-2-website/staging-pages/ | Internal Review status. General discovery overview, not the full Resource Center.
WEB-11 | pathway-documents/work-package-2-website/staging-pages/GCSD_CulinaryPathway_WEB-11_Credentials-Recognition_v1.0_2026-07-12.html | HTML (staged) | pathway-documents/work-package-2-website/staging-pages/ | Internal Review status. Only ServSafe carries a status badge (GOV-10 PA-10) — other credentials have no GOV-10 row, flagged rather than guessed.
WEB-12 | pathway-documents/work-package-2-website/staging-pages/GCSD_CulinaryPathway_WEB-12_Results-Accountability_v1.0_2026-07-12.html | HTML (staged) | pathway-documents/work-package-2-website/staging-pages/ | Internal Review status. States plainly that no real outcome data exists yet — program hasn't launched.
WEB-23 | pathway-documents/work-package-2-website/staging-pages/GCSD_CulinaryPathway_WEB-23_FAQ-Partial_v1.0_2026-07-12.html | HTML (staged) | pathway-documents/work-package-2-website/staging-pages/ | Internal Review status. Partial — only Gateways/Passport, Courses, and Credentials sections; full FAQ awaits Work Package 2B Phase 2.
SBE-02,04,08,09,10,12,13,17 | pathway-documents/work-package-4-cottage-kitchen-management/GCSD_CulinaryPathway_SBE-02-04-08-09-10-12-13-17_Cottage-Operations-Instructional-Guide_v1.0_2026-07-12.docx | Word | pathway-documents/work-package-4-cottage-kitchen-management/ | Master reference manual, 8 Register items consolidated into sections/appendices. Includes Gateway 4 → CMP-02 Passport cross-reference.
SBE-03,06,07,11 | pathway-documents/work-package-4-cottage-kitchen-management/GCSD_CulinaryPathway_SBE-03-06-07-11_Event-Planning-Packet_v1.0_2026-07-12.docx | Word | pathway-documents/work-package-4-cottage-kitchen-management/ | Fillable 4-part planning packet, completed together during the planning phase.
SBE-05 | pathway-documents/work-package-4-cottage-kitchen-management/GCSD_CulinaryPathway_SBE-05_Client-Agreement_v1.0_2026-07-12.docx | Word | pathway-documents/work-package-4-cottage-kitchen-management/ | Kept separate (legal/contractual). Payment/cancellation/liability terms explicitly flagged pending district counsel review.
SBE-15,16,17 | pathway-documents/work-package-4-cottage-kitchen-management/GCSD_CulinaryPathway_SBE-15-16-17_Event-Closeout-Financial-Reconciliation-Record_v1.0_2026-07-12.docx | Word | pathway-documents/work-package-4-cottage-kitchen-management/ | Financial/inventory reconciliation, closeout review, and student reflection combined — staff-facing, RESTRICTED.
SBE-14 | pathway-documents/work-package-4-cottage-kitchen-management/GCSD_CulinaryPathway_SBE-14_Client-Feedback-Form_v1.0_2026-07-12.docx | Word | pathway-documents/work-package-4-cottage-kitchen-management/ | Kept separate (external client-facing).
SBE-19 | pathway-documents/work-package-4-cottage-kitchen-management/GCSD_CulinaryPathway_SBE-19_Cottage-Event-Register_v1.0_2026-07-12.xlsx | Excel | pathway-documents/work-package-4-cottage-kitchen-management/ | RESTRICTED annual log, 3 tabs including a live-formula Annual Summary. Example rows clearly marked, to be deleted at first real use.
CUR-03 | pathway-documents/work-package-4-cottage-kitchen-management/GCSD_CulinaryPathway_CUR-03_Kitchen-Management-Scope-Sequence_v1.0_2026-07-12.docx | Word | pathway-documents/work-package-4-cottage-kitchen-management/ | 7-unit course document, deferred here from Work Package 3. Explicitly states it is not additional cooking instruction. Flags that CMP-03-07 (Work Package 3) needs a follow-up update now that this exists.
KM-02,03,04,05 | pathway-documents/work-package-4-cottage-kitchen-management/GCSD_CulinaryPathway_KM-02-03-04-05_Kitchen-Management-Student-Leadership-Handbook_v1.0_2026-07-12.docx | Word | pathway-documents/work-package-4-cottage-kitchen-management/ | Core handbook plus Leadership Assignment Brief and Resource Management Plan as appendices.
KM-06,08 | pathway-documents/work-package-4-cottage-kitchen-management/GCSD_CulinaryPathway_KM-06-08_Kitchen-Management-Event-Leadership-Packet_v1.0_2026-07-12.docx | Word | pathway-documents/work-package-4-cottage-kitchen-management/ | Event Leadership Record + Post-Event Debrief, same event/moment.
KM-07 | pathway-documents/work-package-4-cottage-kitchen-management/GCSD_CulinaryPathway_KM-07_Kitchen-Management-Leadership-Observation-Rubric_v1.0_2026-07-12.docx | Word | pathway-documents/work-package-4-cottage-kitchen-management/ | Live observation instrument operationalizing CMP-03-07's Gateway 5 domains — cross-references rather than duplicates the standard.
KM-10 | pathway-documents/work-package-4-cottage-kitchen-management/GCSD_CulinaryPathway_KM-10_Career-Readiness-Completion-Checklist_v1.0_2026-07-12.docx | Word | pathway-documents/work-package-4-cottage-kitchen-management/ | Travel Rights decision-gate checklist.