## Read Me
GCSD Culinary Pathway ¦ Production Control Document
Production Control Log
Three tabs: Change Log, Unresolved Decisions, Legal/Policy Verification Flags. Update all three at the close of every work package.
Title | GCSD Culinary Pathway Production Control Log
Audience | Kevin McCann (Pathway Lead); lead editor; work-package leads
Purpose | One running record, across every work package, of what changed, what remains an open decision, and what still needs current official legal/policy verification before it can be finalized.
Owner | Lead Editor
Version | 4.0
Date | July 2026
Approval / Planning Status | Planning document; not adopted district policy
Access Classification | RESTRICTED — production control document
Governing Source | Production brief "OUTPUT EXPECTATIONS" and "ADDITIONAL CONTROL" sections; GOV-09 Document Control and Versioning Procedure; Kevin McCann's 2026-07-12 quality-control corrections and next-sequence instructions
Review Date | Updated at the close of every work-package pass, not on a fixed calendar
Superseded Document | v1.0–v3.0, all superseded 2026-07-12 — archived to pathway-documents/_archive/. v4.0 adds Work Package 4 and Work Package 2B Phase 1 change-log entries.

## Change Log
GCSD Culinary Pathway Change Log — RESTRICTED — Planning document; not adopted district policy
Date | Work Package | Source Used | Material Retained | Material Revised | Material Replaced | Material Archived | New Material Created | Notes
2026-07-12 | Work Package 1 | Canon v3.0; Operating Principles v1.0; Master Document Register v1.0; Books One–Four | Canon, Operating Principles, Register, Books One–Four (KEEP per Register) | None this pass | None this pass | None this pass | GOV-08 Glossary; GOV-09 Document Control Procedure; GOV-10 Authorization Register v1.0; GOV-11 Review Calendar; GOV-12 Companion Document Map; Master Execution Matrix v1.0 | First production pass. Status: production complete, awaiting Kevin McCann's visual QA review.
2026-07-12 | Work Package 1 (revision) | Kevin McCann decisions on Senior WBL, SkillsUSA, and sequencing | GOV-08, GOV-09, GOV-12 (unchanged) | GOV-10 (PA-06 Senior WBL and PA-13 SkillsUSA status language); Master Execution Matrix (WP2 split into 2A/2B, WP3 status, WP5 hold, decisions resolved) | None | GOV-10 v1.0; Master Execution Matrix v1.0 — both moved to pathway-documents/_archive/ with -ARCHIVED suffix | Production Control Log (this workbook) | Same-day major-version revision per GOV-09 Section 6 (substantive change to authorized public-facing status language).
2026-07-12 | Work Package 2A | Live website (index.html, pages/*.html, assets/css/styles.css — read only, not modified); Canon; GOV-10 v2.0; GOV-09 | Live site content and design system (read for reference, not altered) | None — all WP2A items were CREATE per the reconciliation memo | None | None | WEB-01 Migration Spec; WEB-25 Page Template Standards (provisional ID); WEB-19 Status-Label System; WEB-22 Download Index structure; WEB-24 Ownership Schedule; staged HTML for WEB-02, WEB-13, WEB-21, WEB-20; status-labels.css | 9 files produced. Live site confirmed untouched. Nothing deployed or published.
2026-07-12 | Work Package 3 | Canon; Book Two; source materials (CA 1&2 outline, Advanced Culinary S&S, 3x Skills Map, Employability Profile template) | Original table structures in Employability Profile (6 tables preserved, 1 added) | CA 1&2 outline and Advanced Culinary S&S (analyzed in one alignment memo — sources themselves not yet revised); Skills Map (reconciled from 3 duplicates); Employability Profile (revised as a separate file, source confirmed untouched) | None | Recommends archiving the 2 duplicate Skills Map source files (content-identical to the 3rd) once Kevin McCann confirms | CUR-05 reconciled Skills Map; CUR-06 Evidence Crosswalk; CUR-07 Credential Crosswalk; CUR-08 Assessment Inventory; CMP-02 Passport workbook; CMP-03-07 Gateway 1-5 rubrics; CMP-08 Gateway 6 rubric (conditional); CMP-14 Evidence Naming Guide | 10 files produced. Boxed conditional-draft statement verified present on CMP-08. Two open questions logged to Unresolved Decisions (UD-06, UD-07) — see the 2026-07-12 correction entry below for how they were resolved.
2026-07-12 | Quality-control correction (Kevin McCann) | Kevin McCann's item-by-item review of Work Packages 2A/3 | GOV-08, GOV-09, GOV-11, GOV-12, WP2A staged HTML pages, WEB-19/22/24 (unchanged) | GOV-10 (v2.0→v3.0: PA-02/03/04 course-title language, UD-05); Master Execution Matrix (v3.0→v4.0: WP3 status corrected, OPS-01–21 reassigned individually, GOV-13 cross-references); Production Control Log (this entry); WEB-01 (GOV-13 cross-reference); CUR-05 (v1.0→v1.1: Strategies for Success reclassified, UD-07) | None | GOV-10 v2.0, Master Execution Matrix v3.0, CUR-05 v1.0, and the WEB-25-named file all archived to pathway-documents/_archive/ with -ARCHIVED suffix | GOV-13 (relocated from provisional WEB-25, UD-06); WP3 File-Level Manifest (new — confirms only the alignment memo exists for CUR-01/02, not revised course documents); Source Immutability Verification (embedded in the manifest — confirms no source materials/ file was modified in place) | Corrections applied: (1) verified and documented source-file immutability — no violation found, agent report language was imprecise, not inaccurate about outcomes; (2) WP3 status corrected from overstated "production complete" to "architecture and alignment complete — course-document revision pending"; (3) OPS-01–21 reassigned individually per operational domain (UD-04), single cross-cutting row removed; (4) GOV-10 course-status language corrected to not assume Canon course names match official district titles (UD-05); (5) WEB-25 renamed GOV-13 and relocated to governance (UD-06); (6) Skills Map "Strategies for Success" column reclassified with exact required language (UD-07), new UD-08 opened for the underlying identity question.
2026-07-12 | Work Package 4 | Canon; Operating Principles; Book Three (esp. Ch.11–15); CMP-02 Passport; CMP-03-07 Gateway rubrics; GOV-09 | None modified — CMP-02 and CMP-03-07 read only, not edited | None (all new production) | None | None | The Cottage Operations and Instructional Guide (8 Register items consolidated); Event Planning Packet (4 items consolidated); Client Agreement; Event Closeout and Financial Reconciliation Record (3 items consolidated); Client Feedback Form; Cottage Event Register; Kitchen Management Scope and Sequence (CUR-03, deferred from Work Package 3); Kitchen Management Student Leadership Handbook (4 items consolidated); Kitchen Management Event Leadership Packet (2 items consolidated); Leadership Observation Rubric; Career Readiness Completion Checklist | 11 files produced (30 raw Register items consolidated to 11). "Not just a catering business" and "not additional cooking instruction" framing verified present. Gateway 4/5 evidence confirmed routed into the existing CMP-02 Passport, no competing SBE-18/KM-09 file created. One agent run hit a session rate limit after completing all 7 Cottage files cleanly; resumed to finish the 4 remaining Kitchen Management files with no rework. Flags a stale cross-reference in Work Package 3's CMP-03-07 (says CUR-03 doesn't exist — it now does) for that package's owner to update.
2026-07-12 | Work Package 2B Phase 1 | Canon; GOV-13 template; GOV-10 v3.0 status language; Work Package 3 deliverables (CMP-02, CMP-03-07, CMP-08, CUR-07, CUR-01-02) | assets/css/styles.css and the 4 existing WP2A staged pages (read as models, not modified) | None (all new production) | None | None | 7 staged HTML pages: Pathway at a Glance (WEB-03), Six Gateways and Culinary Passport (WEB-04), Courses and Learning Environments (WEB-05), Students and Families overview (WEB-09), Credentials and Recognition (WEB-11), Results and Accountability (WEB-12), partial FAQ (WEB-23) | Verified: exact boxed conditional-draft statement present on Gateway 6 content; SkillsUSA exploratory language used correctly; Cottage/Kitchen Management/WBL sections kept deliberately brief with a visible deferral notice, consistent with the dependency controls. All 7 pages set to "Internal Review," not yet "Approved for Planning Use." Flags a nav-list inconsistency (9 items on new pages vs. shorter nav on the 4 original WP2A pages) for a future reconciliation pass before any deployment.

## Unresolved Decisions
GCSD Culinary Pathway Unresolved Decisions Log — RESTRICTED — Planning document; not adopted district policy
ID | Decision Needed | Raised | Status | Decision / Answer | Decided By | Date Decided | Affects
UD-01 | Draft Senior External WBL materials now, or hold entirely until real authorization exists? | 2026-07-12 | Resolved | Draft now as CONDITIONAL planning documents. Every applicable document must state "Conditional planning draft. Not adopted district policy. Not authorized for implementation." verbatim. May draft structures, templates, workflows, course framework, approval requirements, and launch-readiness materials. Legal, labor-law, insurance, transportation, staffing, fiscal, NYSED-registration, and district-policy claims must not be finalized without current official verification — see Legal/Policy Verification Flags tab. | Kevin McCann | 2026-07-12 | Work Packages 3, 4, 6, 7; Gateway 6; PA-06 (GOV-10)
UD-02 | How should SkillsUSA be represented until chapter status is confirmed? | 2026-07-12 | Resolved | "Exploratory / interest-development stage — active chapter status not confirmed." Use "SkillsUSA development initiative" language. Do not claim an active chapter currently operates. May discuss possible future participation, student interest, informational sessions, and competition opportunities. | Kevin McCann | 2026-07-12 | CUR-11, COM-05, WEB-07; PA-13 (GOV-10)
UD-03 | Sequence Work Packages 2, 3, and 5 — parallel, sequential, or hold? | 2026-07-12 | Resolved | Work Packages 2 and 3 proceed in parallel. Work Package 2 splits into 2A (architecture/navigation/access/status content not dependent on WP3 terminology — proceeds now) and 2B (final page copy for terminology-dependent pages — waits for WP3). Work Package 5 is on hold; do not begin. | Kevin McCann | 2026-07-12 | Work Packages 2, 3, 5
UD-04 | Cross-cutting Program Operations category (H, OPS-01–21, 21 items) is not assigned to a single work package by the Register. | 2026-07-12 | Open | Recommend Kevin McCann confirm the cross-cutting treatment (supports WP4, WP6, WP7 as each is produced) or assign it explicitly to one package. |  |  | Work Packages 4, 6, 7
UD-05 | Confirm current status of Culinary 1, Culinary 2, and Advanced Culinary as active GCSD courses before WP3 revision memos are finalized. | 2026-07-12 | Open | Lead editor marked these Active based on Kevin's prior stated program context; Curriculum Office confirmation still needed before external distribution. |  |  | Work Package 3; PA-02/PA-03/PA-04 (GOV-10)
UD-06 | WP2A's Page Template Set deliverable has no ID in the Master Document Register's WEB-01–24 range. | 2026-07-12 | Resolved | Assigned GOV-13 (Website Page Template and Content Standards). It is a governance and publication-control document, not a public website page — relocated from pathway-documents/work-package-2-website/ to pathway-documents/work-package-1-governance/. All registers, maps, logs, and cross-references updated. | Kevin McCann | 2026-07-12 | Work Package 2A; Master Document Register; Master Execution Matrix
UD-07 | The original Skills Map's "Strategies for Success" column has no match in the Canon or Book Two. | 2026-07-12 | Resolved (classification) / Open (underlying identity) | Classified as "Unverified legacy field — instructional purpose and owner confirmation required." Preserved unrenamed in the untouched source files and as a labeled legacy column in CUR-05 v1.1. Must NOT be used for Gateway completion, Passport evidence, assessment logic, or public claims until Jason Carlson, Corey Skinner, or another authorized GCSD representative confirms its intended purpose — that confirmation itself remains open, tracked as UD-08. | Kevin McCann | 2026-07-12 | Work Package 3; CUR-05 v1.1
UD-08 | What is the "Strategies for Success" field, and who owns it? | 2026-07-12 | Open | Awaiting confirmation from Jason Carlson, Corey Skinner, or another authorized GCSD representative. Until answered, the field stays excluded from all Gateway/Passport/assessment/public-facing use per UD-07's resolution. |  |  | CUR-05 v1.1
UD-09 | Kevin McCann's 2026-07-12 quality-control review found WP3 was reported as "production complete" when only an analysis memo exists for the Culinary 1/2 and Advanced Culinary course revisions. | 2026-07-12 | Resolved | WP3 status corrected to "Architecture and alignment complete — course-document revision pending" everywhere (Master Execution Matrix v4.0, this Log). A WP3 File-Level Manifest was produced identifying exactly what exists vs. is pending. Actual revised, versioned CUR-01 and CUR-02 course documents remain a tracked pending deliverable (see the manifest's "Pending Deliverables" tab), not yet scheduled against a specific work package. | Kevin McCann | 2026-07-12 | Work Package 3; Master Execution Matrix

## Legal-Policy Verification
GCSD Culinary Pathway Legal and Policy Verification Flags — RESTRICTED — Planning document; not adopted district policy
ID | Item Requiring Verification | Applies To | Status | Official Source Needed | Notes
LP-01 | Minor employment and scheduling law (hours, prohibited duties, work permits) | Senior External WBL (EMP-12, BRD-09) | Not verified | Current NYS Department of Labor minor employment regulations; NYSED CO-OP guidance | Do not finalize EMP-11/EMP-12 duty and scheduling language against outdated CTE 566 course-module text.
LP-02 | District insurance and liability coverage for off-site placements | Senior External WBL (BRD-09, OPS-19) | Not verified | District risk management / business office; district insurance carrier
LP-03 | Transportation responsibility and liability for off-campus travel | Senior External WBL (BRD-07, FAM-05) | Not verified | District transportation policy; district legal counsel
LP-04 | Staffing and coordinator credentialing requirements for a WBL Coordinator | Senior External WBL (BRD-06) | Not verified | NYSED WBL Coordinator certification requirements
LP-05 | Fiscal impact and budget authority for course launch | Senior External WBL (BRD-05) | Not verified | District business office current budget cycle
LP-06 | NYSED CO-OP / state registration package requirements and current forms | Senior External WBL (BRD-11) | Not verified | Current NYSED CTE/CO-OP registration guidance (verify at time of submission, not from course materials) | Register's own instruction: verify current forms and terminology at time of submission, not from CTE 566 source PDFs.
LP-07 | District accessibility requirements for public and participant digital documents | Website (WEB-20, OPS-20) | Not verified | District accessibility policy; current WCAG conformance target
LP-08 | District media/photo consent and privacy release requirements | Communications (COM-06, FAM-06) | Not verified | Current district media release and privacy policy — do not create a competing release
LP-09 | SkillsUSA chapter status and any existing advisor/charter documentation | Curriculum (CUR-11), Communications (COM-05) | Not verified | Current SkillsUSA advisor; district activity records | See Unresolved Decisions UD-02.
LP-10 | Current ServSafe Management and YouScience Culinary III passing scores, retest rules, and CTE endorsement requirements | Credentials (CUR-07, CMP-08 Gateway 6) | Not verified | Current ServSafe/YouScience provider documentation; current NYSED CTE endorsement requirements | Work Package 3 deliberately left these as "current provider/NYSED requirements control" per Book Two Chapter 14's explicit instruction not to invent local values.
LP-11 | The Cottage Client Agreement payment, cancellation, and liability terms | The Cottage (SBE-05) | Not verified | District counsel; district business office contract standards | Work Package 4 left these as explicit placeholders rather than inventing binding terms — no prior Legal-Policy item covered Cottage contract terms specifically until this one.