## Read Me
GCSD Culinary Pathway ¦ Production Control Document
Work Package 3 File-Level Manifest
Title | Work Package 3 File-Level Manifest
Audience | Kevin McCann (Pathway Lead); lead editor
Purpose | State exactly what exists, file by file, so Work Package 3's status is reported honestly rather than summarized loosely. Produced in response to Kevin McCann's 2026-07-12 quality-control correction.
Owner | Lead Editor
Version | 1.0
Date | July 2026
Approval / Planning Status | Planning document; not adopted district policy
Access Classification | RESTRICTED — production control document
Governing Source | Kevin McCann's 2026-07-12 quality-control corrections, item 2 ("WP3 Course-Document Status")
Review Date | Superseded when the pending revised course documents are produced
Superseded Document | None — first issue
Finding
• CONFIRMED: no revised, versioned Culinary 1/2 or Advanced Culinary course documents (i.e., new versions of the actual scope-and-sequence/outline documents themselves) were produced. What exists is CUR-01-02, an analysis memo that reads the two real source documents and states what needs to change — it is not itself a revised course document.
• Of the 10 files produced, only two are genuine REVISE actions against an existing authoritative source (CUR-05 Skills Map, CMP-01 Employability Profile) — both confirmed produced as separately named, versioned files with the original source left untouched (see the Source Immutability Verification tab).
• WP3 status is corrected accordingly: "Architecture and alignment complete — course-document revision pending." It may not be described as production complete until the revised Culinary 1/2 and Advanced Culinary course documents actually exist as their own files.

## File Manifest
WP3 File Manifest — RESTRICTED — Planning document; not adopted district policy
Actual Filename | Document ID | Original Source | Status | Version | Approval Status | Access Classification | Document Type
GCSD_CulinaryPathway_CUR-01-02_Course-Alignment-Memo_v1.0_2026-07-12.docx | CUR-01-02 | CA 1 & 2 outline 8_8_25.docx; Advanced Culinary - Scope and Sequence 2023-2024.docx (read for reference only, not modified) | CREATE | 1.0 | Approved for Planning Use | RESTRICTED | Analysis memo — NOT a revised course document. States what CUR-01/CUR-02 need to change; does not itself replace them.
GCSD_CulinaryPathway_CUR-05_Culinary-Pathway-Skills-Map_v1.0_2026-07-12.xlsx | CUR-05 | Culinary_Pathway_Skills_Map.xlsx and 2 duplicate copies (confirmed cell-content-identical; originals untouched) | CONSOLIDATE + REVISE | 1.0 | Approved for Planning Use | PARTICIPANT | Revised authoritative document — genuine content revision, separately versioned, original preserved.
GCSD_CulinaryPathway_CUR-06_Course-Gateway-Evidence-Crosswalk_v1.0_2026-07-12.xlsx | CUR-06 | No prior standalone document existed | CREATE | 1.0 | Approved for Planning Use | PARTICIPANT | Crosswalk — net new.
GCSD_CulinaryPathway_CUR-07_Credential-Recognition-Crosswalk_v1.0_2026-07-12.xlsx | CUR-07 | No prior standalone document existed | CREATE | 1.0 | Approved for Planning Use | PUBLIC | Crosswalk — net new.
GCSD_CulinaryPathway_CUR-08_Assessment-Evidence-Inventory_v1.0_2026-07-12.xlsx | CUR-08 | No prior standalone document existed (built from existing course evidence, catalogued not replaced) | CREATE | 1.0 | Approved for Planning Use | RESTRICTED | Operational inventory — net new.
GCSD_CulinaryPathway_CMP-01_Employability-Profile_v1.0_2026-07-12.docx | CMP-01 | Employability Profile- Culinary Pathway-Template.docx (confirmed untouched — mtime 2026-07-07, predates this session; original placeholder text and typo still present in source) | REVISE | 1.0 | Approved for Planning Use | RESTRICTED | Revised authoritative document — genuine content revision, separately versioned, original preserved.
GCSD_CulinaryPathway_CMP-02_Culinary-Passport_v1.0_2026-07-12.xlsx | CMP-02 | No prior standalone document existed | CREATE | 1.0 | Approved for Planning Use | RESTRICTED | Blank record template — net new, not a filled student record.
GCSD_CulinaryPathway_CMP-03-07_Gateway-1-5-Standards-Rubrics_v1.0_2026-07-12.docx | CMP-03–07 | No prior standalone document existed (built from Canon competency lists and Book Two Appendix B) | CREATE | 1.0 | Approved for Planning Use | PARTICIPANT | Rubric — net new.
GCSD_CulinaryPathway_CMP-08_Gateway-6-Standard-Rubric_v1.0_2026-07-12.docx | CMP-08 | No prior standalone document existed | CREATE | 1.0 | Conditional Planning Draft — Not Authorized | PARTICIPANT | Rubric — net new. CONDITIONAL: Senior External WBL not authorized.
GCSD_CulinaryPathway_CMP-14_Evidence-Naming-Storage-Guide_v1.0_2026-07-12.docx | CMP-14 | No prior standalone document existed (cross-references GOV-09 rather than restating it) | CREATE | 1.0 | Approved for Planning Use | RESTRICTED | Procedure — net new.

## Pending Deliverables
Pending WP3 Deliverables — Not Yet Produced
Document ID | Title | Status | What Exists Today | What's Missing
CUR-01 | Revised Culinary 1 and Culinary 2 Outline | Pending | Analysis in CUR-01-02 Course Alignment Memo describing required changes | An actual revised, versioned replacement for CA 1 & 2 outline 8_8_25.docx, incorporating the memo's findings, aligned to Gateways 1-3
CUR-02 | Revised Advanced Culinary Scope and Sequence | Pending | Analysis in CUR-01-02 Course Alignment Memo describing required changes | An actual revised, versioned replacement for Advanced Culinary - Scope and Sequence 2023-2024.docx, aligned to Gateway 4 / The Cottage
CUR-03 | Kitchen Management Scope and Sequence | Deferred to Work Package 4 | Not started | Deliberately deferred per the WP2A/WP3 Reconciliation Memo — belongs with Work Package 4's Cottage/Kitchen Management operational build.

## Source Immutability
Source Immutability Verification — performed 2026-07-12 in response to Kevin McCann's correction
Source File | Location | Verification Method | Result | Revised Copy (if any)
Employability Profile- Culinary Pathway-Template.docx | source materials/ (SOURCE / LEGACY) | File mtime (2026-07-07, predates this session) + content check: original "Insert exam name here" placeholder and unfixed "Serve Safe" typo still present; "YouScience" absent | CONFIRMED UNTOUCHED — not modified in place, despite the earlier agent report's imprecise "edited in place" phrasing (it produced a separate file, it did not overwrite the original) | CMP-01_Employability-Profile_v1.0_2026-07-12.docx (work-package-3-curriculum-passport-gateways/)
CA 1 & 2 outline 8_8_25.docx | source materials/ (SOURCE / LEGACY) | File mtime (2026-07-07, predates this session) | CONFIRMED UNTOUCHED | None yet — see Pending Deliverables tab (CUR-01)
Advanced Culinary - Scope and Sequence 2023-2024 .docx | source materials/ (SOURCE / LEGACY) | File mtime (2026-07-07, predates this session) | CONFIRMED UNTOUCHED | None yet — see Pending Deliverables tab (CUR-02)
Culinary_Pathway_Skills_Map.xlsx (+ 2 duplicate copies) | source materials/ (SOURCE / LEGACY, all 3 copies) | File mtime (2026-07-07, predates this session) on all 3; cell-by-cell content comparison confirms all 3 are content-identical (note: raw file MD5 differs slightly due to xlsx zip-container metadata, not cell content — the earlier agent report's "same MD5 hash" phrasing was imprecise, the correct claim is identical cell content) | CONFIRMED UNTOUCHED, all 3 copies | CUR-05_Culinary-Pathway-Skills-Map_v1.0_2026-07-12.xlsx (work-package-3-curriculum-passport-gateways/)