## Read Me
GCSD Culinary Pathway ¦ Work Package 6 ¦ CONDITIONAL PLANNING DRAFT
Legal, Policy, and Credential Dependency Log
Every unresolved legal/policy dependency found while producing Work Package 6 — no answer invented for any item.
Conditional planning draft. Not adopted district policy. Not authorized for implementation. This log exists precisely because the items below are NOT yet verified — do not treat any row as confirmed until it carries a real Verification Date and named official source.
Document ID | WP6 Legal-Policy Dependency Log
Title | Work Package 6 Legal, Policy, and Credential Dependency Log
Audience | District Leadership, District Legal Counsel, District Business Office, WBL Coordinator
Purpose | Compile every point in Work Package 6 (Employer, Mentor, Training Station, and Conditional External WBL System) where labor law, NYSED requirements, insurance, accessibility, district policy, or credential requirements are relied upon but cannot be verified from documents currently available. No answer is invented for any of these items.
Owner | WBL Coordinator (pending assignment); District Administration
Version | 1.0
Date | July 2026
Approval / Planning Status | CONDITIONAL PLANNING DRAFT — Not adopted district policy — Not authorized for implementation
Access Classification | RESTRICTED
Governing Source | Kevin McCann's explicit Requirement 4 instruction, 2026-07-12; Production Control Log's Legal-Policy Verification tab (LP-01 through LP-11); GOV-10 PA-06, PA-14
Review Date | Immediately upon any Board or District Leadership action affecting PA-06 or PA-14 authorization
Superseded Document | None — first issue. Supplements, and does not replace, the Production Control Log's Legal-Policy Verification tab (LP-01 through LP-11). Items already logged there are cross-referenced by ID, not re-derived. New items found during Work Package 6 production are assigned LP-12 onward, continuing that sequence.
Required Action | District Legal Counsel, the District Business Office, and District Administration must resolve each item's Unresolved Dependency and record a Verification Date and finding before the corresponding Work Package 6 document can move beyond Conditional Planning Draft status.
How This Log Relates to the Production Control Log
• The Production Control Log (pathway-documents/GCSD_CulinaryPathway_Production-Control-Log_v4.0_2026-07-12.xlsx), Legal-Policy Verification tab, already lists LP-01 through LP-11 — project-wide dependencies raised by earlier work packages.
• This log's 'Dependency Register' tab restates every LP item that a Work Package 6 document actually depends on (cross-referenced by ID, language unchanged) alongside newly found items, so a reader can see the complete Work Package 6 legal/policy picture in one place without cross-opening two files.
• New items found during Work Package 6 production are assigned LP-12 onward, continuing the existing sequence. They should also be added to the master Production Control Log by its owner (Lead Editor) at the next project-wide update — this log does not itself edit that file.
• Every field below follows the exact structure Kevin McCann required: Source, Verification Date, Unresolved Dependency, Responsible Reviewer. No legal/policy specific was invented to fill a gap; every unresolved item is stated as unresolved.

## Dependency Register
WP6 Legal-Policy Dependency Register — RESTRICTED — CONDITIONAL PLANNING DRAFT
ID | Applies To (WP6 Document) | Source (What Official Source Would Confirm This) | Verification Date | Unresolved Dependency | Responsible Reviewer | Origin
LP-01 | EMP-03, EMP-04, EMP-10-11-13, EMP-12, EMP-18, OPS-19, WBL Coordinator Operations Workbook (OPS-07/10/14 tabs) | Current NYS Department of Labor minor-employment regulations; NYSED CO-OP guidance | Not yet verified | Permitted hours by age/school-day status, prohibited/hazardous duties, work-permit requirements, wage/payroll classification for a minor worker in food service. Do not finalize any EMP-11/EMP-12 duty or scheduling language against outdated CTE 566 course-module text. | District Legal Counsel; District Business Office | Cross-reference — Production Control Log LP-01
LP-02 | EMP-04, EMP-06, OPS-19 | District risk management / business office; district insurance carrier | Not yet verified | Whether district insurance/liability coverage extends to a student at an off-site employer training station, and under what conditions. | District Business Office; District Legal Counsel | Cross-reference — Production Control Log LP-02
LP-03 | EMP-03, EMP-10-11-13, OPS-19, WBL Coordinator Operations Workbook (OPS-14 tab) | District transportation policy; district legal counsel | Not yet verified | Whether the district or the family is responsible for transportation to an off-campus training station, and what liability follows each option. | District Legal Counsel; District Transportation | Cross-reference — Production Control Log LP-03
LP-04 | OPS-19; Mentor Handbook (EMP-07-08-09) references to 'credentialed WBL Coordinator' | NYSED WBL Coordinator certification requirements | Not yet verified | What credential(s) the assigned WBL Coordinator must hold before the course and placements can be supervised. | District Administration; NYSED liaison | Cross-reference — Production Control Log LP-04
LP-05 | OPS-19 | District business office current budget cycle | Not yet verified | Fiscal impact and budget authority required to launch the course, staff a coordinator, and support the training-station system. | District Business Office | Cross-reference — Production Control Log LP-05
LP-06 | OPS-19; EMP-06 (Employer Partnership Agreement compliance section) | Current NYSED CTE/CO-OP registration guidance — verify at time of submission, not from course materials | Not yet verified | Current NYSED CO-OP/state registration package requirements and forms applicable when the course is submitted for state registration. | District Administration; NYSED liaison | Cross-reference — Production Control Log LP-06
LP-12 | EMP-20 Incident Report | District Administration current incident-reporting policy | Not yet verified | The district's official incident-reporting form, submission process, timelines, and responsible office for a Work-Based Learning placement incident. EMP-20 deliberately provides only a structural template pending this confirmation, per the production brief's instruction not to invent a district incident-reporting process. | District Administration | New — found in Work Package 6 (EMP-20)
LP-13 | EMP-02 Partner Interest Form; EMP-03 Training Station Profile; EMP-06 Employer Partnership Agreement | District business office / HR; NYS working-papers process | Not yet verified | Whether working papers are required for a student in this placement type, who issues them, and the process/timeline for obtaining them before a placement may begin. | District Business Office; WBL Coordinator | New — found in Work Package 6 (EMP-02/03/06)
LP-14 | EMP-06 Employer Partnership Agreement; EMP-03 Training Station Profile (Section 10, Compensation) | District business office; NYS Department of Labor wage and hour requirements | Not yet verified | Whether and how a student may be paid for a training-station placement (minimum wage applicability, payroll mechanics, tax/withholding responsibility), and what district payroll or contracting process, if any, applies when an employer pays a student directly. | District Business Office; District Legal Counsel | New — found in Work Package 6 (EMP-03/06)
LP-15 | OPS-19; WBL Coordinator Operations Workbook (OPS-12 tab, Incident and Corrective-Action Register) | District policy on mandated reporting and harassment/discrimination investigation for an off-site work setting | Not yet verified | How the district's existing mandated-reporting and harassment/discrimination investigation procedures apply when the reported conduct occurs at an external employer site rather than on school property, and who has investigative authority in that setting. | District Legal Counsel; District Administration (Title IX/Compliance) | New — found in Work Package 6 (OPS-19, EMP-19/20)
LP-16 | EMP-01 Employer and Community Partnership Overview; future WEB-10 public page (Work Package 2B Phase 2B) | District communications policy; district legal counsel | Not yet verified | What level of public detail about a prospective employer (name, logo, description) may be published before a formal partnership agreement (EMP-06) is signed, to avoid implying an endorsement or partnership that does not yet exist. | District Communications; District Legal Counsel | New — found in Work Package 6 (EMP-01)

## Summary
Summary
Total items on this log | 11
Cross-referenced from existing Production Control Log (LP-01–LP-06) | 6
New items found in Work Package 6 (LP-12–LP-16) | 5
Items with a completed Verification Date | 0
Note: LP-07 through LP-11 on the Production Control Log (accessibility, media/photo consent, SkillsUSA, credential passing scores, Cottage contract terms) were reviewed and do not apply directly to Work Package 6's employer/mentor/training-station scope, so they are not restated here. See the Production Control Log itself for those items.